## Slide 1: WP1 meets WP2
Status and activities
Alessandro Costantini
INFN-CNAF

## Slide 2: WP1 – Topics for the All Hands
WP1 - Project Management (NA1)
  T1.1: Consortium coordination and Project Management
  T1.2: Financial Management
  T1.3: Project Quality Assurance and Activities Oversight
  TT1.4: Communication
Review QA metrics and KPIs
  How are we behaving?
Consortium Agreement Signature
  during the Collaboration Board
Liaisons with EOSC-Hub (in collaboration with WP3/WP2)
  We should be ready for exploitation
    What is missing? A service catalogue? A White paper?
Review expenses reporting
Start discussing the preparation of the First EC review (PM16/17)
Communication
  How to improve website updates
  Gadgets, Twitter etc..
Track WP1 activity in confluence?
  Also WP4 and WP5
Collect publications list
INDIGO review outcome analysis

## Slide 3: WP1 and WP2 Activities
The Work Package is composed of four tasks:
  Task T1.1: Consortium coordination and Project Management
  Task T1.2: Financial Management
  Task T1.3: Project Quality Assurance and Activities Oversight
  Task T1.4: Communication
WP2
  Task T2.1 Use Case Analysis
  Task T2.2 Solutions for the EOSC Data Management
  Task T2.3 Integration and Testing
  Task T2.4 Dissemination and Training

## Slide 4: Summary
Recommendation to indigo follow-up projects
Communication and Dissemination
Project metrics and status
Liaisons with other projects
  EOSC-Hub
  DEEP
  CDB
Discussion on the first EC review

## Slide 5: Recommendation to indigo follow-up projects
Major effort has been put into adequate metrics and thresholds to measure the success of use [….]. Based on this exercise the metrics itself as well as the procedure to assess the metrics should be optimised in future projects.
What is missing so far is a clear plan for uptake of the results and spread of tools and services to other research communities not involved in INDIGO or one of the upcoming projects
Work in this area (collaboration with e-infras) must be expanded to gain wider acceptance, and the EOSC-Hub is a good platform to address this
The project should publish in gold open access journals and conferences
A comprehensive networking solution should be considered for future projects leveraging INDIGO deliverables
More extensive scalability testing should be performed to have a convincing case when interacting with other EINFRA. INDIGO will need to demonstrate that platform and framework can scale
Continue and expand on training events to promote user and community adoption
QoS standard implemented in OneData

## Slide 6: Communication and Dissemination
Dissemination Plan D2.2
  https://confluence.extreme-datacloud.eu/display/XDCPROJ/Dissemination+Events
Dissemination Events
  https://confluence.extreme-datacloud.eu/display/XDCPROJ/Dissemination+Events
Publications
  https://confluence.extreme-datacloud.eu/display/XDCPROJ/Publications

## Slide 7: Communication and Dissemination
Communication strategies
  Gadget to be prepared for oncoming events
    T-shirt, stickers, …
    Social media
  Dissemination activities
    Half day session in major conferences and events
    Demo needed
Dissemination actvities
  Training
    School/Course on the Santander model

## Slide 8: Santander Course
Agenda with material available
  Can be used for dissemination
  First example of interaction with external projects
  https://agenda.indigo-datacloud.eu/conferenceTimeTable.py?confId=214#20180619

## Slide 9: Project metrics and status
Area | KPI | Achieved | Notes
User Community adoption | Number of research communities internal and external to the project that adopted the developed services 5/7/10 Number of extreme scale future experiments evaluating the developed services 1/3/5 Number of use-cases implemented on the e-infrastructures that take advantage of the project developments 5/8/12 Number of applications using the developed services 5/8/12 | - - 5 - | 
User Community productivity and involvement | Number of publications related to researches and use cases that exploit the developed services 4/6/8 Tutorials/demos on developed services made available 1/3/5 | 1 - | 2 in submission
Project visibility and role in policy making | Number of contributions to roadmaps and strategic papers 3/5/7 Number of presentation at international conferences and workshop 15/20/30 Number of scientific paper published by the project members 6/8/12 Website and social network activity. Quarterly growth rate(%) 5/10/20 Software repositories activity. Quarterly average growth rate(%) 3/5/15 | - 9 1 Q2: 60% - | WP2 Q3: 30% WP3
Project Technical Productivity | Number of new functionalities addressing real requirements released 3/5/7 Number of major and minor releases 3/5/7 Number of high level requirements received 4/8/12 Number of high level requirements addressed and implemented 4/8/12 | 3 - - - | WP2 WP2/JRAs
E-Infrastructures adoption | Number of sites that deployed services developed by the project 4/6/8 Number of XDC services deployed in production in Europe and Worldwide 4/6/8 | - - | 
D1.2 Project Quality Assurance and Progress Monitoring Plan
  https://nextcloud.extreme-datacloud.eu/s/CBPHDAf44kaWXG2#pdfviewer

## Slide 10: Liaisons with other projects
EOSC-hub
  User involvement
    Engage with external users from day 1
    An interactive way to recieve direct suggestion
    E.g., a INDIGO-XDC webinar for EOSC-hub CCs, TCs
  Design considerations
    Interoperability with other EOSC services
    Service/soft provisioning model suits for EOSC context
  XDC service catalogue
    White paper used for dissemination

## Slide 11: Liaisons with other projects
DEEP
  Some people are working in both projects
  Common WP3 activity
  Common usecase (from Santander)
    Provide storage managemetn components and services
    https://docs.google.com/document/d/1eLZUdDwk2k7qPWUgbSjQkkXcDEesFw2Ch-yIPDipchQ/edit
Other E-INFRA21 project
  Invited at EOSC-Hub week in Malaga
  No more contacts

## Slide 12: Liaisons with other projects
CDB
  Ongoing activity under the TRUST-IT coordination
  Joint XDC, DEEP, INDIGO projects
  Project management and branding strategies
    Maximize communication and dissemination
  Phase 5
    They need 2 people for each project to start a management,dissemination and communication course
    Online course with final evaluation
  Limited interest from projects
  Leave the CDB project is not an option

## Slide 13: Discussion on the first EC review
Deliverables and Milestones
  https://docs.google.com/spreadsheets/d/1Yv4vGvvGFClitMkfLunu6hOc-xA_xY2MdjjnaUyM3Hg/edit#gid=0
  Almost in time but…
    Architecture still missing
    Justification about the D3.1 submission
      Due at M4, submitted at M
  Add deadlines in the XDC calendar?
Concentrate on Demo from usecases
  Devs and Users made aware of common tools and criterias and how to use them
  Starting populate Confluence and JIRA
    Track activities