## Slide 1: Joint Operation & Readiness meeting
Report Operation / Photon Run Coordinator
Report Dispatch
Instruments
  FXE
  SPB/SFX
  SCS
  SQS
  MID
  HED
Beam transport
  Task force XTD6 installation
  Vacuum
  X-ray optics
  Photon diagnostics
Optical lasers
Detectors
Electronics
  AE
  EETF
CAS
ITDM
SRP
Technical services
AoB

## Slide 2: X-ray Diagnostics, week 34-2018 - 1
XGM
Unexplained behavior seen last weekend in XGM@XTD2 during switching of number of bunches from 1 to multibunch (without SASE3 operation): Investigation showed a combination of effects : if the SA1-SRA is too open, the XGM@XTD2 Keithleys in SA1 can detect significant additional signal depending on the number of bunches sent to TLD and SA2 ! --> Preliminary Conclusion: open SRA for SASE tuning, but mandatorily close SRA around FEL beam (check with IMGFEL) once lasing is established and definitely before going to multibunch and/or user operation
XGM Status: operating in XTD1, XTD2, XTD9. Shutdown in XTD10. Under technical commissioning in XTD6. Under construction in SCS.
Imagers
SQS_XTD10_IMGES repaired (motor issue for optics switching)
  Report on Radiation damage of scintillators on two imagers: SQS_XTD10_IMGES, SQS_XTD10_IMGPI. https://docs.xfel.eu/share/page/site/xfelwp74/document-details?nodeRef=workspace://SpacesStore/fd862f30-c6a3-4a5e-9a65-817cbcebb2d9 Preventive actions: Interlock for bunch modes established for all imagers in SASE3, with AE.
  Karabo macro for warning message for focussed beam integrated in scenes of SASE3 imagers, for imagers downsream of focussing optics, i.e. for SQS_XTD10_IMGES, SCS_XTD10_IMGES, SQS_XTD10_IMGPI, SCS_XTD10_IMGPI

## Slide 3: X-ray Diagnostics, week 34-2018 - 2
KMONO
absolute calibration of Kmono in SASE3 and SASE2
  SASE3: scanned KMONO in 2-bounce mode from 3rd until 23rd harmonic of the fundamental (914.6eV)
  SASE2: scanned KMONO from fundamental (6.6keV) to the 5th harmonic. In addition a monochromator glitch at 8.62 keV was measured (XOP calculation: 8.6192 keV)
Further data evaluation necessary.
PES
Detector [06 SE] has shorter TOF than other detectors. Loose HV connection suspected (could be inside the vaccuum chamber). Detector [15 NNW] MPOD channel goes in to error mode when more than 2000 V are applied on the MCP. This problem emerged during the high energy pulses of about 6 mJ. TOF data sets collected during parasitic use of beam last week : data collected as a function of different undulator gaps and different voltage settings, but more beamtime is needed. Diamond Detectors
Coordination meeting (MID, HED, XPD) for implementation of DDs in the SASE2 instruments

## Slide 4: Laser
SASE 1:
PP-laser is in operation. First user run with FXE started this wek. All required specs and tools for controlling the PP-laser are available (pulse energy, -patterns, etc.)
Laser shutter: one cause for erratic occurence of errors was identified. A fix was implemented to all SASE 1 shutters this week. Time will tell...
LAS is providing OCD according to published plan.
SASE 3:
components and sub-systems installation has started.
seeder, Front-End and high power pump amplifiers, shutters were placed on table in SASE 3
SASE2:
under table cabling still not started
high power pump amplifiers were placed on table

## Slide 5: Detectors – DET -1
1st AGIPD SPB
  Preparation of the detector for the User beam time:
    18 till 19. August detector commissioned with X-rays
    Detector configuration for 176 memory cells and 1MHz operation defined and tested with X-ray beam
    Calibration data (i.e. darks and pulse capacitor scans ) for different operation modes was taken and processed for 176 memory cells
    Calibration X-ray data was taken for 120 memory cells  processing ongoing

## Slide 6: Detectors – DET -2
2nd AGIPD MID
  transportation from CFEL lab to HERA South scheduled on 28. August 2018
  Calibration data was taken at CFEL lab and copied to XFEL
  Preparation for detector installation and tests in the DET lab in HERA South ongoing

## Slide 7: Detectors – DET - 3
DSSC
  Testing of the DSSC vessel
  New RGA confirmed oil-free vacuum with the new pressure. RGA brought back to HERA South, filament degassed, RGA to be repeated when the vessel is at XFEL.
  Leak detector revealed the leak on the side flanges and not on the vessel. This opens the way to bring the vessel to HERA South.
  Discussion on the document prepared for the definition of the remaining tasks on the vessel is ongoing, input from CFEL expected soon.
  Quadrant mounting tool under test with real components, outcome expected this week.
  PLC system to be updated
    Change request now approved, work on the crate can start.
  Power supply control in Karabo
    Tables produced by CAS, to be checked
    Manpower allocated for the testing
FastCCD
  Calibration measurements with PulXar finalized
  Detector moved from HERA South to the detector laboratory in XHQ

## Slide 8: AE
SASE3 Tunnel:
Working in an interlock solution to have safe state in the tunnel in order to prevent instruments shutter to be damaged. Will be implemented next Tuesday, but we can already make some loops updates between Friday and Monday (GATT and EPS updates).
SQS:
Loop 4 in SQS will have new interlock definition and coordinated motion configured. Waiting for some motor cables to be connected in order to bring up loop 6.
SCS:
Since they have no beam, taking advantage to go deeper in some cable issues.
There was one faulty ELMO and has been replaced alredy, this was detected when FMB was doing tests.
Waiting for input to bring up loop 4, now all cables should be in place.
MID: all crates placed for loops 1 and 4, starting to connect PLCs now.
SASE2 Tunnel:
Starting to focus on HED loop.
Tests for CRL are going to be done on Monday, after JJXray were doing some alignment work.

## Slide 9: TS – Heating interruption
Due to VATTENFALL maintenance there will be an interruption of the heat supply from the 28.9 afternoon until the 29.9.2018 11p.m
Setup time, only affects the Undulators  NO issue.