## Slide 1: LCLS-II Cryomodule Transportation Experience and Lessons Learned
Tom Peterson
LCLS-II Project, SLAC
6 Feb 2019
TTC Working Group 4

## Slide 2: LCLS-II 1.3 CM Transport System
Transportation Frame
1.3 GHz CM
End Cap
Feed Cap
Beam

## Slide 3: LCLS-II 1.3 GHz cryomodule – 8 superconducting niobium RF cavities, 12 meters long assembly

## Slide 4: Transport System. DESY Feed Cap Sectional View
Shipping end cap supports 300 mm pipe with attachment to
vacuum vessel flange. Support is provided in all directions.

## Slide 5: 1.3 GHz Cryomodule Mass

## Slide 6: Transport Accelerations – Summary of NASA Study
“Structural Design Criteria Applicable to a Space Shuttle,”
NASA Space Vehicle Design Criteria (Structures), NASA SP-8057,1971.

## Slide 7: Sea transport – slow motion but large angles possible

## Slide 8: Acceleration vs Time – DS Outer Frame (Truck)

## Slide 9: Our experience for truck transport with transport frame
  X – horizontal side motion
  Y – vertical
  Z – horizontal travel direction
  On the truck trailer bed with air-ride suspension
    X < 2.5 g
    Y < 2.5 g
    Z < 1.5 g
  At our cryomodule on the inner frame on springs
    X < 1 g
    Y < 1.5 g
    Z < 1 g

## Slide 10: CAD model cross section at RF power coupler
Center part of coupler between bellows is free to oscillate front to back in this image, cryomodule axis direction. Relative motion of cavity string and coupler in X (cavity string swinging side-to-side in this image) is also taken mostly via the inner coupler bellows.

## Slide 11: Coupler internal motion during shipping
Analysis predicts 16 Hz. During last road test,
we measured 15 Hz with amplitudes sufficient
to damage the bellows.

## Slide 12: MODE 1 (12 Hz) :Rocking Mode in X-Dir
Y
Z
X

## Slide 13: Many resonance frequencies in the 10 – 20 Hz range

## Slide 14: Key improvements in transportation system
Reconfigured CM isolation frame springs:
lowered frame Z motion resonance from 13 Hz to 7 Hz
Constrained bellows motion:
increased coupler Z motion resonance from 15 Hz to > 30 Hz
Improved shipping frame spring configuration

## Slide 15: “M-mount” constraint of assembled coupler
Neoprene constraint sits on G-10
block, held with tie-wrap.
Limits Z (coupler lateral) motion
but permits axial movement.

## Slide 16: A cage of thin rods – another transport option (tested and proven OK but not presently in use)
Warm half of coupler removed, so disconnected from vacuum vessel.
Cold half constrained by a cage of thin rods.
This shipping method was verified with two short road tests, a 3000 mile
road test to JLab, and was our configuration for F07 delivery to SLAC.
Shake table test model

## Slide 17: Lessons learned
Design for transportation
    Seismic design is different – short duration.
    Transportation may mean long periods of vibration with risk of fatigue failure.
Shipping after cold test may be different from shipping before cold test.
    Thermal cycling can loosen fasteners in ways which room-temperature vibration does not, so the sequence of the two events (cold test and shipping) may make a difference.
Small differences in design and structure may provide dramatically different results.
Take time to reexamine key features even in a “copied” design.
    Perform an in-depth review (not just PPT slides) of the design early during the project.
    This review may take the form of a risk analysis or a Failure Mode and Effects analysis, a detailed look for failure modes.

## Slide 18: Engage shipping professionals
Just a comment –
Our experience was that shipping professionals can provide very detailed, practical advice and experience regarding specific plans and modes of transport.

## Slide 19: Acknowledgements
The partner labs and entire collaboration responded immediately and with continued intense, expert effort to bring us to our present understanding and set of solutions.
Thanks to people in the LCLS-II collaboration for slides, images, information and all the excellent work which I have only briefly summarized in this presentation.

## Slide 20: Sector 10 entrance
F07

## Slide 21: Additional slides for reference

## Slide 22: F1.3-06. First cryomodule shipped to SLAC. Arrival 19 Jan 2018

## Slide 23
Some dimensions,
for reference

## Slide 24: Cavity motion which could result from support motion
~774 mm
~476 mm
Ratio of cavity motion
to support bolt lift is
about 1.6. Cavity
motion up at about a
17 degree (0.3 radian)
angle.
Motion in the direction shown would lift the G-10 support block into contact with the coupler.
Cold mass is not
locked down at the
top. Rests here
on vertical
alignment
bolts.

## Slide 25: LCLS-II-4.5-ES-0403, Cold Button Beam Position Monitor

## Slide 26: Project response to cryomodule fasteners issues
  Various reviews provided recommendations which were used to establish conditions for production restart and actions to be taken at the partner labs
    Repair of existing cryomodules including BPM seal bolt replacement
    Resumption of production of new cryomodules
    Study of vibration in transportation– possible adjustments for transportation frame
  A spreadsheet was created listing all fasteners specifies methods for ensuring the quality of each joint. [ED0007530 -- 1.3 GHz Cryomodule Threaded Fasteners]
  Conclusion at the end of this process: “The design is sound. We understand how to fix the beamline vacuum seal issue, tighten and replace loose fasteners, and ensure fastener integrity.”

## Slide 27: The rough ride continued
F1.3-06 returned to Fermilab on April 8
On April 23 we learned that a leak check of the cavity string revealed leaks in addition to the likely BPM seal leaks.
Cracks were found in two bellows
  Inner coupler bellows of cavities 4 and 5
  Subsequent leak checking showed these to be the only leaks other than the BPM bottom flange where bolts had come loose.
  We do not know whether bellows cracking occurred on the first trip (to SLAC) or on the return trip (to Fermilab).

## Slide 28: Eu-XFEL road shock data were similar to ours
From Proceedings of LINAC2014, Geneva, Switzerland
XFEL Cryomodule Transport: From the Assembly Laboratory in CEA-Saclay (France) to the Test Hall in DESY-Hamburg (Germany), by S. Barbanotti, K. Jensch, W. Maschmann, O. Sawlanski, DESY, Hamburg, Germany
“From these results, the damping factor of the new frame looks satisfactory. Nevertheless, values higher than 1.5 g on the inner frame have to be accepted also with the new frame design.” (my emphasis)

## Slide 29: F1.3-05 Shipping Test July 25, 2018, More Results

## Slide 30: Summary for F1.3-05 road tests
F1.3-05 vacuum cavity loss during second road trip, July 25, 2018.
  Total miles to failure ~ 200
  Inner bellows for RF coupler at cavity 1 (inner bellows failed on F1.3-06 for couplers at cavities 4 and 5)
Shipping configuration was that agreed upon following the June 12 Transportation Review
Road shocks occasionally exceed the 1.5 g specification but are similar to those experienced by Eu-XFEL and within our expectations
This short road test was to measure displacements with better instrumentation
  We were not ready to ship to SLAC
  We thought this might be the final configuration for transportation to SLAC
  But some additional data were needed
  Vacuum loss was totally unexpected

## Slide 31: Foam blocks damp thermal shield swinging

## Slide 32: Upstream end post tie-down

## Slide 33: Upstream end post with tie-down removed

## Slide 34: Upstream end post shows normal cool-down slide mark

## Slide 35
SSX-002
SSX-003
Slice 238.2
Slide Courtesy J Holzbauer

## Slide 36: Technical Failure Analysis Logic Path

## Slide 37: Bellows prediction, data, and specification
Note about the blue line specification:
Below 2 mm peak to peak lateral offset, bellows stress is below the fatigue limit for 316L stainless.
We selected a specification which sets the number of cycles at 2 mm peak to peak at no more than 100,000, two orders of magnitude below failure. We set the magnitude of high frequency cycles at 1 mm peak to peak, a factor of two below failure amplitude.

## Slide 38: Alignment requirements
Cavity strings are aligned at the partner labs, and data referenced to vacuum vessel fiducials provide cavity positions with respect to the vacuum vessel. Tunnel alignment sets vacuum vessel position so as to place cavities, quad, and BPM on the beamline. Thus, offsets during shipping result in errors regarding our knowledge of cavity position and should be small, (e.g., tenths of a mm).

## Slide 39: Present status at SLAC
  Five cryomodules are at SLAC
    In Sector 10 entrance and linac tunnel
    Four are linac-ready; one is for practice and will be rebuilt
  F1.3-07 (linac-ready cryomodule) arrived successfully at SLAC from Fermilab in November using the bolt cage solution for RF coupler support.
    Couplers were reassembled by Fermilab personnel in December.
  F1.3-05 (needs eventual rebuild) remains at SLAC for practice handling.
    Traveled over 10,000 miles for various tests without losing cavity vacuum.
    The last test and delivery from Jefferson Lab to SLAC utilized constraints (M-mounts and another design) of fully assembled couplers.
    M-mount is our long-term solution.
  J1.3-04 (linac-ready cryomodule) arrived at SLAC in December using M-mount constraints of fully assembled RF couplers.
  F1.3-04 and J1.3-08 (linac-ready cryomodules) arrived at SLAC in January with our new transportation methods and procedures.
  We have released SLAC Engineering Note LCLSII-4.5-EN-1370-R0, “F1.3-05 Study, Lines of Inquiry Conclusions and Responses”.
    This summarizes the conclusions and project responses to the investigation of the cryomodule transportation issues.
  We now have our cryomodule transportation solutions in place.

## Slide 40: Next
  One trailer and end caps returning from SLAC to Fermilab now.
  The other trailer with end caps departs from SLAC to JLab on Monday.
  Jlab personnel will be here next week for M-mount removal from F05 and J04 and associated training of SLAC personnel.
  F-05 will be moved into CM15 slot (last of L2) where it will be mounted and aligned, followed by HPRF waveguide practice installations, cable dressing, and measurements for terminations.
  F1.3-04 is being prepared for shipping from Fermilab with M-mounts.
  Next cryomodules from Jefferson Lab and Fermilab will arrive at SLAC by late January. (Jan 22 and Jan 28)
  We plan to bring another “practice” cryomodule (one which needs rebuilding) to SLAC, which combined with F05 will enable full practicing of interconnect assembly in the tunnel.
  Fermilab and Jefferson Lab have a total of 7 cryomodules now which are ready to send for linac installation.
    We expect to begin receiving one cryomodule every few weeks starting in February.