## Slide 1: Joint Operation & Readiness meeting
Report Operation / Photon Run Coordinator
Report Dispatch*
Instruments
  FXE
  SPB/SFX
  SCS
  SQS
  MID*
  HED*
Beam transport
  Task force XTD6 installation
  Vacuum
  X-ray optics
  Photon diagnostics
Optical lasers*
Detectors
Electronics
  AE*
  EETF
CAS
ITDM
SRP*
Technical services
AoB

## Slide 2: Report from Dispatch meeting
PSPO is tasked with gathering ALL activities in the XHEXP1 and the XTDs for the upcoming winter shutdown. We need your feedback until the end of October! Our goal is to schedule most if not all works which severely impact the operation of the machine and the experiments / lasers (e.g. by cutting power, cooling, control services etc.) before the 14th of January, in order to allow the experiments to actually do proper commissioning & start-up afterwards.
The milestones of the SASE2 Technical commissioning Task Force headed by CY have been achieved. Starting from this week CY is no longer taking care of the SASE2 tunnel activities planning and coordination. It has to be discussed in the Friday meeting how to go on, since the planning and coordination of the shutdown activities is needed.
  Comment from TT: We have the concept of equipment owners and for the tunnels this concept is challenging, as there are many groups having instrumentation here. For the next shutdown these equipment owners have to plan and execute work (partly helped by support groups). In the longer term we need another solution, but that requires first more discussion.

## Slide 3: HED
DN160 vacuum line (to quickly rough large target chambers with large roughing pump outside the EXP hutch): pipes, routing and wall mounting have been fitted this week, finish by Friday. Installation of final welded arts expected in first week of Nov 2018.
rail covers are finished in rear part of EXP hutch. The aluminum covers can take 2 tons per wheel (fork lift).
works in OPT hutch: safety modification of shutter (Fan), mounting of OPT_CRL bellow.

## Slide 4: Optical Lasers
SASE 1:
PP-laser is in user operation.
SASE 3 and 2:
Control system and PLC are somewhat delayed, but not yet critical.
Otherwise progress as planned.

## Slide 5: AE - 1
SASE3
Deploy of new hardware and interlock configuration for D3/GATT safe operation related issues
Master loop should be restarted next week on Maintenance day
SQS
SQS to MPS communication will be included next week on Maintenance day
New interlocks in different loops have to be updated
SQS loop 13 hardware not connected yet
SQS loop 12 ongoing
CRds taking in count for various loops
SCS
Loop 2 working on Peltiers and signals for EPPs connected
Loop 1 and 9 updated.
SASE3 PPL
PLC project prepared and running. We will wait for parameters from Daniel/Tomasz

## Slide 6: AE - 2
SASE2
Supporting MID with commissioning in the tunnel
MID
Loop 4 will include interlocks next week.
Loop 2 and 5 work ongoing.
SPB
Loop 5 AGIPD ready for deploy with new interlock in motors defined.
Master loop for communication with MPS ready for deploy
FRAMEWORK development main points
AInvertValue removed from SD_digitalInput from version 1.32.0 onwards. And hotfix done in 1.28.3 to include that feature in SASE3 EPS loop.
Homing procedure for Mc2_ devices work ongoing with different setups.

## Slide 7: AE - 3
AE-MicroTCAs
SASE2 Balcony Room
DESY MPS group report that Timing/MPS cards in SASE2 Balcony room where not reachable.
A reboot of MicroTCA in SASE2 Balcony room was schedule with all the affected groups (BKR, MID, HED, XTD, CAS, ITDM).
Problem solved but it was found that the Crate has no backplane FRU info. This does not affect hardware functionality, but a replace should be schedule in the next shutdown.