## Slide 1: Joint Operation & Readiness meeting
Report Operation / Photon Run Coordinator
Report Dispatch/PSPO
Instruments
  FXE
  SPB/SFX
  SCS
  SQS
  MID
  HED
Beam transport
  Vacuum
  X-ray optics
  Photon diagnostics
Optical lasers
Detectors
Electronics
  AE
  EETF
CAS
ITDM
SRP
Technical services
AoB

## Slide 2: PSPO/Readiness Meeting
On 16.01. D.23 will be painted. Scaffolding is needed. Therefore the passage will be closed.
Back

## Slide 3: SQS
Installation of fiber laser in SQS laser hutch starts on Mo, 14.01.
Removal of AQS chamber
  MEA2 for final position of the chamber Tu, 15.01.
  Disconnection of all cables
  Removal of chamber
Installation of REMI chamber
  Arrival at XFEL Thu, 17.01.
  Installation starting Fri, 18.01.
Back

## Slide 4: HED
IC2 delivered, but support frame and rails need to go back to DESY workshop for re work.
Back

## Slide 5: VACUUM
Done:
Removal of SPB CRL from XTD9
Repair of Solid Attenuators (SASE1&2)
Test/repair of FXE monochromators
Cabling of XTD6 monochromators
Installation of viewport on frontend absorbers (8/9)
Improvement of forevacuum system at differential pumps
Assisting XPD with screen exchange on imagers 2/4

## Slide 6: VACUUM
Still pending:
SASE3 M2 installation, connection of MCP (start Monday)
Re-installation of burn-through monitors to instrument shutters MID SPB (Wednesday)
Installation of viewport on XS3 frontend absorber (starts today)
Assisting XPD with screen exchange on imagers 2/4
SASE1&3 vacuum loop updates
SXP installation has started (marking, drilling, installation of pipe supports)
New on the list:
Preparing HED high resolution mono for crystal installation
Installation of additional gauges on XTD2 XGM (next week?)
Issues:
- problems with SASE1 vacuum loop update
- serial communication of GATT mass flow controller not working (anymore)
Back

## Slide 7: XPD
IMAGERS
SCS_XTD10_IMGES : focus of Kowa lens repaired.
SQS_XTD10_IMGES and SA1_XTD2_IMGFEL: YAG scintillator exchanged against an Al coated YAG screen.
SQS2_XTD10_IMGPI : removed, repaired, tested in lab.
KMONO
broken Al filter in SA3_FLT exchanged (& requested to include the filter chambers in EPS)
design (in NX) of modifications of SR-imager for using the new Photonic Science camera and ordering of base parts. Repaired the migrated NX model. The repaired camera should arrive in time, otherwise we need to use the borrowed camera from HED for SASE1 / XTD2.
vacuum pipes for HIREX2 beamline attachment are ordered

## Slide 8: XPD
PAM & TPLM
Analysis of last December’s PAM commissioning data and Cross correlation of PAM and BAM data
TPX window for THz project ordered.
XGM
All XGMs are set to offline (gas and HV is off)
SASE3 XGM loop update
Fresh Kr bottle in XTD10
Power failure at SCS effected also XGM in SCS -> fixed by Martin Teichmann
Venting and installing 2 full range gauges at XTD2-XGM on Monday with VAC (Janni)
PES
in progress: adapting the SA3 PES for two color experiments (modifications on the patch-panel electronic connections and also modifications of the Karabo Macros and scenes)
in progress: automatic data processing from SPdevices digitizers (with CAS and A. de Fanis)
under development: Karabo Macro for automatic changing of target gas
Back

## Slide 9: Detectors – DET
1st AGIPD SPB
  Installation of new cooling pipes for Si-oil ongoing  should be finished next week
  Karabo framework was upgraded  to be tested as soon as the system can be powered up (i.e. after the cooling system is again operational)
LPD at FXE
  None operational super modules removed, testing and debugging will follow in the laboratory test stand.

## Slide 10: Detectors – DET
2nd AGIPD MID
  Detector is disconnected from the sample chamber, the blank flange is installed and test system was under vacuum over the Xmas break
  Vacuum system was restarted after the unexpected power failure
  Detector cannot be operated/tested before the new cooling pipes for Si-oil are installed, leak-tested and isolated  the needed components were ordered, schedule for the installation is not yet fixed
DSSC
  DSSC testing in the HERA South clean tent
    All quadrants installed end of last year. Backside flanges with feedthroughs installed and cables connected. Detector to be closed and pumped on Thursday (today).
    Cable support to be installed on Friday.
    Long cables to be dismounted and given to SCS in KW 4. Spare cable set exists, testing to be done
  Power supply control in Karabo
    Procedure fully tested, needs to be documented and implemented in a Karabo scene.
  DSSC testing and calibration to happen in the next ˜two months.
    Next week: cooler test and possibly connection, connection to power
    Dismounting of cables end of next week / beginning of KW 4 and transport to XFEL
    Preparation of vessel and pulsed X-ray source PulXar
    Ladder prototype in test stand available for tests after installation of the test stand in the clean tent (for connection to X-ray source)

## Slide 11: Detectors – DET
FastCCD
  Cooling: finalizing design of new cold rod
    Made of copper
    Larger outer diameter
    50% denser Cu braids
    To be delivered by the end of January
  Calibration:
    Reviewing old plans to have an 55Fe calibration source at SCS (or possibly a Mini-X X-ray generator)
    Planning calibration with fluorescence during next commissioning period
Back

## Slide 12: AE
Tunnel acitivites:
SASE2 VAC PLC was updated and new interlocks introduced in week 1
SASE3 XMG PLC was updated and new interlocks introduced in week 2
SASE1 VAC PLC was planned to be updated in week 2, but only partially updated and full update postponed for next week - ( new soft devices introduced, interlocks modified and inter-loop communication from FXE to SASE1_VAC PLC will be added) - after this update FXE loop 1 will be also updated!
SASE2 - preparation for commissioning of Si111 monos
SASE2 MOV2 - will be updated this or next week
Instrument activities:
SCS & SQS: change request implementation continued... (mostly changes in beckhoff crate modules)
SFX - first eplan export for PLC firmware received from EETF - PLC project prepared!
Starting commissioning of vacuum components in MID
after power failure we had some smaller issues with bringing all PLC modules into operation - mostly SQS & SCS (one beckhoff terminal in SCS stopped working ...)
Planned for next week (3):
update of the SASE3_VAC, SASE1_EPS & SASE2:XGM...
Back