## Slide 1
Beate Heinemann (DESY and University of Freiburg)
April 16th 2019
Summary and next steps

## Slide 2: Very Short Summary
Beam line designed very advanced already
  First parts of LUXE already exist!
    Magnet reserved
    New fast kicker to be installed this summer
  Could start ordering magnets this autumn!
Theoretical motivation further elaborated
  Several aspects of QED in strong field
  BSM physics also? E.g. axions => need to check if it could be competitive/complementary with other lab-based experiments
Laser systems
  Many challenges to design a “precise” laser
  Two benchmarks for intensity uncertainty:
    25% (Matt: “this can be done for sure”)
    10% (Matt: “less than that is hard”)
Detectors:
  Very wide range of rates for several detectors => first ideas include silicon tracking, cerenkov and calorimeters

## Slide 3: The first parts of LUXE

## Slide 4: Location
Strong preference for location right after LINAC (start of 2nd fan)
  More space
  No interference with SASE4/SASE5
  No photon beam in the way
  No worries about legal process
  Synergetic other activities thinkable (e.g. test beam)

## Slide 5: Location

## Slide 6: Location: Osdorfer Born
Decide: let’s use this location as default for all planning purposes

## Slide 7: Local Support
Directorate of European XFEL very supportive from the start
  Last month the SAC of the EU.XFEL confirmed scientific value to be high
  Sergei emphasized that it is critical that we do not interfere the photon science programme
Directorate of DESY very supportive
  Strategy fund granted 1.5 years ago
  The directorate of DESY has included in its financial planning support for the civil construction (for a volume of up to 3M Euro) for the LUXE experiment, pending successful application of an ERC or other equivalent sources.
  Positive remarks by intl. review committees when presented
  Part of plan for next funding period (POF IV)
Leadership of European XFEL Linac and DESY MD in general also very supportive

## Slide 8: Time scale constraints I
Access to XFEL generally only possible during yearly shutdowns
  Normally about 4 weeks per year
  Plus some shorter (hours- days) a few times per year
  Longer shutdown planned ~2021 (about ~8 weeks)
  SASE4/SASE5 installation starting ~2023
Need to understand how many shutdowns needed for installation
  Beam line elements => could order magnets this autumn
  Laser
  Detector system
Important to prepare installation as much as possible on surface
  Make it ”plug in” and possible to control remotely as much as possible
Need rooms for several parts in Osdorfer Borm
  Initial laser
  Data acquisition, IT, … control room
  Final laser
Maybe find room in existing building => check?
Likely need new building => check if possible
}

## Slide 9: Time scale constraints II
Need to write “letter of intent” this summer (by end of August)
  Basis for evaluation by XFEL.EU committees (MAC and SAC, and then Council)
  Basis for all funding applications => e.g. ERC grant in November
  Should contain
    Physics case
    Required modifications of XFEL.EU accelerator
    Conceptional (and realistic) design of laser and detectors
    Simulation studies showing that this design gets the desired physics (or at least significant part of it)
  This is in four months from now!
This year is last round of current ERC grant scheme => unclear how things will be after this year => apply for synergy grant this year
  Results need to be obtainable within funding period of seven years
  Money will start to flow after summer 2020 (if successful)
  Need to work on alternative funding sources in parallel

## Slide 10: Proposed Time scale: Phase-0
April 2019:
  Decide on location => at end of LINAC
Summer 2019:
  Determine work plan for beam line modifications to understand cost and shutdown compatibilities
August 2019:
  Publish letter of intent
November 2019
  Application for ERC synergy grant for phase-0 “prototype” experiment
  Obtain letter of support by management and council of EU.XFEL
  Order first magnets
Winter 2020 and 2021
  Installation: assume it extends over shutdowns (2021 shutdown may be “longer”)
2022+2023: prototype experiment (stage-0)
  Commissioning, data taking and publication of results

## Slide 11: Draft Time scale: Phase-1
2024:
  Install more powerful laser (need to get money for it before)
2025-2027: Data taking with high-power laser (stage-1)
  Interesting to run at different energies, beam currents,… configurations
  Plan to benefit from requirements of other experiments
  Would like to run as much as possible

## Slide 12: Major points that came up: I
DESY funding statement on civil construction
  See page 7.
  Can also obtain letter if needed from DESY particle physics director for funding proposals
Osdorfer Born location:
  Where can we put initial and final laser there?
  Where can we have control room?
  What are dimensions/space constraints in tunnel?
Simulations
  Why is positron energy spectrum so hard?
  Should also simulate “normal” XFEL parameters: 14 GeV and 1.5e9 electrons/bunch
  Compare between different calculations (Nina, Tony, Andreas)
  What are tails of the beams (photon and electron)
  What wavelength should we use to optimize physics programme?

## Slide 13: Major points that came up: II
Laser
  Need to know the pulse shape and parameters very well
    Large impact on x-axis of “money plot”
  Design of laser control system requires knowledge of tunnel dimensions
  Should aim to have laser capable of delivering ~50% higher power than we need as many losses can (and do) occur
    e.g. could try for 1 PW laser even if don’t need full power
  Should use gaussian laser pulses if we aim for stability
  Want to make design of initial and final laser as similar as possible
Detectors
  Need to do full Geant simulation to study secondary interactions, backgrounds, shielding
  Could also use “off-the-shelf” detectors designed for photon science?
  Increase realism of simulation of detectors and study background rejection

## Slide 14: Conclusions
LUXE Project strongly supported, looks very promising in general
Tight time scale driven by document due in Aug. 2018
  Need to make progress fast!
  Need more meetings to help converge
    Should we increase frequency of meetings to every two weeks?
    Should we have another full-day meeting in the summer (before Aug)?
    Should draft outline and assign responsibilities to chapters
  We will have meeting at 2pm among senior people to discuss resources (human and financial)
Very interesting talks, I learned a lot! Thanks to all the speakers!!

## Slide 15: Final Words
Steven Weinberg (03/2019, interview at APS):
Do you think the problems faced by particle physicists today are different from those that you faced as a young scientist?
I do. It was a different situation 50 years ago. Back then, we had experimental data coming out of our ears, and a lot of it didn’t seem to fit any pattern. The problems seemed formidable, but there were so many ways to go with new theories. It really was a thrilling time to be a physicist.
Nowadays, it’s very hard to think of a challenge that we can get our teeth into. The current puzzles don’t offer theorists many opportunities to propose solutions that can be tested experimentally.
Do you have any advice to offer the next generation?
Winston Churchill had a motto at the beginning of World War II: “Keep buggering on.” In that spirit, I think it’s better to do something than to do nothing. My advice is to try crazy ideas and innovative experiments. Something will come up.
Steven Weinberg,
NP 1979

## Slide 16: Have a good trip home!