## Slide 1: Hardware
Production of spares, delivery: April expected
3 RFFEs at PSI (2 Button and 1 Cavity RFFE) will be get back with spare delivery: April
In general: when a card needs repair, can PSI repair it, procedure: agreed DESY will take transport and non negligible hardware costs
2 Button and 1 Cavity RFFE need repair, will be send to PSI, attention to parts in controlled area (need to be send back to DESY)
PileUp: reason resonances of accelerator cavity at 2.4 GHz, special filter necessary, development of filter at PSI: Feb. 2020, risk when it is not solved in Feb.
Reentrant RFFE redesign 2020+
MBU at 1755m: GPAC not responding, ongoing: next days
Problem fans in one MBU found yesterday: 902m; repair ongoing: check fan remotely, WK will check and contact DESY for implementation
Priority: high, middle, low, ongoing

## Slide 2: Firmware and Software
Power cut can cause that cooling of racks will be established after hours. Therefore high temperature was 2 times observed. Need solution by FW: permanent switch OFF when temperature too high and only switch them ON by experts! Will be worked on after Freeze AGC (June 2020 in summer shutdown)
Implementation of Tuning and Precision Mode: Precision Mode leads to reproduce-able attenuator settings for predefined charge and position range (charge from timing, position from doocs), tuning mode increases gain after N shots and both modes reduce gain immediately when saturated. Will be observed with Freezed AGC and check that this is solved.
Freeze AGC when no bunch expected: according timing info and BPM location will be implemented. Implementation in this shutdown, operation with beam on 13.01.2020.
  Implemented for 1 Cavity BPM MBU in injector in Nov. 2019 and successfully tested
Individual button attenuator setting: Idea: check offset and when true attenuate one channel with external attenuator (DESY) 2020
Improve resolution for position and charge when external 216 MHz is missing maybe not 2020
Internal Save&Restore for Cavity and Reentrant BPM (Summer shutdown 2020)
FW for insitu Button BPMs calibration with onboard pulser: maybe not 2020
Implementation of Direct Memory Access (DMA) in MBU and DAMC02 (25 Hz operation): 2020
Additional: Implementation of attenuator range for cavity BPM when beam near BPM axis like it is realized in PSI
Priority: high, middle, low, ongoing

## Slide 3: Operation
Improvement beam based calibration of attenuators for cavity and buttons: maybe not 2020
Write BPM article (DESY and PSI and CEA Saclay ) , maybe 2020
Priority: high, middle, low, ongoing