## Sheet1
LUXE ECAL | subtopic start | subtopic end
|  |  | January 1 2021 | June 1 2021 | January 1 2022 | June 1 2022 | January 1 2023 | June 1 2023 | Octobre 01 2023 | November 1 2023 | December 31 2023
CDR preparation and review | 1.1 2021 | 2021-06-01 | x
ASIC design | 2021-01-01 | 2021-06-01 | x
application ASIC funding | June 01 2021 | January 01 2022 |  | x
sensor design | January 01 2021 | April 01 2021 | x
application sensor funding | June 01 2021 | January 01 2022 |  | x
Design of HV and read-out PCB | June 01 2021 | January 01 2022 |  | x
Sensor procurement | January 01 2022 | June 01 2022 |  |  | x
Production of HV and read-PCB | January 01 2022 | June 01 2022 |  |  | x
ASIC production | January 01 2022 | June 01 2022 |  |  | x
FE PCB design, production and prototyping | April 01 2022 | January 01 2023 |  |  |  | x
Sensor Quality test | June 01 2022 | January 01 2023 |  |  |  | x
ASIC performance test | June 01 2022 | January 01 2023 |  |  |  | x
Assembly of FE ASICS | January 01 2023 | June 01 2023 |  |  |  |  | x
Sensor assembly, bonding, glue in support | January 1 2023 | June 01 2023 |  |  |  |  | x
Installation of Cables, trigger, DAQ at DESY | June 01 2023 | Octobre 01 2023 | [5 empty] | x
Full system test (test beam) | June 01 2023 | Octobre 01 2023 | [5 empty] | x
Full system Construction and Commissioning | September 1 2023 | November 1 2023 | [6 empty] | x
Transport to DESY and installation | December 1 2023 | December 31 2023 | [7 empty] | x