## planning
|  | 2022 |  |  |  | 2023 | [11 empty] | 2024
tasks | days | 9 | 11 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 6 | 7 | 8 | 9 | 10 | 11 | 12
test beam | bar: 2022 9
decision | bar: 2022 12
sensor production | 180 | bar: 2023 5 to 2023 10
fanout production | 60 | bar: 2023 5 to 2023 6
purchasing | 60 | bar: 2023 5 to 2023 6
tooling | 120 | bar: 2023 5 to 2023 8
test with dedicated probe | 50 open days | bar: 2023 11 to 2024 1
gluing HV+RO | 25 open days | bar: 2023 12 to 2024 2
gluing envelop | 25 open days | bar: 2024 1 to 2024 3
elx test of detectors (noise+cosmic) | 50 open days | bar: 2024 2 to 2024 4
contingency | 30 | bar: 2024 5
transport to DESY | 15
tooliong for gluing W | 60 days | bar: 2023 5 to 2024 1
gluing of the detectors on W | 30 open days | bar: 2024 6 to 2024 7
test of each planes with elx | 30 open days | bar: 2024 6 to 2024 7
installation and test inside the frame | 30 open days | bar: 2024 8
installaton of the frame in LUXE | 5 open days
contingency | 30 | bar: 2024 9

## test beam2020
| week | 2021-06-14 | 2021-06-21 | 2021-06-28 | 2021-07-05 | 2021-07-12 | 2021-07-19 | 2021-07-26 | 2021-08-02 | 2021-08-09 | 2021-08-16 | 2021-08-23 | 2021-08-30 | 2021-09-06 | 2021-09-13 | 2021-09-20 | 2021-09-27 | 2021-10-04 | 2021-10-11 | 2021-10-18 | 2021-10-25 | 2021-11-01
tasks
tungsten production
mechanics design | bar: 2021-06-14 to 2021-07-12
mechanics production | bar: 2021-07-19 to 2021-08-16
mechanics test | bar: 2021-08-30
mechanics delivery | bar: 2021-10-04 to 2021-10-25
sensor test | bar: 2021-06-14 to 2021-06-28
carbon production
kapton production | bar: 2021-06-28 to 2021-07-05
tooling | bar: 2021-07-05 to 2021-07-26
gluing | bar: 2021-08-02 to 2021-08-16
test | bar: 2021-08-30
sensor delivery | bar: 2021-10-18 to 2021-10-25
FPGA firmware | bar: 2021-06-14 to 2021-07-19
DAQ | bar: 2021-07-05 to 2021-08-16
TB | bar: 2021-11-01

## manpower at tau
tasks | skills | FTE | can be student ?
sensor production | physics | 0.25 | no
fanout production | physics | 0.5 | no
purchasing | tech | 0.25 | no
tooling | mechanics | 0.5 | no
test with dedicated probe | tech/physics | 1 | no
gluing HV+RO | tech | 1 | no
gluing envelop | tech | 1 | no
elx test of detectors (noise+cosmic) | tech/physics | 1 | yes
minimum FTE |  | 2

## mannpower at DESY
task | skillls | FTE
gluing of the detectors on W | tech | 1
test of each planes with elx | elx/physics | 1
installation and test inside the frame | tech | 1
installaton of the frame in LUXE | tech/physics/elx
minimum FTE |  | 3