## Tabelle1
LUXE ECAL
| 2021 |  |  |  |  | 2022 | [11 empty] | 2023 | [11 empty] | 2024
| Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March | April | May | June | July | August
Tungsten plate prototype | bar: 2021 Sept. to 2021 Nov.
Tungsten plate quality check | bar: 2021 Nov. to 2022 June
Tungsten plate production | bar: 2022 July to 2022 Dec.
Mechanical frame completion | bar: 2023 Jan. to 2023 April
ASIC design | bar: 2021 Aug. to 2022 June
Application ASIC funding | bar: 2021 Aug. to 2021 Nov.
sensor prototypes | bar: 2021 Aug.
sensor prototype tests | bar: 2021 Aug. to 2021 Oct.
beam test of sensor prototypes | bar: 2021 Oct. to 2021 Dec.; 2022 Sept. to 2022 Nov.
application sensor funding | bar: 2021 Sept. to 2021 Dec.
design HV and fan-out PCB | bar: 2022 Feb. to 2022 June
ASIC production | bar: 2022 July to 2023 June
production of HV and fan-out PCB | bar: 2022 July to 2022 Dec.
FE PCB design, production and test | bar: 2022 Dec. to 2023 April
ASIC performance test | bar: 2023 March to 2023 Sept.
sensor production | bar: 2023 May to 2023 Oct.
sensor quality test | bar: 2023 June to 2023 Oct.
assembly of FE ASICs | bar: 2023 Sept. to 2024 Jan.
plane assembly (bonding, glue) | bar: 2023 Nov. to 2024 March
first tower completed | bar: 2024 Jan. to 2024 Feb.
beam test CERN (FCAL structure) | bar: 2024 Feb.
ECAL assembly and commisiioning | bar: 2024 Feb. to 2024 April
beam test DESY, calibration | bar: 2024 May to 2024 July
installtion in the area | bar: 2024 July to 2024 August