## Slide 1: EURIZON Annual Meeting 2023
WP6 - "Technology development for future high-power laser facilities“
Parallel session summary
Lead beneficiary : CEA
Catalin MIRON, CEA-LIDYL
10 February 2023, Darmstadt, Germany

## Slide 2: WP6 : Transition from CREMLINPlus to EURIZON
Joint technology developments for XCELS
(IAP, CEA, LaserLab-Europe AISBL, ELI-DC AISBL)
Technology development
for future multi-PW laser facilities
(CEA, LaserLab-Europe AISBL, ELI ERIC)
CREMLINPlus (01/02/2020 – 23/02/2022) | Lead beneficiary | EURIZON (24/02/2022 – 31/01/2024) | Lead beneficiary
Task 6.1A – Using relativistic plasma mirrors as ‘light condensers’ | CEA (FR) | Task 6.1 – Intensity enhancement of high-power ultrashort laser beams using optically controlled curved plasma mirrors | CEA (FR)
Task 6.1B - Temporal contrast improvement CafCA - completed | IAP (RU) |  | 
Task 6.1C - Two-stage nonlinear compression of fs laser pulses – only simulations | IAP (RU) |  | 
Task 6.2A – Advanced metrology of ultrashort laser beams (Experiment@IAP) | CEA (FR) | Task 6.2 – Advanced metrology of ultrashort laser beams (SC@SourceLab) | CEA (FR)
Task 6.2A – Non-linear devices for E-field reconstruction – intended for the last 24M | IAP (RU) |  | 
Task 6.3 – Training and scientific exchange involving ELI-DC AISBL (BE) | LLE AISBL (BE) | Task 6.3 – Training and scientific exchange involving ELI ERIC (CZ) | LLE AISBL (BE)

## Slide 3: WP6 : Work progress
Task 6.1 – Intensity enhancement of high-power ultrashort laser beams using optically controlled curved plasma mirrors – completed
Task 6.2 – Advanced metrology of ultrashort laser beams – ongoing (40%)
- SourceLab SME subcontracted in June 2022
- numerical studies, control software & hardware provisioned
- prototype assembly and tests will be finalized by the end of 2023
Task 6.3 – Training and scientific exchange – ongoing (66%)
- 2 out of the 3 knowledge sharing and training sessions organized
- complementary training session to be organized in 2023

## Slide 4: WP6 : EURIZON Deliverables and Milestones
Deliverable / Milestone | Lead beneficiary | Status | Delivery date
D6.1 Training event on beam delivery and propagation at extreme intensities (M15) | LLE AISBL | Postponed to M30 by amendment due to COVID-19 travel restrictions | 10.08.2022
D6.3 Training event on pulse metrology, techniques and challenges (M28) | LLE AISBL | Postponed to M34 by amendment due to COVID-19 travel restrictions | 25.11.2022
MS32 Workshop : improving spatio-temporal metrology of high- power fs lasers (M36) | CEA | Workshop held on 12/05/2022 | 04.02.2023
D6.4 Conceptual design towards extreme intensities using plasma mirrors (M36) | CEA | Delivered | 04.02.2023
D6.6 Training event on pulse metrology, techniques and challenges (M42) | LLE AISBL | Pending | -
D6.8 Prototype for spatio-temporal metrology of high-power fs lasers (M48) | CEA | Pending | -
The activities have been refocused to benefit the whole European high-power laser community