## Slide 1: XFEL Accelerator R&D Status / Final Report RP-211: CW Accelerator Modules
Hans Weise / Detlef Reschke
03.05.2023

## Slide 2: Scope of the R&D activity
Improve XFEL standard cavities for lower cryogenic losses (as needed for HDC and/or cw operation)
  Study cavity end groups
  Understand / improve Niobium surface treatment incl. UHV furnace baking
  Discuss Niobium specs.
  Build and test single and multi-cell cavities
Operate spare XFEL modules in cw or long pulse mode
Discuss LCLS-II lessons learned wrt. cryogenic module design
All activities interface with
  OP-220 which includes maintaining SRF knowledge (sustainability of technology)
  RP-212 SRF Gun, due to common resources and knowledge
  DESY ARD activities in subtopics ST1 and ST4
  DESY technology held by many groups (MSL, MKS, MVS, MSK, MHF, …)

## Slide 3: Promised deliverables
Cavity end group design; verification of electromagnetic design of end-groups & investigate 3-D printing of HOM coupler antennas
Nitrogen infusion of cavities; study, use/adopt the new recipe
Large grain Niobium; reduced total grain boundary length looks attractive wrt. to reducing cryo losses; but LG Nb is challenging (PED)
RF power coupler; better thermal conductivity / cooling by increased Cu thickness; test and operate cw
RF coupler test stand; set-up new conditioning and test stand; become independant of external partners
Accelerator module; understand / digest LCLS-II modifications; what do we need for an E-XFEL HDC or cw upgrade?
3.9 GHz module; OP230 activity; RF test of spare 3.9 GHz module (pulsed and cw)

## Slide 4: Achievements in the past year(s)
Cavity end group design
The work on cavity end group design was discontinued after the end of the DESY – HERAEUS cooperation in May 2021. No new industrial partner was found regarding 3D printing of Niobium. The development is still of interest but now has low priority. There is no risk for the sustainability of the overall SRF technology, and here for the cavity end group. Replacement of seamless end tubes is under study.
Large grain Niobium
In parallel to the study of standard fine grain Niobium cavities we are still investigating large grain material. Sheets from three different suppliers were procured and tensile tests (cold and warm), hardness and RRR measurements were performed considering the orientation of grain boundaries. Emphasis was on the weld connection between half-cell and stiffening ring.
Evaluation and discussion with TÜV experts unfortunately didn’t come to an end.
So far, we are not ready to seriously consider the procurement of large grain material for a complete batch of cavities.

## Slide 5: Achievements in the past year(s)
Nitrogen infusion and other treatment (mid-T bake) of cavities
During the last years, DESY studied and tried to reproduce existing N-infusion recipes but also to investigate in detail the so-called mid-T heating process.
      The goal is to improve the cavities’ Q-factor i.e. reduce the cryogenic losses at the envisaged cw or long pulse / high duty cycle acceleration gradients.
      The infusion as well as the mid-T heating process requires dedicated vacuum furnaces.
      Meanwhile the quite fundamental refurbishment of the ultra-high vacuum furnace with it’s all Niobium chamber shows clear success.
      As of today, a group of single cell cavities was treated successfully, and the overall process is stable enough to concentrate on a larger series with well-defined parameter variations, e.g. temperature gradients.
      The actual goal is a first 9-cell cavity heating (mid-T) in Q4/2023.
      We are going to procure a set of ten 9-cell cavities (OP-220) and study its performance depending on treatment parameters (OP-211).

## Slide 6: Achievements in the past year(s)
RF power coupler LLRF testing of XM46.1
Done. We are quite happy with the thicker Cu plating. The thermal connection at the cold window needs further studies connected with the module design improvements.
RF coupler test stand
Commissioned and in operation.
Accelerator module
Cryogenic design modifications will be done based on LCSL-II lessons learned, on simulations, and on measurements. The spare (scavenger) module XM99 will be used to study heat flow, the necessity of the
5 K shield, and the detailed design of the 2K 2-phase line together with the cavity’s He-vessel.

## Slide 7: Deviations from plan
Commissioning of the refurbished UHV furnace took longer; thus experiments came later
  The overall effort was larger since we aimed for an optimum / perfect performance
  Attempts to also use the ZM UHV furnace failed (carbo-hydride contamination)
LG material causes real challenges regarding Pressure Equipment Directives
  Even if the principle ideas is tempting, we may have to give up.
HOM antenna 3-D printing
  We lost our industrial partner
Cavity heating
  We have the two principal recipes N-infusion and mid-T heating
  Decision can be made after getting more statistics
  10 more fine-grain single-cells in production; 10 nine-cell cavities will follow
  Some large grain single-cell also.

## Slide 8: Timeline of this R&D activity
Proposed Date | Milestone Description | Updated Date
 | Large grain Niobium | 
Q4/2022 | Investigation of mechanical properties incl. welding studies | still ongoing
Q1/2023 | Finish modified Nb material specifications wrt. Pressure Equipment Directives | still ongoing
Q2/2023 | Order LG material for 6 cavities | Q3/2023 ???
 | Nitrogen infusion of cavities / mid-T heating | 
Q3/2021 | Establish stable N-infusion recipe | first success
Q4/2021 | Establish stable N-infusion at cavity vendor | open
 | RF coupler test stand | 
Q2/2022 | Start regular operation | finished
 | Accelerator module | 
2024 | Finish cryogenic design | 2024
2025 | Finish TDR European XFEL CW accelerator module | 2025

## Slide 9: Risks to R&D Project
schedule
  All activities rely on sufficient resources
  Personal ‚affiliation‘ is shared between XFEL and DESY; therefore renewal is challenging
  Success cannot be guaranteed in all areas; some scientific and technological risk

## Slide 10: Outlook / Summary
More N-infusion and mid-T heating treatments to find optimum parameters
Start procurement of 9-cell cavities (OP-220 & OP-211) (incl. PED related issues)
Joined accelerator module activities (incl. Coupler therm.connection & He-vessel design)
Risk of too high expectations (own & others) creating overload
Activities need to lead over into a follow-up proposal
  We can stop only after defining / building a pre-series cw accelerator module
Several LINAC2022 and SRF2023 conference papers; others if time allows…