## Slide 1: XFEL Accelerator R&D Final Report Intra-Bunch Train Longitudinal Feedback (IBTLF  L-IBFB)
Marie Kristin Czwalinna
03.05.2023
PIs : H.Schlarb, B.Lautenschlager

## Slide 2: Scope of the R&D activity
Goal of scientific work Achieve ≤10 fs rms arrival time and ≤ 2% rms peak current stability at BC2
interfaces with other operation activities
  OP-215 LLRF systems,
  OP-325 optical synchronization,
  OP-365 special diagnostics,
  OP-430 feedbacks
  valuable exchange and large progress stability task force activities (2021-2022),
    XPD, LAS, FXE, SPB, SQS/SCS, ..
(2021)

## Slide 3: Achievements of the entire R&D project (1)
recruitment of Post-Docs
  (2018) control theory,
  (2019) firmware development
(2020…2021) Implementation & tests of L-IBFB
adapted to cope with changed requirements
  beam regions concept, Q3/2022
Independent
arrival time monitoring,

## Slide 4: Achievements of the entire R&D project (2)
New feedback structure L-IBFB in operation at EuXFEL (2022)
  main goal reached
After adaptation of intra-train feedback, → bunch timing jitter < 6fs rms
@250pC bunch charge
L-IBFB off
L-IBFB on

## Slide 5: Achievements of the entire R&D project (3)
Concept for global feedback architecture,
  Inter-operability,
  Robustness,
  Connect several architectural layers
    Operator interface
    High-level layer
    Middle layer
    Frontend servers
    Firmware/hardware
  Work in progress,
  (2022) started implementation & tests

## Slide 6: Deviations from plan
Implementation of fast arrival time feedback on photo-injector laser
  in this form not necessary  slow feedback
Establish new feedback architecture  global feedback manager
  High complexity
  Effort in time and software development
    Requires continuation
Direct (low-latency) intercommunication in between RF stations for L-IBFB
  Re-evaluate if / how feasible.

## Slide 7: Timeline of this R&D activity
Proposed Date | Milestone Description | Updated Date
Q3/2018 | Hire control system expert (Postdoc) | Q4/2018
Q3/2019 | Hire firmware expert (Postdoc) | Q3/2019
… | … | 
Q3/2021 | Implementation of fast arrival time feedback on photo-injector laser (if the laser permits) | skipped
Q3/2021 | Establish new feedback architecture interlinking L-IBFB with slow L-FB | work in progress
Q2/2022 | New feedback (L-IBFB) structure implemented and in operation at EuXFEL | Q4/2022

## Slide 8: Risks to R&D Project
risks associated with our R&D project
  Observation of unexpected effects,
  Underestimation of complexity

## Slide 9: Outlook / Summary (1)
achievements of the entire R&D project
  ≤10 fs rms electron bunch arrival time stability
    @250pC and @100pC
    Residual jitter and drift contributions under investigation
  provided procedure for operators to setup the L-IBFB
  agreed with MXL  L-IBFB in standard operation
PAM
BAM
= 12.4fs
Difference signal (fs)
BAM – PAM
Intra-pulse train correlation,
with timing slope
photon pulse vs. electron bunch
(during low charge operation, @100pC)

## Slide 10: Outlook / Summary (2)
follow-up activities
  continuation of activities within OP-365
  RnD projects on-going
    to predict & correct effect from ground motions
    Drift contribution : Tidal waves (+/- 300fs over 12 hour period)
    Significant contribution : Ocean waves
    At ca. 0.2Hz (~3fs rms over seconds)

## Slide 11: Outlook / Summary (3)
List of related publications
  conference
    IPAC 2021 Invited Talk: Beam arrival stability at European XFEL, M.K. Czwalinna et al, JACoW-IPAC2021-THXB02
    FEL 2022 Poster: Achievements And Challenges For Sub-10 fs Long-Term Arrival Time Stability At Large-Scale SASE FEL Facilities, B. Lautenschlager et al
  peer-reviewed
    Optica Vol. 9 Issue 4 pp. 429-430 (2022), D. Rivas, M.Meyer, et al., High-temporal-resolution X-ray spectroscopy with free-electron and optical lasers, doi.org/10.1364/OPTICA.454920
    Joint paper DESY/EuXFEL in preparation (2023)