## Slide 1: XFEL Accelerator R&D Status Report Fault Diagnosis for the LLRF control system
Julien Branlard
With Lynda Boukela, Nur Zulaika Jumhari and Annika Eichler
May 3, 2023

## Slide 2: Scope of the R&D activity
Chart: Quenches proportion in 2022
| Quenches | Other Trips
 | 90 | 303
Trips and Quenches
  Significant downtime
  System degradation
  Energy and financial costs
Fault diagnosis
  Reliability study
  Significant impact
  Opportunity for enhancement
Notes: give a short summary of what your project is about
if you have any interfaces with other XFEL R&D or operation activities both on the accelerator and/or photon system side, mention them here
if you promised any deliverables, list them here

## Slide 3: Scope of the R&D activity
Chart: Quenches proportion in 2022
| Quenches | Other Trips
 | 90 | 303
Scientific work
  Online operation
  ML-based algorithm for quench detection
  Fault prevention & system recovery
  Communication and reporting
  Resources management
Trips and Quenches
  Significant downtime
  System degradation
  Energy and financial costs
Fault diagnosis
  Reliability study
  Significant impact
  Opportunity for enhancement
Fault Diagnosis
AI
Online
Recovery
Rep
Notes: give a short summary of what your project is about
if you have any interfaces with other XFEL R&D or operation activities both on the accelerator and/or photon system side, mention them here
if you promised any deliverables, list them here

## Slide 4: Timeline of this R&D activity
Proposed Date | Milestone Description | Updated Date
Q1/2022 | Module integration of signal calibration (PostDoc) | Q4/2023
Q3/2022 | Online implementation of the trip event logger (PostDoc) | Q2/2023
Q4/2022 | Scalability analysis of online implementation (PostDoc) —> changed to: In-depth offline analysis | 
Q4/2022 | Online analysis of the cavity module (PostDoc) | Q3/2023
Q4/2022 | Hire phd student —> changed to: Hire PostDoc | 
Q3/2023 | Scalable solution of the infrastructure (PostDoc) | 
Q4/2023 | Fault detection and isolation algorithms developed for further subsystems (PhD) | 
Q3/2024 | Infrastructure updates for feedback to allow system recovery and fault prevention (PostDoc) | 
Q4/2024 | Algorithms developed for recovery and/or fault prevention (PhD) | 
Q2/2025 | Analysis of the overall system with regard to all modules and capabilities (PostDoc + PhD) | 

## Slide 5: Achievements in the past year
Planned Achievements
Purchase servers and Ethernet switch
Hiring a software expert
Hiring a PhD
Deliverables
Resource
Online implementation of the TEL
Online analysis of the cavity mod…
Integration of a signal calibration module
Scalability analysis of online TEL
Notes: this matches your summary in the written report
depending on the amount of presentation time assigned to your report, you can use up to 3 slides on this topic
if this is your final report, give the achievements of the entire R&D project
  Hire a software expert
  Online implementation of the previously developed trip event logger
  Integration for other modules like signal calibration.

## Slide 6: Achievements in the past year
Deviations from plan
  Visa problem and hiring process difficulties
  Delays occurred in the project between May and November 2022, absence of the PI due to maternity and sick leave.
Achievements
  Two postdocs were hired
    Nur Zulaika Jumhari, software expert, June 2022
    Lynda Boukela, ML and fault detection, October 2022
  Familiarization of the new staff
  In-depth offline analyses
  Online prototype implementation
  Data storage, Ethernet switch, servers
  Publications
X
Online implementation of the TEL
Online analysis of the cavity module
Integration of a signal calibration module
Scalability analysis of online TEL
X
In-depth offline analysis
Purchase servers and Ethernet switch
Hiring Postdoc (Machine Learning)
Hiring a PhD
X
Hiring a Postdoc (software)
Maternity and sick leave of the PI
Delays
Deliverables
Resources
Notes: this matches your summary in the written report
depending on the amount of presentation time assigned to your report, you can use up to 3 slides on this topic
if this is your final report, give the achievements of the entire R&D project
  Hire a software expert
  Online implementation of the previously developed trip event logger
  Integration for other modules like signal calibration.

## Slide 7: Achievements in the past year
Notes: this matches your summary in the written report
depending on the amount of presentation time assigned to your report, you can use up to 3 slides on this topic
if this is your final report, give the achievements of the entire R&D project

## Slide 8: Achievements in the past year
TP : true positive (accurately detected a quench)
TN : true negative (accurately recognized a trip was not a quench)
FP : false positive (a “fake” quench)
FN : false negative (algorithm failed to identify a real quench)
Improved Detection
Samples
GLR
Beam information inclusion
Notes: this matches your summary in the written report
depending on the amount of presentation time assigned to your report, you can use up to 3 slides on this topic
if this is your final report, give the achievements of the entire R&D project

## Slide 9: Achievements in the past year
Notes: this matches your summary in the written report
depending on the amount of presentation time assigned to your report, you can use up to 3 slides on this topic
if this is your final report, give the achievements of the entire R&D project

## Slide 10: Risks to R&D Project
Online analysis needs new hardware in the tunnel (is already bought)
  Test phase with A24 (installation in summer shutdown)
  Goal is seamless integration with existing LLRF systems
  Therefore, as many offline tests as possible (+ staged approach)

## Slide 11: Outlook / Summary
Publications
  [1] J. Branlard, A. Eichler, J. Timm and N Walker, “Machine Learning Assisted Cavity Quench Identification at the European XFEL“, LINAC2022, Liverpool, UK, 2022, doi:10.18429/JACoW-LINAC2022-THPOPA26
  [2] A. Eichler, J. Branlard, and J. H. K. Timm, „Anomaly detection at the European X-ray Free Electron Laser using a parity-space-based method“, Physical Review Accelerator and Beams, vol. 26, no. 1, pp. 012801, 2023, doi:10.1103/PhysRevAccelBeams.26.012801
Online testing
Signal calibration
Scalability
Notes: describe the planned activities for the this year
are there any risk that may challenge this plans
if this is your final report, summarize the achievements of the entire R&D project
  give list of deliverable
  give a short summary of its planned content
do you plan a follow-up proposal
give a short summary of its planned content for the follow-up