## Slide 1: XFEL Accelerator R&D Proposal STERN
Francois Lemery
27.6.2023

## Slide 2: Scope of the R&D Activity
STERN will investigate high power THz radiation generation via wakefields generated in Cherenkov waveguides by the to meet user demands (0.1 – 30 THz).
To eventually meet user delivery, STERN will require establishing a handle on radiation generation, characterization, transportation and synchronization.
  We now need to especially produce and characterize structures via atomic-layer deposition and electro-optic sampling techniques.
The next 3 year segment of STERN aims to establish an experimental area at XS4 to produce first THz and to expand the program to include the development of high-power THz diagnostics to enable fs bunch measurements, along with investigations in beam conditioning.
There is strong synergy between the radiation and laser-driven approaches, both relying on similar waveguides and frequencies.
The inclusion of a laser also enables THz characterization and preliminary investigations on THz transport with XFEL (photon side) which are binding for success.

## Slide 3: Summary of initial exploratory STERN phase
Developed elegant optics simulation to confirm small symmetric beta functions of 1 m could be achieved which also abide by beam dump conditions.
Developed a new waveguide concept to generate high-frequency THz fields from the e-beam.
Worked out theory in detail, with collaborative papers with Armenian colleagues
Developed first phase velocity characterized 3D printed waveguides
Motivated investigation and development of new code with I. Zagorodnov to account for anomalous skin effect in cooled waveguides to reduce losses.
Developed THz source to characterize 3D printed and ALD-based waveguides.

## Slide 4: Deliverable of the R&D Proposal and it‘s benefit for the XFEL
The final deliverable of this (intermediate) proposal is the development of an experimental area to produce and characterize THz, as well as the development and characterization of the structures with laser-based approaches.
  In addition we will develop THz and laser-based diagnostics and manipulation techniques to enable e.g. high temporal resolutions
  Investigate transverse energy correlations to support conditioning.
  First design and tests of a THz transport line based on laser-based THz radiation.
  THz amplifier – amplify injected laser-based THz with e-beam.
The three year segment should enable first experimental results to be achieved assuming no major delays occur in the installation timeline.
The benefit of a THz source is in high demands for user operation.
  Further, the inclusion of a laser in this extension will support initial THz transport tests with XFEL-photon side, along with R&D on novel laser-based diagnostics which could enable improved machine operation.

## Slide 5: Timeline of this R&D Activity
General milestones for STERN experimental area development, structure dev and characterization
Includes simulation, site planning etc.
Milestone Description | Target MTH / QTR
Optics / lattice design completion | Q4/2023
Vacuum design completion | Q2/2024
Preliminary structure characterization complete | Q1/2025
THz Generation and Transport | Q4/2025

## Slide 6: Personnel Resource Needs of the R&D Project
Give an overview about the personnel resource needed for this activity
  list skill needed or task description
  from when to when this personnel is needed?
  indicate if new hires are needed or if available personnel is participating
    PhD student, postdoc, scientist or Engineer
Skill or Task Description | FTE | from | to
Wakefield simulations and experimental area preparation (PhD) | 1 | Q3/23 | Q3/26
Structure fabrication and characterization (PhD) | 1 | Q4/23 | Q4/26
Area design and beamline transport development (postdoc) | 1 | Q3/24 | Q3/26

## Slide 7: Expenditure
List individual items 50 k€ and above (if any)
indicate when the purchase in planned, quarter would be nice, year is necessary
Items to be purchased / Task Name | When | Cost/k€
Synchronization system for laser (Schulz) | Q4/2024 | 100
Laser amplifier | Q4/2024 | 550
Sync-ready Oscillator | Q4/2024 | 110

## Slide 8: Resource and Cost Profile of Proposal
Give here to total investments and FTEs per year
  Invest + Recurrent cost can be different from slide 6, if smaller (<50 k€) expenditurs are expected
for the sake of this table, assume 100 k€ / FTE for full FTE, 2/3 for a PostDoc, 1/2 PhD student (values include overhead)
Year | FTE | FTE Cost / k€ | Invest + Recurrent / k€ | Total Cost / k€
2023/H2 | 2 | 52.9 |  | 52.9
2024 | 3 | 150.5 | 760 | 910.5
2025 | 3 | 195.2 |  | 195.2
2026/H1 | 3 | 150 |  | 150
Total cost of this activity |  |  |  | 1308.6