## Slide 1: XFEL Accelerator R&D Proposal: High intensity two-color pulses from twin bunches: conceptual design
Weilun Qin
27.06.2023

## Slide 2: Scope of the R&D Activity
This project aims at generating high-intensity (mJ level) two-color x-ray pulses using a twin-bunch method.
Twin laser pulses at the injector produce twin electron bunches ==> % level energy difference and fs level delay ==> both e-beam use the full undulator length and thus intensity could be high
This one year proposal is the simulation phase of this project, we aim to answer two important questions:
  How are the two bunches coupled in energy and delay in our 3-stage compression system?
  What FEL performance can be achieved vis this scheme?
This scheme can be connected/combined with other FEL R&D activities
  femtosecond to sub-femtosecond pulses
  multi-bunch with N*0.77 ns (separate bucket, more or less standard dynamics)

## Slide 3: Deliverable of the R&D Proposal and it‘s benefit for the XFEL
This proposal will deliver a conceptual report for generating mJ level two-color x-ray pulses at the European XFEL
  machine working point found by beam dynamics model
  FEL pulse performance at various photon energy found by FEL simulation
  Consideration for experiments
An extension proposal will be needed to continue with the experiment phase of this project.
Benefit for the XFEL
  The project can provide very high intensity two color pulses, which is crucial for photon hungry users ( warm dense matter, x-ray-induced Coulomb exlplosion etc)
  The project can provide two-color pulses at very high photon energy (20keV and up) that are not possible with split undulator scheme, enabling new reseach for the users
  The arc system before the undulator system at XFEL can provide extra tunability for delay controls that are not demonstrated at other facilities.

## Slide 4: Timeline of this R&D Activity
Milestone Description | Target MTH / QTR
Personnel is hired | Q4/2023
Injector simulation with twin bunches completed (gun phase, emittance compensation) | Q1/2024
Linac simulation with twin bunches completed (wakefield, compression, arc tunability) | Q2/2024
FEL simulation and experiment design finished (various photon energy, diagnostic) | Q3/2024
As a start-to-end simulation proposal, the milestones are defined by completing simulation at different parts of the machine

## Slide 5: Personnel Resource Needs of the R&D Project
We prefer to have one (visiting) PhD student who knows start-to-end simulations to complete the simulation task
  DESY beam dynamics, FEL and operation experts will involved in discussions/meetings/plannings
Skill or Task Description | FTE | from | to
new: start-to-end simulations (injector, linac, FEL simulations) | 1/2 | Q4/2023 | Q3/2024

## Slide 6: Resource and Cost Profile of Proposal
One (visiting) PhD for the simulations
  with some traveling budget (5k) for conferences (IPAC or FEL conference).
Year | FTE | FTE Cost / k€ | Invest + Recurrent / k€ | Total Cost / k€
2023-2024 | 1/2 | 50 | 5 | 55
Total cost of this activity: 55 k€ |  |  |  | 
Cost per FTE incl. FTE Overhead 100 k€/FTE

## Slide 7: Summary
We aim to delivery the conceptual design report for high-intensity two color FEL pulses with detailed start-to-end simulations in one year. The output will be evaluated afterwards and plans for experiment will be made.
This proposal will
  push the intensity limit of two-color pulses at XFEL
  push the photon energy limit of two-color pulses at XFEL
  stimulate other accelerator and FEL R&D activities which uses such twin-bunch modes.
Required resources for this proposal is purely personnel. The task is suitable for a (visiting) PhD student.