## Slide 1: XFEL Accelerator R&D Proposal CW Accelerator Cavities & Modules RP211new
Hans Weise / Detlef Reschke / Serena Barbanotti
31.10.2023

## Slide 2: Scope of the R&D Activity
The development of the E-XFEL CW module started already in the frame of RP-211 activities which are coming to an end around end of 2023.
During the next years additional R&D is required, and a number of issues are to be addressed in order to become ready for take-off in the year 2030+.
This proposal describes the planned work, emphasizes the remaining work referring to the RP-211 status, and avoids doubling with the operation package OP-220 which includes all activities towards sustaining the E-XFEL SRF technology.
Activities are:
  SRF Cavities – Niobium material, seamless tubes, end-group design, cavity string assembly, Helium vessel, frequency tuner, magnetic shielding
  RF Power Coupler
  (Quadrupole Absorber, Beamline Absorber)
  Cryogenic aspects of the Accelerator Module
  Single cavity – horizontal test stand
  PhD Support for cavity measurement systems & cavity R&D

## Slide 3: Deliverable of the R&D Proposal and it‘s benefit for the XFEL
The final deliverable of this proposal is a first preliminary design of an E-XFEL HDC/CW optimized cryomodule before end of 2026.
OP220 addresses milestones in 2024 til 2026
  Q1/2024 Finish and implement update of the SRF cavity specification
  Q1/2024 Seamless tubes used for cavity production
  Q2/2024 Order ten state-of-the-art cavities based on new specification
  12/2026 Verify technology sustainability of quadrupole package & beamline absorber
In 2025/2026 accelerator module XM99 should get a new cavity string to support the preliminary E-XFEL HDC/CW optimized cryomodule design
Decision about the need for a single cavity horizontal test-stand in 2025
PhD Support for cavity measurement systems & cavity R&D is urgently required; detailed program depends on availability of students and supervisors & technical support

## Slide 4: Timeline of this R&D Activity
Milestone Description | Target MTH / QTR
Finish the implementation of mechanically modified coupler tuners | 12/2024
Finish initial RF testing of the new cavities | Q3/2025
Define cavity string assembly procedure under vacuum | Q4/2025
Verification thermal connections of all ports (RF power coupler, HOM coupler), Helium vessel, frequency tuner | 12/2025
Preliminary design of E-XFEL HDC/CW optimized cryomodule | 12/2026
PhD Support for cavity measurement systems & cavity R&D correlation of furnace treatment and surface analysis of SRF cavities magnetic hygiene impacting the performance of mid-T baked cavities Impact of cool-down velocity on cavity performance (exact milestones depend on the availability of PhD students) | 2024/2025

## Slide 5: Personnel Resource Needs of the R&D Project
Skill or Task Description | FTE | from | to
new: (100% RP211) PhD Student PhD Student Eng/Techn | 1 1 1 | 2024 2025 2024 | 2026 2027 2026
available: Scientist/Eng/Tech Scientist/Eng/Tech (‘vacant’ OP220 & RP211) | 4,75 (1,35/1,5/1,9) 2,25 | 2024 2024 | 2026 2026

## Slide 6: Expenditure
Items to be purchased / Task Name | When | Cost/k€
Remark: activities are aligned with and co-funded through XFEL OP-220, OP-530 |  | 
8 x MG single cells (fabrication incl. Electro Polishing) (related Nb <50k€) | 2024 | 275
Medium Grain Niobium Sheets (tbd, see above) | 2025 | 175
Niobium parts for MG cavity end groups (tbd) | 2025 | 75
External study to investigate HDC cryogenic operation (2nd cold box) | 2024 2025 | 50 100

## Slide 7: Resource and Cost Profile of Proposal
Year | FTE | Invest + Recurrent / k€ | Comment
2024 | 7 *) | 300 | requires ramp-up by 2 FTE (1 PhD student, 1 Eng/Techn)
2025 | 8 *) | 275 | further ramp-up by 1 PhD
2026 | 8 *) | 300 | 
*) Remark: the currently shared ‘vacant’ personnel is not included here 2nd Remark: small invest not included here; expected as part of OP220 |  |  | 

## Slide 8: Summary
see above…