## Slide 1: XFEL Accelerator R&D Proposal LLRF system preparation for continuous wave operation of the European XFEL
Julien Branlard
15.12.2023

## Slide 2: Scope of the R&D Activity
Perform the R&D necessary to adapt the LLRF system to continuous wave operation in preparation of a possible upgrade of the European XFEL
In particular, this project interfaces with
  High power RF solutions (type of sources, waveguide QL tuner, operation efficiency, power budget, ...)
  SRF cryomodules and cryogenics (couplers, microphonics control, heat load, …)
  Operations and beam-based feedbacks (timing, controls, cavity bandwidth and tuning, beam manipulation…)
  Other XFEL R&D proposals
    Improved diagnostics using machine learning
    TS4i : LLRF development for SRF gun

## Slide 3: Deliverable of the R&D Proposal and its benefit for the XFEL
What is the final deliverable with completion of this R&D activity?
  LLRF CDR for the XFEL continuous wave / high duty cycle upgrade
  LLRF system prototype for an SRF injector / TS4i
Is the deliverable of the proposal already beneficial for the XFEL or is an extension proposal needed after the initial funding?
  This proposal already constitutes an extension
  The 3-year scope of this proposal (2024 - 2027) should cover the CDR delivery time.
Clearly outline the benefit of this proposal for the XFEL in particular for the accelerator
  The LLRF system requires substantial modification for the upgrade
  The R&D required for this upgrade requires resources beyond normal operation (personnel, skill set, invest)
  Due to its interfaces with many other subsystems, a CW-optimized LLRF system would benefit the overall accelerator operation, flexibility, efficiency, availability and cost

## Slide 4: Timeline of this R&D Activity
Outline the major development steps within the timeframe of the proposal
  CW control of the cavity field and resonant frequency in narrow bandwidth (high QL)
  Third harmonic CW operations
  Modernization of LLRF system and performance improvement
  LLRF system for CW injector (TS4i)
  Documentation and CDR
Define milestones that allow tracking of the progress
Milestone Description | Target MTH / QTR
M2024.3 algorithms for cavity parameter estimation (bandwidth, tuning) developed | Q4.2024
M2025.1 cavity resonance control tested at CMTB | Q1.2025
M2025.2 next generation digitizer prototypes produced | Q3.2025
M2026.1 LLRF system for TS4i installed | Q2.2026
M2026.2 LLRF CDR first draft completed | Q4.2026

## Slide 5: Personnel Resource Needs of the R&D Project
Give an overview about the personnel resource needed for this activity
  list skill needed or task description
  from when to when this personnel is needed?
  indicate if new hires are needed or if available personnel is participating
    PhD student, postdoc, scientist or Engineer
Skill or Task Description | FTE | from | to
New: postdoc (diagnostics, machine learning, LLRF) | 1 | 1.2024 | 1.2027
New: PhD student (control techniques) | 0.6 | 1.2024 | 1.2027
New: 1-2 Master student(s) |  | 1.2024 | 1.2027
Available: postdoc (LLRF expert, CW expert) | 1 | 1.2024 | 1.2027
Available: FW / SW Engineer (implementation support) | 0.2 | 1.2024 | 1.2027
TOTAL | 2.8 |  | 

## Slide 6: Expenditure
List individual items 50 k€ and above (if any)
indicate when the purchase in planned, quarter would be nice, year is necessary
Items to be purchased / Task Name | When | Cost/k€
Selected components for evaluation (new generation ADCs, piezo drive, FPGA controller boards) | Q1.2024 – Q4.2025 | 100 – 150k€
LLRF demonstrator for a single cavity CW drive with SSA control | Q3.2025 | 50 k€
LLRF demonstrator for a complete RF station with SSA or with IOT | Q3.2026 | 150 k€

## Slide 7: Resource and Cost Profile of Proposal
Give here to total investments and FTEs per year
  Invest + Recurrent cost can be different from slide 6, if smaller (<50 k€) expenditures are expected
Year | FTE | Invest + Recurrent / k€ | Comment
2024 | 2.8 | invest 100 k€ | prototyping
2025 | 2.8 | invest 100 k€ | small production quantity
2026 | 2.8 | invest 150 k€ | LLRF system demonstrator

## Slide 8: Summary
Emphasize the collaborative aspect of this proposal
  Many tests planned in collaboration with other M-groups at DESY
    Collaboration with MHF (SSA, waveguide tuner, IOT, etc…)
    Collaboration with MKS (heat load tests at XFEL / CMTB / AMTF etc…)
    Collaboration with MXL (HDC Jork workshops)
  Collaboration with industrial partners
    Cryoelectra : SSA efficiency control
    Struck System : new ADC production
    MTCA community  benefits for other MTCA users
  Collaboration with other Helmholtz institutes
    Test of algorithms / software / firmware / hardware
    ELBE (HZDR), HobiCat/BESSY (HZB)
  Synergies with R&D financed by third party grants
    iSAS : initiative for sustainable accelerator systems