## Slide 1: ARES Operation Meeting
Summary of week 07 / 2024
Max Kellermeier, on behalf of the ARES crew

## Slide 2: Summary of week 07
Mon. 12th Feb | Tue. 13th Feb | Wed. 14th Feb | Thu. 15th Feb | Fri. 16th Feb
MVS: installation of new Baseplate assembly MKK3: preparations for ventilation system (removal of yellow fence) MEA2: laser interlock panel checked MKK2: replacement of water valves/filters at RF stations | MVS: de-assembly of clean room tent MEA: EA laser table put back in place Hexapod movements thoroughly tested Re-cabling of EA chamber diagnostic | MVS: Conditioning of leakage pump on EA chamber | UV photocathode laser alignment on Beam pointing stabilizer | UV laser on beam pointing stabilizer established Beam-based Laser-on-cathode alignment improved Gun phase stability over night
Glass capillary broke during installation  replaced, but fragments remain in chamber | EA LED periodically lights up, unintended |  |  | 11:15 water flow too low for TWS1 RF station 12:50 DIO1 does not switch on Temp and Humidity Servers off partially
MCS: Windows updates on BKR machines |  | Visit by Beate Heinemann Reference Phase Tracking for Gun enabled |  | 
Achievements
Difficulties
Notes

## Slide 3: New Baseplate Installed

## Slide 4: New Pre-defined Hexapod Positions

## Slide 5: UV beam on virtual cathode cam

## Slide 6: Beam based alignment of UV cathode laser
Before
After
Adjusting BPS picomotors
On LI.R1

## Slide 7: Schedule and Plan for the Week
Week 08
If you want to learn or join the shift: please give the shift leader a call (BKR 2840 / SINBAD Box 2454)
Date | Shift Crew
19.02. | Max, Frank
20.02. | Thomas, Max (morning)
21.02. | Thomas, Max
22.02. | Thomas, Hannes
23.02. | Thomas, Max
Mon: Petra IV
Tue – Fri, KW 09: TWAC