## Slide 1: Magnets Timeline, Cost and R&D Plan
1 CERN ,2 INFN – Genova, 3 INFN – Milano, 4 University of Milan
L. Bottura1, F. Boattini1, B. Bordini1, B. Caiffi2, S. Fabbri1, S. Mariotto3,4, M. Statera3

## Slide 2: Outline
References
Magnet timeline
R&D plan
Cost evaluation
Summary and discussion points

## Slide 3: Outline
References
Magnet timeline
R&D plan
Cost evaluation
Summary and discussion points

## Slide 4: References
402 pages
11 pages
42 pages
The material presented here is detailed and discussed extensively in the documents prepared for submission to the 2026 ESPPU process
Much space and attention was given to building a bottom-up and analytical R&D program

## Slide 5: Outline
References
Magnet timeline
R&D plan
Cost evaluation
Summary and discussion points

## Slide 6: Project Timeline
Technology R&D completed: 2032
Demonstrators built and tested: 2037
Prototypes and industrialization (Optimisation): 2040
Production completed: 2048

## Slide 7
This is one of the possible plans, prepared as a technically limited timeline
Most magnet milestones are well aligned with the overall plan of the project
A 3TeV option (consisting of HTS solenoids, NC RCS1+RCS2 and Nb-Ti collider) appears to be feasible with contingency by the desired start in 2050
A 10TeV option (HTS solenoids, NC RCS1+RCS2, HTS HCS3 and HTS collider) misses the desired milestones by 2…3 years, with no contingency
Technology R&D
Demonstrators
Prototypes and Industrialization
Production

## Slide 8: Outline
References
Magnet timeline
R&D plan
Cost evaluation
Summary and discussion points

## Slide 9: TRL Drives the R&D
We wish to reach a TRL 6 for the decision of construction, the level of readiness appropriate to enter the industrialization

## Slide 10: R&D Technology Milestones

## Slide 11: R&D Resources - Personnel
414FTEy

## Slide 12: R&D Resources - Material
82.5MCHF

## Slide 13: R&D Impact

## Slide 14: Practical Impact Examples
Fusion for Energy (ITER EU Domestic Agency)
  Framework agreement and first addendum in final negotiation
  Contribution to the design of the HTS target solenoid, relevant to the central solenoid of DTT
EUROFusion (next step European fusion reactor)
  Framework agreement signed in 2023, first addendum signed in 2024
  Contribution to the design of the HTS target solenoid, relevant to the magnets of a Volumetric Neutron Source proposed as next step in the European fusion strategy
Gauss Fusion (one of the leading EU fusion start-ups)
  Consultancy agreement signed in 2023
  CERN contribution to the design of the LTS/HTS GIGA stellarator magnets, based on advances in the HTS target solenoid
ENI (oil and gas energy giant)
  Framework agreement and first addendum signed in 2024
  Collaboration on the conceptual design and project proposal for the CERN construction of a large bore HTS solenoid (20@20 model coil) relevant to the muon collider and fusion
IFAST-2 proposal to INFRA-2025-TECH-01-02 (CERN, INFINEON, PSI)
  Proposal of fast pulsed power cell + magnet system sent to IFAST-2 coordination for ranking at TIARA
  Industrial interest in rapidly pulsed and large energy/power supplies

## Slide 15: Outline
References
Magnet timeline
R&D plan
Cost evaluation
Summary and discussion points

## Slide 16: Cost Model
PROPOSAL

## Slide 17: Cost Model

## Slide 18: Cost Estimate Examples
700 FTEy
8.2 BCHF
1000 FTEy
11 BCHF
CAVEAT: THIS IS ONLY AN ESTIMATE
WORK IN PROGRESS

## Slide 19: Cost Scaling Expectation
Material cost per unit length is proportional to coil cross section
M.A. Green, B. Strauss, IEEE TAS, 18(2), 248-251, 2008
Magnet stored energy is proportional to B2 and length
Green-Strauss scaling does not apply to accelerator magnets
Sector dipole

## Slide 20: Outline
References
Magnet timeline
R&D plan
Cost evaluation
Summary and discussion points

## Slide 21: Summary and Discussion Points
NOTE: while the R&D plan is rather self-consistent (R&D review), the present plan to completion is a basis for discussion
  Q1: Is the cost evaluation method shared and agreed ? And, assuming resources available, is the timeline credible and agreed ?
  Q2: Which scenario should we recommend as a baseline ?
    Nb3Sn – is it worth maintaining a line on this R&D ?
      HFM is working on this technology, but not at the right aperture, nor specification
      Is there a secured future for this technology ?
    Nb-Ti – should we propose a demonstrator ?
      Can be realized with relatively modest effort
      Could bring a strong image impact
    HTS for the various parts of the complex
      Is it credible ? Is it too ambitious ?
  Q3: Which R&D do we miss ?
    Combined function magnets
  Q4: are there means to simplify, standardize, and reduce cost ?

## Slide 22: HIC SVNT LEONES

## Slide 23: Magnet R&D Targets

## Slide 24: TM1 – 20@20

## Slide 25: TM2 – SOLID

## Slide 26: TM3 – UHF-Demo

## Slide 27: TM4 – RCS-String

## Slide 28: TM5 – MBHY

## Slide 29: TM6 – MBHTS

## Slide 30: TM7 – MBHTSY

## Slide 31: TM8 – MQHTSY

## Slide 32: Materials and Methods R&D
High-field measurement of transport properties of REBCO conductors, also necessary to define scaling laws required for the design and analysis of the magnet demonstrators;
Micrography, Micro-structure and mechanical properties of REBCO conductors and winding;
Radiation effects in REBCO conductors;
Tailored experiments to establish design rules for HTS magnets, e.g. allowable hot-spot temperature, or allowable peak stress and strain;
Multi-physics modeling of transient electromagnetics, mechanics and thermal fields in HTS magnets, relevant to the electro-mechanical design, operation and quench protection of NI HTS magnets.