## Slide 1: Working Group on XFEL Commissioning
1st Meeting
23.09.2011
Notes: How to edit the title slide
Upper area: Title of your talk, max. 2 rows of the defined size (55 pt)
Lower area (subtitle): Conference/meeting/workshop, location, date, your name and affiliation, max. 4 rows of the defined size (32 pt)
Change the partner logos or add others in the last row.

## Slide 2: Agenda
Purpose and Mandate
XFEL Schedule (very rough)
High Level Milestones
Open Questions
Organizational Matters
Notes: Before you start editing the slides of your talk change to the Master Slide view: Menu button “View”, Master, Slide Master:
Edit the following 2 items in the 1st slide: 1) 1st row in the violet header: Delete the existent text and write the title of your talk into this text field 2) The 2 rows in the footer area: Delete the text and write the information regarding your talk (same as on the Title Slide) into this text field.
If you want to use more partner logos position them left beside the DESY logo in the footer area Close Master View

## Slide 3: Purpose and Mandate
The European XFEL Project board calls for a working group to plan the commissioning of the facility
This group will work out the commissioning strategy, the initial operating envelope, the high level goals and their sequence
Although not specifically charged – and maybe even to early to deliver – a first commissioning schedule should be one of the outcomes

## Slide 4: XFEL Schedule (very rough)
  One year before linac cooldown (mid 2014) start of beam operation with the injector
  Backwards tied to start of linac cooldown, i.e. it makes little sense to start commissioning of injector earlier than 12 month before linac cooldown
  Fits to 3rd harmonic and cryogenics schedule
  Injector commissioning no issue for this working group
Cool down of main linac mid 2015 (driven by production rate of RF-modules)
Technical Commissioning as far as possible in parallel to installation, but expect some weeks of additional commissioning time before first beam into main linac

## Slide 5: XFEL Schedule

## Slide 6: Initial Beam Parameters
17.5 GeV
0.5 nC
  Higher charge eases diagnostics tasks
5 kA, 70 fs FWHM electron bunch
single – few bunches
  Eases machine protection issues

## Slide 7: High Level Milestones
First Beam through Linac
  A 17.5 GeV beam is transported through the linac to the TLD dump.
  Pattern: 10 Hz, single bunch, 0.5nC, C=100
  Control: Charge, peak current, energy and trajectory are controlled by slow feedbacks.
First Beam to TD4 (SASE1 and SASE3)
  A 17.5 GeV beam is transported through the linac to the T4D dump.
  Pattern: 10 Hz, single bunch, 0.5nC, C=100
  Control: Charge, peak current, energy and trajectory are controlled by slow feedbacks.
  Electron beam based trajectory alignment in undulator
First Lasing in SASE1
  Tasks:
    Photon based alignment of undulators
    SASE search SASE1 (0.1 nm)
  Alternatives:
    Start with SASE2 if SASE3 not ready
Lasing in SASE 3 (see 2.)

## Slide 8: High Level Milestones cont.
From here on parallel operation photon/electron development appears possible.
Multi-bunch operation
  Pattern: 10 Hz, 2700 bunches, 0.5nC, C=100
  Control: Charge, peak current, energy, trajectory and arrival time are controlled by slow and fast feedbacks.
Quasi-simulataneous operation of SASE1 and SASE2 beam line
  Pattern: 10 Hz, 2700 bunches, 0.5nC, C=100
  Control: Charge, peak current, energy, trajectory and arrival time are controlled by slow and fast feedbacks.
  Tasks:
    Bunch pattern control by fast switching elements
Flexibility in wavelength and bunch length
  Pattern: 10 Hz, 2700 bunches, 0.02-1nC, C=2000-50
  Control: Charge, peak current, energy, trajectory and arrival time are controlled by slow and fast feedbacks.
  Tasks:
    establish procedures to change bunch length/bunch charges
    establish procedures to change photon wavelength by changing energy/undulator gap

## Slide 9: High Level Milestones cont.
First Lasing in SASE2 (see 2.)

## Slide 10: High Level Milestones - Attempt to sort
Milestone |  |  | Beam where | Energy | Repetition Rate | # of Bunches | Bunch Charge | Peak Current | SASE Wavelength
 |  |  |  | GeV | Hz |  | nC | kA | nm
 | 1 | First Beam in Injector | I1D | 0.13 | 10 | 1-2700 | 0.5 | 0.05 | -
 | 2 | First Beam in BC2 | B2D | 2 | 10 | 1 | 0.5 | 5 | -
1 | 3 | First Beam in TLD | TLD | 17.5 | 10 | 1 | 0.5 | 0.5 | -
2 | 4 | First Beam in T4D | T4D | 17.5 | 10 | 1 | 0.5 | 0.5 | -
3 | 5 | Lasing in SASE 1 | T4D | 17.5 | 10 | 1 | 0.5 | 5 | 0.16
4 | 6 | Lasing in SASE 3 | T4D | 17.5 | 10 | 1 | 0.5 | 5 | 4
 | 7 | Parasitic lasing SASE1 and SASE 3 | T4D | 17.5 | 10 | 600 | 0.5 | 5 | 0.16/4
 | 8 | Multi Bunch operation | TLD | 17.5 | 10 | 600 | 0.5 | 0.5 | -
5 | 9 | Lasing with long bunch trains | T4D | 17.5 | 10 | 600 | 0.5 | 5 | 0.16
 | 10 | Compression at various bunch charges | TLD | 17.5 | 10 | 1 | 0.05-0.5 | 5 | -
 | 11 | Lasing with short pulses | T4D | 17.5 | 10 | 1 | 0.05-0.5 | 5 | 0.16
 | 12 | Wavelength variation | T4D/T5D | 10.5-17.5 | 10 | 600 | 0.5 | 5 | <0.1
 | 13 | First Beam in T5D | T5D | 17.5 | 10 | 1 | 0.5 | 0.5 | -
7 | 14 | Lasing in SASE 2 | T5D | 17.5 | 10 | 1 | 0.5 | 5 | 0.16
 | 15 | Slow 10 Hz switch between 1 & 2 | T4D/T5D | 17.5 | 10 | 1 | 0.5 | 0.5 | -
 | 16 | Fast switching and arbitrary bunch patterns | T4D/T5D | 17.5 | 10 | 600 | 0.5 | 0.5 | -
6 | 17 | Lasing with fast switching and arbitrary bunch patterns | T4D/T5D | 17.5 | 10 | 600 | 0.5 | 5 | 0.16/4
 | 18 | Multi Bunch operation | TLD | 17.5 | 10 | 2700 | 0.5 | 0.5 | -

## Slide 11: Open Questions
Start with SASE2 or SASE1/3
Once SASE is achieved how to continue (emphasize on user runs, machine development, additional beam lines, …)
Requirement to x-ray diagnostics during e-beam/SASE commissioning (this probably includes priorities/time-table)
Rough time-table for taking e-beam/SASE/x-ray into operation (at least up to ‘end of construction milestone’)
When to do fast e-beam switching, pulse train operation, pulse duration, etc.

## Slide 12: Organizational Matters
ToDos:
  Align rough commissioning schedule
  Gather sub-sytems commissioning pre-requisites and time needed
  Define day one photon diag
  …

## Slide 13: Organiztional Matters
Next Meetings:
  Friday, October 21, 10:00, 30b/459
  Friday, November 25 or December 02