## Slide 1: Development of FH Infrastructures
Detector Assembly Facility, Building 2, Wolfgang Pauli Centre, Data Centre, Test Beam Facility
Thomas Schörner PRC 100, 11 November 2025

## Slide 2: The Detector Assembly Facility (DAF)

## Slide 3: Detector Assembly Facility
Thinking about usage after HL-LHC tracker end-cap production
Ideas for the future:
“small” DAF: lab space for detector development (FE); compensation for labs in building 2?
“large” DAF: Plan to use as infrastructure for detector development (FH, FS / PETRA IV, potentially external / industry)
Contribution to High-Tech Agenda of Federal Government
Two clean rooms with 255 m2 (ISO6) and 620 m2 (ISO7); facility with specialized equipment for detector development and construction
Essential for the HL-LHC upgrades of the ATLAS and CMS tracker, excellent asset for future detector projects

## Slide 4: Building 2, the New Data Centre and the Wolfgang Pauli Centre

## Slide 5: B2: Status and Options
Theory and Computing Centre
            Building 2 (a and b)
            Built in 1972
            home to (parts of) DESY and UHH theory, to computer centre / IT and electronics development FE
            Status of building
            In strong need of repair (and extension) ..
            … but current renovation estimate at ~28 Mio EUR
            Decision: no full renovation, but investments into electricity / cabling and fire safety measures to keep building alive for ~10 more years.
            Consequences for theory and Computing Centre / IT!

## Slide 6: The New Data Centre
            DESY operates modern compute centre
            Focus on data-intense computing: LHC, DESY data sources, European XFEL, soon PETRA IV, …
            Science City Hamburg Bahrenfeld: new requirements
            … in terms of data volumes / rates, AI etc.
            Existing computing centre building 2b (built 1972!)
Extension / renovation not reasonable
 Feasibiliity study new compute centre SCHB on campus
Taking SCHB computing into the next decades
            Current plan and status:
Planning for joint DESY-UHH compute centre
Focus on data intense science for Bahrenfeld location
Aspiration: AI centre for northern Germany
Cost frame phase 1 (next slide): 96 Mio EUR
Notes: There is a document proposing such a regional AI centre in Hamburg, which has already quite detailed ideas on the structural and scientific implementation.

## Slide 7: A Staged Approach
… allowing continued use of building 2
Original one-building plan
Phased Ansatz with two buildings
adjust to the development of the needs from the main users
Separate into more manageable chunks
Area
Old: 2000 m2
New phase 1: ~10.000 m2
New phase 2: ~15.000 m2
Energy consumption
Old: 1.5 MW
New phase 1: 4.0 MW
New phase 2: 16.0 MW
New PUE = 1.158!
Invest:
Phase 1: 96.49 Mio EUR 19200 EUR/kWh
Phase 2: 138.8 Mio EUR 8697 EUR/kWh
Operation costs / year (100% IT usage, phase 2, 2025 cost base)
0.3 EUR/kWh: 52 Mio EUR
0.15 EUR/kWh: 28 Mio EUR (DESY price)

## Slide 8: A Staged Approach
… allowing continued use of building 2
Original one-building plan
Phased Ansatz with two buildings
adjust to the development of the needs from the main users
Separate into more manageable chunks
Area
Old: 2000 m2
New phase 1: ~10.000 m2
New phase 2: ~15.000 m2
Energy consumption
Old: 1.5 MW
New phase 1: 4.0 MW
New phase 2: 16.0 MW
Invest:
Roughly 100 Mio EUR for phase 1
Operation costs / year
Depending on electricity prices
28-52 Mio
Notes: New building very efficient PUE 1.1598 oder so!
2025 cost base)
0.3 EUR/kWh: 52 Mio EUR
0.15 EUR/kWh: 28 Mio EUR (DESY price)

## Slide 9: The Wolfgang Pauli Centre (WPC)
            Centre in existence since long
            Centre established as centre of excellence and meeting point of DESY + UHH theorists and guests with strong scientific programme
            Goal: building = surroundings that foster scientific exchange
Planning since about 10 years, numerous ideas for (initially) a new building on campus.
Goal: scientific home for theory, room for discussions and seminars, room for guest. / visitor programme
            Current status:
Rental and renovation of „Doppel-H“ close to campus Planning DESY-UHH concluded
Discussions with City of Hamburg about rental conditions ongoing
Expectation: Moving to Doppel-H in 2 years
An interdisciplinary centre for theoretical physics in Hamburg
WPC building requirements in numbers
DESY 116 persons
UHH 81 persons
WPC: 46 persons (guests, admin, etc.)

## Slide 10: The Test Beam Facility

## Slide 11: Test Beam Facility Status
            2025 Statistics (status 3 Nov)
376 users - 167 from German institutes
105 slots (weeks) – 81% used
~Half of the users are students  essential training facility!
Going very strong – many users, upgrade of infrastructure, Beamline4Schools !
            Telescope upgrade – ALPIDE!
New ALPIDE-based telescopes – first benevolent users!; some features identified and fixed
Next steps: Final board – 2nd generation submitted.
Inquiries from FNAL and SLAC
            Beamline4Schools 2025: 2 teams!
Two projects: testing self-designed muon detector and testing organic scintillators
A. Athanassidis and A. Laudrain essential as support scientists (and S. Krause!)
Continuous support with dedicated staff is essential!
Notes: Teams from Canada and Mexico
BIG RED MAGNET 1.4
pCMAG 1 T

## Slide 12: Test Beam Facility Future
Continued user interest / need  need to think about the „PETRA IV“ future
Schedule 2026 finalized – again well booked
Shutdown Sep ‘26 – Feb ‘27 (new LINAC II interlock, PIA renovation)
After 2027:
CERN LS3 (2027-29+)
Shift of PETRA IV (2030): “dark time” in Europe avoided
Coping with >700 users during LS3 a challenge (in particular given current person power)
Additional FNAL test beam facility down time starting 2027  additional beam time requests from US users expected
Test beam in PETRA IV era: Discussions ongoing!
Test beam should become integral part of PETRA IV project
Keep in mind: Test beam is an internationally used (and highly esteemed) infrastructure!

## Slide 13: Test Beam Facility Future: Options
Refurbish DESY II or build DESY IV (traditional injector)
Test beam line at PETRA IV?
(Politics? Cost? Space?)
Test beam at EU.XFEL? (bunch structure, rates, …)
Timely decision needed (PIV: review 2026, decision 2027)
Test beam in PETRA IV era: Discussions ongoing!
DESY DIR needs to decide that test beam becomes part of PETRA IV project
Central: Question of PETRA IV injector:
  Traditional injector: integrate test beam!
  Plasma injector: integration difficult!
Notes: DESY II ? IV and laser injection – geht zusammen oder nicht?
For XFEL: in principle wrong bunch structure and too high rate. Maybe Crystall extraction in halo of full bunches or using empty bunches?
DESY IV 100 M
DESY 2 refurb 20 M
XFEL rep rate too low – 5 Hz trains, Cw waere ein anderer Schnack
Note that ELBEx profits from new XTD8 location discussions and the possible synergies with laser fusion …

## Slide 14: Thank you!
            Thomas Schörner
DESY-FH/CMS
Notkestr. 85, D-22607 Hamburg
Tel: +49 40 (9) 8998 3429
thomas.schoerner@desy.de