## Items
Commissioning towards first lasing at 2 Angstroem in SASE1 and first experiment (Milestone "end of construction phase")
Minimally needed items and time needed by WP74 |  |  | created | Oct.14th, 2011
|  |  | updated | Oct.20th, 2011
Step | Device(s) | Description | Duration | Open questions / comments
1 | Transmissive Imager | see first spontaneous x-ray photons from a single undulator segment ("first light")
2 | ---------------------- spontaneous radiation up to offset mirrors
3 | Transmissive Imager | increase / change number of active segments |  | how many segments available ?
4 | Filter box + Transmissive Imager or Filter Box + K-mono Diode | check roughly xray energy (against theoretical value from gap setting)
5 | WP73 | commission collimators, apertures, slits, attenuators (position+function)
6 | 2D-Imager | detection of spontaneous radiation from single segment on 2D imager
7 | 2D-Imager + slits | checkout slits
8 | Diode (at K-mono) | measure angle-integrated pulse energy (photon flux) with diode
9 | Slits + Diode | find position of maximum intensity (find central ray): fast slit scan (e.g. slits at 1mmx1mm), find maximum signal on photodiode
10 | Transmissive Imager + Diode pos. | check beam pointing
11 | MCP-based detector | first search for SASE (pre-phBBA) |  | offset mirrors available ?
12 | K-mono + Diode | single segment (+ref) gap tuning: spectra by changing electron beam energy +/- 1.5% |  | wide scan ~ +/-1% range to find emission line, narrower scan ~ +/- 0.5% to acquire spectrum
13 | K-mono + Diode | repeat for all installed segments |  | 1) when using higher order reflexes, reject lower energies with foils 2) Might apply another PBBA method before moving to the next segment (depending on durations)
14 | K-mono + Diode | calibration scan of K vs. gap for each segment (fixed e-energy) |  | measure electron beam energy per shot
15 | K-mono + Diode | Steepest slope method / gap tuning of 2 adjacent segments: change gap of one segment, take spectra
16 | K-mono + Imager | optional - Quadrupole kick method: introduce 20µrad kick between these two segments, minimize DK
17 | K-mono | repeat pairwise segment tuning for all pairs
18 | K-mono | optional: pairwise tuning of non-neighboring segments
19 | K-mono | optional: vertical undulator alignment (single segment spectra, dK/K~y^2 )
20 | K-mono + Diode | Fine adjustment of phase shifters
21 | MCP-based detector | more search for SASE (post-phBBA): pulse energy and imaging
22 | ---------------------- first lasing at 2 Angstroem
23 | 2D-Imager | see FEL on 2D imager ("first lasing")
24 | all XGMDs & XBPMs | commission XGMDs and XBPMs
25 | XGMD-1 | calibrate FEL pulse energy with XGMD-1 (cross-check with estimate from e-beam energy loss)
26 | XBPM-1 | calibrate FEL position with XBPM-1
27 | XGMD-1 + XGMD-2 | check/calibrate attenuators
28 | XBPM-1 + XBPM-2 | check/calibrate FEL pointing
29 | Filter Box + Diode (+MCP?) | initial spectral measurements using absorption edge of foils |  | K-edges Ge=11103eV(1A), Cr=5998eV (2A), Ni=8333eV, GaAs wafer
30 | XGMD | Optimize undulator taper (empirically) by intensity
31 | Pop-in monitor after mirrors | photon assisted offset mirror adjustment (tilt,translation)
32 | ---------------------- transport FEL to XHEXP1
33 | PES | Commissioning of PES, measure spectrum COG
34 | Pop-in monitor after distrib. mirrors | photon assisted offset mirror adjustment (tilt,translation)
35 | all phDIAGS | optimize SASE (vary bunch compression, emittance, RF, BBA, taper,...)
36 | ---------------------- experiment in XHEXP1
37

## comments
List of comments to this file
Gianluca Geloni, 20Oct2011
A general comment about pbba steps. From your table it looks like if you plan to go through one alignment method for all segments, and then switch to the next (e.g. 12-13). Are you searching from SASE again in between? Maybe it will be useful to perform different alignment methods on the same segment before going to the next segment, and compare results looking if they are comparable within the required accuracy. And then look for SASE again (with finger crossed….)
Concerning durations, I think you will be capable to tell something more only when sub-procedures for each method are investigated. For example, take the two segment+kick. We have some simulations which indicate the number of bunches needed, and from that we have a “time”. But this is obviously only part of the story. Extra time will be taken for physically changing the gap, redo the measurement to see the changes, analyze the data… before you have a detailed procedure, it is a bit difficult to estimate the duration, in my opinion…
Cigdem Ozkan, 20Oct2011
I am not sure about the rough energy check with the filter box. I think this is not straightforward nor conclusive. That might be better done with a single diode (already at K-mono) in the same position of the scintillator. This can be discussed later if indeed the energy check needs to be done.
There is no mention of alignment methods. Is this our concern?