## Slide 1: WP-85 SQS Scientific Instrument XFEL Project Progress Report (1-2012)
presented by
Tommaso Mazza
(for WP-85)
“Small Quantum
Systems”
Atoms
Molecules
Clusters
Notes: How to edit the title slide
Upper area: Title of your talk, max. 2 rows of the defined size (55 pt)
Lower area (subtitle): Conference/meeting/workshop, location, date, your name and affiliation, max. 4 rows of the defined size (32 pt)
Change the partner logos or add others in the last row.

## Slide 2: Comparison of forecasted and achieved progress: Jul. 11 -> Dec. 11
Status of SQS
Towards the Technical Design Report
Experimental campaigns at FELs
Installation of the HHG experiment
Recruitment process
Forecast
TDR
Experiments
WP-85, T. Mazza / M. Meyer XFEL Project Progress Report (1_2012) - 19th of April 2012
OUTLINE
Notes: Before you start editing the slides of your talk change to the Master Slide view: Menu button “View”, Master, Slide Master:
Edit the following 2 items in the 1st slide: 1) 1st row in the violet header: Delete the existent text and write the title of your talk into this text field 2) The 2 rows in the footer area: Delete the text and write the information regarding your talk (same as on the Title Slide) into this text field.
If you want to use more partner logos position them left beside the DESY logo in the footer area Close Master View

## Slide 3: Comparison of forecasted and achieved progress: Jul. 11 -> Dec. 11
Preparation of TDR
  Detailed design study started March 2012
    UHV chambers AQS and NQS
    arrival of H. Zhang (SQS Instrument engineer)
WP-85, M. Meyer
Towards the TDR
AQS - chamber
“Atomic-like Quantum Systems”
Vacuum < 10-10 mbar
Analyzers:
5 e-TOFs
Velocity Map Imaging (e/ions)
Magnetic bottle electron spectrometer
High resolution XUV spectrometer
WP-85, T. Mazza / M. Meyer XFEL Project Progress Report (1_2012) - 19th of April 2012
Notes: Before you start editing the slides of your talk change to the Master Slide view: Menu button “View”, Master, Slide Master:
Edit the following 2 items in the 1st slide: 1) 1st row in the violet header: Delete the existent text and write the title of your talk into this text field 2) The 2 rows in the footer area: Delete the text and write the information regarding your talk (same as on the Title Slide) into this text field.
If you want to use more partner logos position them left beside the DESY logo in the footer area Close Master View

## Slide 4: Comparison of forecasted and achieved progress: Jul. 11 -> Dec. 11
Preparation of TDR
  In-kind contribution & User consortia
    Swedish in-kind proposals U. Uppsala
      XUV (grating) fluorescence spectrometer J.Norgren/J-E.Rubenson
      Magnetic bottle-type electron spectrometer R. Feifel
    User consortia & add-on equipment
      Controlled molecules (COMO) J. Küpper / CFEL
      ((XUV (crystal) fluorescence spectrometer M. Simon / France))
WP-85, M. Meyer
Towards the TDR
WP-85, T. Mazza / M. Meyer XFEL Project Progress Report (1_2012) - 19th of April 2012
Notes: Before you start editing the slides of your talk change to the Master Slide view: Menu button “View”, Master, Slide Master:
Edit the following 2 items in the 1st slide: 1) 1st row in the violet header: Delete the existent text and write the title of your talk into this text field 2) The 2 rows in the footer area: Delete the text and write the information regarding your talk (same as on the Title Slide) into this text field.
If you want to use more partner logos position them left beside the DESY logo in the footer area Close Master View

## Slide 5: Comparison of forecasted and achieved progress: Jul. 11 -> Dec. 11
  Revised floor plan
    Definition of space requirements behind SASE3
WP-85, M. Meyer
Towards the TDR
WP-85, T. Mazza / M. Meyer XFEL Project Progress Report (1_2012) - 19th of April 2012
Notes: Before you start editing the slides of your talk change to the Master Slide view: Menu button “View”, Master, Slide Master:
Edit the following 2 items in the 1st slide: 1) 1st row in the violet header: Delete the existent text and write the title of your talk into this text field 2) The 2 rows in the footer area: Delete the text and write the information regarding your talk (same as on the Title Slide) into this text field.
If you want to use more partner logos position them left beside the DESY logo in the footer area Close Master View

## Slide 6: Comparison of forecasted and achieved progress: Jul. 11 -> Dec. 11
  Ongoing exchange with other WPs (now focused on TDR)
    Detailed definition of DAQ & Control (WP-76) requirements Ch. Youngman / N. Coppola
    Soft X-ray detector requirements (WP-75)
          Working group (DSSC) M. Kuster / M. Turcato
    Sample environment (WP-79)
          Cluster source, liquid jet J. Schulz
    Optical Layout for SQS (WP-73)
          KB-optics, monochromator H. Sinn
    Optical Laser (WP-78)
          Definition of “common” & “SQS” items M. Lederer
WP-85, M. Meyer
Towards the TDR
WP-85, T. Mazza / M. Meyer XFEL Project Progress Report (1_2012) - 19th of April 2012
Notes: Before you start editing the slides of your talk change to the Master Slide view: Menu button “View”, Master, Slide Master:
Edit the following 2 items in the 1st slide: 1) 1st row in the violet header: Delete the existent text and write the title of your talk into this text field 2) The 2 rows in the footer area: Delete the text and write the information regarding your talk (same as on the Title Slide) into this text field.
If you want to use more partner logos position them left beside the DESY logo in the footer area Close Master View

## Slide 7: Comparison of forecasted and achieved progress: Jul. 11 -> Dec. 11
  Exchange with User community
    Presentation & Discussions of CDR
    FLASH II Workshop October 12 – 14
    Joint Instrumentation seminar November 11
    European XFEL school – Moscow November 14/15
    European XFEL Users Meeting January 25/26
    SQS Workshop @ Users Meeting January 26
    Seminar Dublin City University April 19
WP-85, M. Meyer
Towards the TDR
WP-85, T. Mazza / M. Meyer XFEL Project Progress Report (1_2012) - 19th of April 2012
Notes: Before you start editing the slides of your talk change to the Master Slide view: Menu button “View”, Master, Slide Master:
Edit the following 2 items in the 1st slide: 1) 1st row in the violet header: Delete the existent text and write the title of your talk into this text field 2) The 2 rows in the footer area: Delete the text and write the information regarding your talk (same as on the Title Slide) into this text field.
If you want to use more partner logos position them left beside the DESY logo in the footer area Close Master View

## Slide 8
Experimental campaigns at XUV sources
  LCLS – THz streaking for X-ray timing diagnostics
    (PI: A. Cavalieri, CFEL)
    5 shifts March 15 – 19, 2012
  FERMI – LDM commissioning
    (LDM consortium)
    8 shifts March 22 – 25, 2012
  BESSY II – Two-color (opt. Laser + SR) experiments
      (Within SFB925 – A3)
    2 weeks March 12 – 25, 2012
WP-85, M. Meyer
SQS Science
WP-85, T. Mazza / M. Meyer XFEL Project Progress Report (1_2012) - 19th of April 2012
Notes: Before you start editing the slides of your talk change to the Master Slide view: Menu button “View”, Master, Slide Master:
Edit the following 2 items in the 1st slide: 1) 1st row in the violet header: Delete the existent text and write the title of your talk into this text field 2) The 2 rows in the footer area: Delete the text and write the information regarding your talk (same as on the Title Slide) into this text field.
If you want to use more partner logos position them left beside the DESY logo in the footer area Close Master View

## Slide 9
HHG Installation
  Beamline design completed
  Focusing optics tested
  Vacuum parts being delivered
  Setup for coincidence measurements (VMI + eTOF) installed, detectors tested
WP-85, M. Meyer
SQS Science
WP-85, T. Mazza / M. Meyer XFEL Project Progress Report (1_2012) - 19th of April 2012
Focusing mirror
VMI
eTOF
Focusing mirror
diagnostics
monochromator
HHG cell
HHG beampath
Notes: Before you start editing the slides of your talk change to the Master Slide view: Menu button “View”, Master, Slide Master:
Edit the following 2 items in the 1st slide: 1) 1st row in the violet header: Delete the existent text and write the title of your talk into this text field 2) The 2 rows in the footer area: Delete the text and write the information regarding your talk (same as on the Title Slide) into this text field.
If you want to use more partner logos position them left beside the DESY logo in the footer area Close Master View

## Slide 10
Design studies for TDR
  Late and not yet finished
    late recruitment of mechanical engineer
Pump-probe experiments with HHG sources
  Delayed
    no replacement of 2nd postdoc yet
WP-85, M. Meyer
Delays / deviation from the planning
WP-85, T. Mazza / M. Meyer XFEL Project Progress Report (1_2012) - 19th of April 2012

## Slide 11
Personal resources
  Leading scientist: Michael Meyer 05-2010
  Post-doc: Tommaso Mazza 04-2011
  Post-doc: NN Q2-2011
    28 candidates (2nd round)
    interviews planned May 11, 2012
  Mechanical engineer Haiou Zhang 03-2012
  PhD Student: Sadegh Bakhdiarzadeh 11-2011
    SFB 925, project A1 (PIs. M. Martins / M. Meyer)
  PhD Student: Amir Jones Rafipoor 03-2012
    SFB 925, project A3 (PIs: M. Drescher / M. Meyer)
WP-85, M. Meyer
Status of SQS WP
WP-85, T. Mazza / M. Meyer XFEL Project Progress Report (1_2012) - 19th of April 2012
Notes: Before you start editing the slides of your talk change to the Master Slide view: Menu button “View”, Master, Slide Master:
Edit the following 2 items in the 1st slide: 1) 1st row in the violet header: Delete the existent text and write the title of your talk into this text field 2) The 2 rows in the footer area: Delete the text and write the information regarding your talk (same as on the Title Slide) into this text field.
If you want to use more partner logos position them left beside the DESY logo in the footer area Close Master View

## Slide 12: WP schedule
WP-85, M. Meyer
Technical Design Report – SQS October 2012
    Detailed design
      Definition of analyzer specifications
      Definition of focusing optics
      Definition of optical laser transport
    Exchange with Diagnostic group – WP-74 (J. Grünert)
    Information & participation of UC
      Series of ½ or 1 day meetings (including ART)
          AQS – NQS
          Optical laser
          VMI, REMI, Coincidence modes
          Non-linear processes
          Imaging
          Sample preparation
          etc
    Organization of inkind and add-on equipment
WP-85, T. Mazza / M. Meyer XFEL Project Progress Report (1_2012) - 19th of April 2012

## Slide 13: WP schedule
Experiments with kHz laser system at PETRA III
    Installation of HHG set-up
    Experiments with combined VMI-eTOF setup
    First fs pump-probe experiments
Experimental Campaigns at XUV sources (next 6 months)
    5 shifts at DORIS (BW3 beamline) (May, 2012)
      Test -> Characterization of VMI spectrometer
    6 shifts at FLASH (June, 2012)
      Non-linear photoionization dynamics in atoms
    12 shifts at FERMI (July, 2012)
      Last commissioning of the LDM endstation before open-to-users beamtime
WP-85, M. Meyer
WP-85, T. Mazza / M. Meyer XFEL Project Progress Report (1_2012) - 19th of April 2012

## Slide 14: WP schedule
WP-85, M. Meyer
Technical Design Report – SQS October 2012
Start of sending out orders beginning 2013
Reception, test and assembly 2013
Installation in experimental hall end 2014
Ready for beam end 2015
WP-85, T. Mazza / M. Meyer XFEL Project Progress Report (1_2012) - 19th of April 2012