## Slide 1: WP81 FXE Instrument
XFEL Project Progress Report
(1-2012)
Andreas Galler for Christian Bressler
Notes: How to edit the title slide
Upper area: Title of your talk, max. 2 rows of the defined size (55 pt)
Lower area (subtitle): Conference/meeting/workshop, location, date, your name and affiliation, max. 4 rows of the defined size (32 pt)
Change the partner logos or add others in the last row.

## Slide 2: XAS/XES/XRD at the FXE instrument
Dynamics of Solids and Liquids
Combine versatile structural tools into one single setup - x-ray absorption (XANES, EXAFS) - x-ray emission (XES, RXES, …) - x-ray scattering (XRD, diffuse scattering)  Obtain new information during the dynamics
Maintain both ambient and vacuum options - ambient conditions for liquids, solids, … - vacuum chamber for surfaces, cryogenic samples, …
Exploit the highest possible time resolution (≤25 fs) …include as much flux as possible (≥ 120 pulses)

## Slide 3: Towards the TDR
Preparation of TDR and Instrument Realization
  In-kind contribution
    Danish in-kind proposal DTU
      production carried out by JJ X-ray
The IKC basically covers nearly the entire scientific instrument.
But MHz compatible 1D/2D detectors, required CRLs, and timing tools remain one of the development tasks of the FXE group.

## Slide 4: Towards the TDR
  Technical Realization:
    The design will be performed in a collaborative effort between FXE and JJ X-Ray and DTU
    The production will be performed by JJ X-Ray in Denmark.
  List of the acceptance tests foreseen:
    Factory acceptance test (FAT) prior to delivery
    Installation and mechanical site acceptance tests (SAT) at XFEL.
    Commissioning with beam

## Slide 5: The Envisioned FXE Instrument
Maintain both Vacuum and Ambient conditions

## Slide 6: FXE Sample Area

## Slide 7: Exploiting complementary techniques (ESRF, APS)
1s2p RXES
1s3p XES
1s2p XES
X-ray Diffuse Scattering (XDS)
XANES
EXAFS
Sector 7ID @ APS, Argonne (3.36 MHz)
KB optics
He-filled
sample chamber
Pilatus
APD
Si/Ge analyzer crystal
APD
Laser
To be submitted 2012
Sample
UDECS collaboration at work!

## Slide 8: XDS preliminary Analysis
Fe(bpy)3/H2O
Measure solute structural changes via fs XDS!
Raw data
Azimuthally integrated data

## Slide 9: Activities and Milestones of the IKC
The major milestones and time schedule:
  Technical Design Report: Sept. 2012
  Final Design Review of each component: Sept. 2013
  Production and Factory Acceptance Tests (FAT’s): 2013 - 2015
  Delivery of all components completed: Mar. 2015
  Site Acceptance Tests of mechanical performance: Jun. 2015
  Commissioning with beam: Dec. 2015

## Slide 10: X-ray Beam Transport (5-20 keV)

## Slide 11: Beam Size Considerations
Beam on DM (380 m): - horizontally bend OM (250 m) (intermediate focus near 600 m)
- collimate beam at 213 m (CRL collection) - combination of both

## Slide 12: Heat Load on Be lens (213 m), 5 keV/0.25 nC

## Slide 13: Revised Floor Plan
FXE
ctrl
SPB
ctrl
SPB
optics
FXE optics
Optical laser (~16.5x6 m2)
SPB experiments
MMM
ctrl
MMM
experiments
FXE
experiments
PP-laser
Sync
Prep, service, spare
lock
KB1
FXE racks
SPB racks
KB2
Jet
Jet
Staging
area
racks
(preliminary)

## Slide 14: Time Line
April 2011: CDR out
September 2012: TDR
2013+: JJ X-ray will deliver first components
2014+: Installation in exp. Hall
Late 2015: ready for beam

## Slide 15: Other Issues
Participation in LCLS beamtime March 2012
PETRA III beamtime June 2012
Participation in SACLA Beamtime June 2012
PostDoc Julien Nillon hired for the CRISP Project devoloping a MHz NOPA April 2012
Openings: 2 PhD students 2012
  (1 SFB925; 1 IMPRS)