## Sketch of Module
Panel 2
Panel 2
Cable Tray 2
Panel 2
Panel 1
Cable Tray 1

## Tabelle1
|  | patch panel | count
Tray 1 | Contains the cables that are related to the couplers.
| interlock signals | 1 | 40
| RF cables probe | 2 | 8
| RF cables HOM(?) | 2 | 16
| cavity tuners | 1 | 8
| piezo cables | 2 | 8
| temperature sensors cable | 1 | 8
verteilerdose interlock signals
| coupler motor cable | 1 | 8
| Pump cable | 1 | 2
| Bias HV cable | 1 | 8
| Interlock Flat Cable | 1 | 8
| Install Cables before AMTF Test | OK
| Install supports at Saclay | OK
| Install cables in one step by one team (one company) | OK
| Cables split on both patch panels | OK
Tray 2 | Contains cables related to waveguides
| WG Forward/Reflected | 2
| Phase Shifter Motor | 2
| Install cables at WATF, Musterkabelbaum, Auftrag auch ueber MDI5 | OK
| Find agreement on cable type | klären
| Define interface with LLRF bundle | klären
General
Kabelarbeiten Tray1&2 werden von MDI5 organisiert
Kabel und Stecker werden von WPs beschafft, bei MDI gelagert
Patchpanel und Durchfuehrungen von MDI
Funds (PSP-Element angeben)
WP05 hat Mittel für Koppler-Kabel
WP02 Probe, WP01 Forw/Refl
| Quality Control/Measurements | nicht besprochen
| type of rf cable | klären | M. Hüning
| Pritschenhalter von MKS betreuen lassen? Aufnahme in Teileliste | klären mit K. Jensch | J. Liebing
| HOM wirklich komplett verkabeln? Mittel zur Zeit nicht vorhanden. Abschlusswiderstände zu gross für Patch-Panel | klären mit Schlarb, Baboi, Sekutowicz | M. Hüning