## Tabelle1
Minutes of the TC Meeting 03-2012
2012-02-15
Item | Title | WP | Follow up
TCM-03-01 | Issue List | all | M. Hüning | done
Description | Issue List will be followed up by WPRs, TC only to collect the results. The decision to close an issue will be communicated in the TC-Meeting
Action | TC will update the issue list in the EDMS, the most recent one will be published after TC-Meeting
TCM-03-02 | Issues | TC,01,03,04,05,06,08,11,33,34,35,36,73 | WPR | done
Description | Close issues TC-02,-04,-05,-07,-09,-11, WP 01-03,03-04,04-01,05-02,06-01,06-02, 08-03,11-03,33-02,34-09,35-01,36-04,36-05,73-02
Action | done
TCM-03-03 | IRR Questionaire | all | A. Brand
Description | A questionaire was presented, that will be sent to WPs who are scheduled to start installation work in the near future. This questionaire will serve as the installation readiness review (IRR).
Action | Continue for future installation tasks.
TCM-03-04 | Report from Photon Systems Coordinator | TC
Description | There is a bi-weekly meeting concerning photon systems coordination. Examples of the current topics are presented to be found on this meeting's indico page.
Action | Continue
TCM-03-04 | Tunnel Access | TC, WP36 | M. Hüning
Description | The procedure for tunnel access can be found on this meeting's indico page. At present this exists in german language as the protagonists of the infrastructure installation are german speaking.
Action | Follow along the procedure, translate into english language in due time.
TCM-04-01 | Issues | 11.06 | TC
Description | Closed Issues 11-3 and 06-2
TCM-04-02 | XTL installation | TC
Description | M. Hoffmann reported on the schedule for installation start and access procedure to construction site. There is a concern about the elevator which will not be ready by end of march, WP31 will take care that the shaft will be available until the elevator is ready.
Action | everything on track
TCM-04-03 | Noisy floor slabs | TC/WP31/WP33 | M. Hoffmann
Description | Floor slabs in XTL are unstable due to 4-point support, cause noise and complaints from neighbours. Slabs supporting beamline elements will have to be screwed down. In the transport path slabs might have to be screwed under inhabitated areas.
Action | Continue tests with damping materials
TCM-04-04 | New (Old) design for Rack Shielding | TC/WP33 | M. Hoffmann
Description | Rack shielding design no longer contains doors. In the bunch-compressors connected with support posts.
Action | Update rack specs (for higher load). Girder tests
TCM-04-05 | Detailed room model | TC, many
Description | There is now a detailed model of a single rf section, BC close to being finished
Action | Make available in EDMS
TCM-05-01 | Cold Water for Air Conditioning | WP34, WP71 | T. Haas
Description | WP34 proposes to increase the cooling water temperature going to the air conditioning units. This is in accordance with a request by the GMSH. It is checked and approved within WP34, a final check with WP71 is needed.
Action | Contact WP71 for information
TCM-05-02 | Cold Water for racks | WP34, many | M. Hüning
Description | WP34 proposes to change the cold water temperature for the rack cooling from 18 deg to 20 deg. A big saving in energy is expected, fallback in case of problems is easy. H. Schlarb commented that bigger heat exchangers would be required inside the racks if the absolute temperature was to remain constant.
Action | Start formal process to collect the pros and cons
TCM-05-03 | Beamline updates in injector | TC, WP14, 17, 18 ,19, 33 | M. Hüning
Description | Regular meetings on injector beamline update
Action | Continue
TCM-05-04 | Update on Coupler Production | WP05 | W. Kaabi
Description | An update on the schedule for the prototype couplers was presented (slides in the agenda). The schedule for brazing and copper plating is delayed from the schedule presented before. W-D. Moeller remarked that updates on the status need to be communicated more often and regularly. The plating process is not verified yet, the thickness in the most recent iteration is outside the specs and the RRR is known from samples only.
Action | Setup Regular Communication
TCM-06-01 | PPR 1-2012 | all | R. Wichmann, W. Decking
Description | On April 16-19 the first Accelerator Consortium Meeting will take place at DESY. For the accelerator work packages this is also the PPR. The photon work packages will attend the meeting but have a separate session on April 19th for their PPR presentations. Update of the MSPE and submission of status reports are due on April 2nd.
TCM-06-02 | CR Tunnel Ventilation | TC, WP34 | M. Hüning
Description | The revised ventilation concept for all tunnels was presented. It foresees serving all tunnels sequentially with only one air intake and one outlet.
Action | Let WP35 assess the amount of radioactive isotopes in the exhaust air, if tolerable approved.
TCM-06-03 | Update on XTL section | TC, many | M. Hoffmann
Description | There are ideas to reduce noise from floor slabs, tests to be performed. Cable planning progresses for RF section, test setup in mock-up. Installation work in XTL has started and advances satisfactory. There are delays for individual tasks which can be handled.
TCM-07-01 | Installation meeting | TC | M. Hüning
Description | The Installation meeting will take place every second Tuesday at 10:00h in 30b/459. Next date March 28th.
TCM-07-02 | Milestone Definition | TC | M. Hoffmann
Description | A list of milestones to be used by the PIT has been presented. There are concerns that the milestone linking as provided by the MSPE is not sufficient for the installation planning. It would have to be backed-up by contact in person.
Action | Keep us informed!
TCM-07-03 | Module Cabling | TC, many | E. Negodin, M. Hüning
Description | On March 20 there was another meeting on module cabling. There are two important results with wide implications. There shall be two patch panels which will change location depending on the category "left" or "right" waveguide distribution. Second the first batch of cables shall be installed before the AMTF test. This would mean that the decision between "left" and "right" would take place before the AMTF test.
Action | Cross check implications with Module Coordinator and evaluate further technical boundaries
TCM-07-04 | Report from Photon Systems Coordinator | TC | T. Haas
Description | Planning of the XHQ, XEXP1 and Schenefeld site is ongoing. Next step for the XHQ is the "Raumbedarfsantrag" to be done by April 20. Lab planning continues. Requirements on labs have almost tripled since 2007, building correspondingly larger, additional TGA requirements. Details in the talk. For the central heating the option of an BHKW (combined heat and power plant) shall be taken into account.
TCM-08-01 | Dates | TC | M. Hoffmann
Description | A List of dates for installation activities was presented to be retrieved from Indico agenda.
TCM-08-02 | Injector Section | TC | M. Hüning
Description | A solution for the installation of a quadrupole inside the shielding downstream of the injector. The Quadrupole will have to be accessed from the side. A hole has to be cut into the concrete.
TCM-08-03 | Temperature Stability of Glass Fibres in Channel | TC, WP18 | M. Hüning, H. Schlarb
Description | Temperature Stability of Glass Fibres in Channel is a concern. Initial ideas to insulate the channel seem to help very little.
Action | Finish evaluation soon.
TCM-08-04 | Schedule WP05 | WP05, ACC | W.-D. Möller, H. Weise
Description | The schedule of the coupler production is far behind the original planning. It is 1/2 year delayed against the emergency plan from end of last year and more than one year behind the original planning. CRITICAL!
Action | Letter to the Orsay management, close follow-up
TCM-08-05 | Cavity production | WP04, ACC | H. Weise
Description | Start of cavity production by one company is delayed, August instead of June. But the rate will be higher than anticipated, contingency towards the end.
TCM-09-01 | XTL installation update | TC, many | M. Hoffmann
Description | The first installation steps in the XTL are finished, many are ongoing, four are delayed. The survey marks on the floor are only slightly delayed, the other three tasks are mentioned separately below.
TCM-09-02 | Rail for survey equipment delayed | WP32
Description | Due to problems with availability of material the installation of the rail for survey equipment is delayed from early April to beginning of May. If the new date is kept this would just about fit with the other tasks.
TCM-09-03 | Cable Tray on the left delayed | WP34
Description | The cable tray on the left for safety cabeling is delayed until after moving the floor plates - also due to missing material. A new time slot is found for this.
TCM-09-04 | Ceiling brackets for the Modules delayed | WP33, many
Description | Due to a delay of the PRR the ceiling brackets for the modules will arrive too late to be installed bevor opening the floor. Sepecial logistics will be required to make up for this.
TCM-09-05 | Solution for noisy floor slabs | WP33, TC
Description | There is a solution to reduce noise emission from floor slabs. This will be implemented when the floor is moved back into place.
TCM-09-06 | Test setup of BC girder | many | M. Hoffmann
Description | One bunch compressor girder is set up in the mock-up tunnel. This will be used for vibration measurements. For this the mounting on the floor has to be re-done. Comparison of measured and simulated resonances can be performed.
Action | Assessment of results against requirements
TCM-10-01 | Time Schedule Consolidation WPGs 2 and 4 | many | R. Wichmann
TCM-11-01 | Issue List Update
Two items concerning cold magnets were taken off the list
TCM-11-02 | XTL Survey | WP32 | J. Prenting
First pass of the XTL survey is finished. The tunnel is better than +/- 50mm straight, which is well within specifications. 3D point clouds are available
TCM-12-01 | Schedule Consolidation | WPG3&5,WP01,WP02,WP17 | R. Wichmann
TCM-13-01 | AMTF Status | WP10 | B. Petersen
Many individual strands of activity have to be considered: Cryo Supply line, compressors, subcooler box, vertical cryostats, module test stands, rf stations, mounting platform. Critical path is defined by vertical cryostat.
Close follow up on vertical cryostat
TCM-13-02 | XTL status |  | M. Hoffmann
Installation is progressing, acquired a few delays which must not affect the overall schedule. Water installation starts in June. New design for girder being worked on, PRR soon.
TCM-13-03 | Module Cabling |  | M. Hüning
Cabling work on the modules has been organized. Weight of cables has been summarized,
final check of list and the audit of statics