## MBOM
Level of Installation | [6 empty] | EDMS ID |  | Metadata |  |  |  | Serialization
L1 | L2 | L3 | L4 | L5 | L6 | L7 | 3D-Modell | Drawing | Amount | Responsible WP | Coordinator | Supplier | Serialized? | S/N Format | Who places S/N? | Label Type
Injector Linac
Level of Installation L2: Aligned Gun |  |  |  | TC
Level of Installation L3: Connected Gun |  |  |  | TC
Level of Installation L4: Installed Gun |  |  |  | WP14
Level of Installation L5: Gun System |  |  |  | WP14
Level of Installation L6: Cavity |  |  |  | WP19
Level of Installation L6: Magnet |  |  |  | WP14
Level of Installation L6: Support |  |  |  | WP19
Level of Installation L6: Cathode Chamber |  |  |  | WP19
Level of Installation L6: Beamline to first module |  |  |  | WP19
Level of Installation L6: Commissioned Laser System |  |  |  | WP14
Level of Installation L5: Gun Installation |  |  |  | WP33
Level of Installation L4: Water Connection |  |  |  | WP34
Level of Installation L4: Magnet Connection |  |  |  | WP34
Level of Installation L4: Vacuum Connection |  |  |  | WP19
Level of Installation L4: RF Connection |  |  |  | WP01
Level of Installation L4: LLRF Connection |  |  |  | WP02
Level of Installation L4: Diagnosis Connection |  |  |  | WP17
Level of Installation L3: Gun Alignment |  |  |  | WP32
Level of Installation L2: Alligned Injector String |  |  |  | TC
Level of Installation L3: Connected Injector String |  |  |  | TC
Level of Installation L4: Injector String |  |  |  | WP13???
Level of Installation L5: Installed Module |  |  |  | WP33
Level of Installation L6: Module with RF distribution |  |  |  | ??? (MO)
Level of Installation L7: Module |  |  |  | WP10
Level of Installation L7: RF distribution |  |  |  | WP01
Level of Installation L6: Support |  |  |  | WP33
Level of Installation L6: Initial Alignment |  |  |  | WP32
Level of Installation L5: Installed 3.9 GHz Module |  |  |  | WP33
Level of Installation L6: 3.9 GHz Module |  |  |  | WP46
Level of Installation L6: Support |  |  |  | WP33
Level of Installation L6: Initial Alignment |  |  |  | WP32
Level of Installation L5: Feedcap |  |  |  | WP13
Level of Installation L5: Endcap |  |  |  | WP13
Level of Installation L5: Injector String Integration |  |  |  | WP13
Level of Installation L6: Inter-Module Connection |  |  |  | WP13
Level of Installation L6: Feedcap Connection |  |  |  | WP13
Level of Installation L6: Endcap Connection |  |  |  | WP13
Level of Installation L4: Water Connection |  |  |  | WP34
Level of Installation L4: Magnet Connection |  |  |  | WP34
Level of Installation L4: Vacuum Connection |  |  |  | WP19
Level of Installation L4: RF Connection |  |  |  | WP01
Level of Installation L4: LLRF Connection |  |  |  | WP02
Level of Installation L4: Diagnosis Connection |  |  |  | WP17
Level of Installation L3: Injector String Alignment |  |  |  | WP32
Level of Installation L2: Aligned Warm Injector Beamline |  |  |  | TC
Level of Installation L3: Connected Injector Beamline |  |  |  | TC
Level of Installation L4: Installed Injector Beamline |  |  |  | TC
Level of Installation L5: Magnet Support XQI |  |  |  | WP33
Level of Installation L5: XQI Magnet |  |  |  | WP12
Level of Installation L5: XQC Magnet |  |  |  | WP12
Level of Installation L5: Magnet Support XB.. |  |  |  | WP33
Level of Installation L5: XB…. |  |  |  | WP12
Level of Installation L5: Vacuum Chamber Support |  |  |  | WP19????
Level of Installation L5: Vaccum Chamber |  |  |  | WP19
Level of Installation L5: Diagnostics |  |  |  | WP17
Level of Installation L5: Pre-Integrated Injector Beamline Girder 1 |  |  | 1 | ???? (TC/WP33)
Pre-Integrated Injector Beamline Girder 2
Pre-Integrated Injector Beamline Girder 3
Girder Installation
Level of Installation L5: Injector Beamline Installation |  |  |  | WP33
Level of Installation L4: Injector Beamline Connection |  |  |  | WP33
Level of Installation L5: Water Connection |  |  |  | TC
Level of Installation L5: Magnet Connection |  |  |  | WP34
Level of Installation L5: Vacuum Connection |  |  |  | WP34
Level of Installation L5: RF Connection |  |  |  | WP19
Level of Installation L5: LLRF Connection |  |  |  | WP01
Level of Installation L5: Diagnosis Connection |  |  |  | WP02
Level of Installation L3: Injector Beamline Alignment |  |  |  | WP17
Level of Installation L2: Aligned Laser Heater |  |  |  | WP32
Level of Installation L3: Connected Laser Heater |  |  |  | TC
Level of Installation L4: Installed Laser Heater |  |  |  | TC
Level of Installation L5: Laser Heater System |  |  |  | WP14
Level of Installation L6: Undulator |  |  |  | WP14
Level of Installation L6: Udulator Support |  |  |  | WP14
Level of Installation L6: Magnet |  |  |  | WP14
Level of Installation L6: Magnet Support |  |  |  | WP12
Level of Installation L6: Coupling Chamber |  |  |  | WP33
Level of Installation L6: Vacuum |  |  |  | WP14
Level of Installation L6: Diagnostic |  |  |  | WP19
Level of Installation L5: Laser Heater Installation |  |  |  | WP17
Level of Installation L4: Commissioned Optical Beamline |  |  |  | WP33
Level of Installation L4: Water Connection |  |  |  | WP14
Level of Installation L4: Magnet Connection |  |  |  | WP34
Level of Installation L4: Vacuum Connection |  |  |  | WP34
Level of Installation L4: Diagnosis Connection |  |  |  | WP19
Level of Installation L3: Laser Heater Alignment |  |  |  | WP17
Level of Installation L2: Connected Injector Dump |  |  |  | WP32
Level of Installation L3: Installed Injector Dump |  |  |  | TC
Level of Installation L4: Aligned Injector Dump Support |  |  |  | WP14
Level of Installation L5: Injector Dump Support |  |  |  | WP20
Level of Installation L5: Injector Dump Support Installation |  |  |  | WP20
Level of Installation L5: Injector Dump Support Alignment |  |  |  | WP33
Level of Installation L4: Installed Injector Dump Absorber |  |  |  | WP32
Level of Installation L5: Injector Dump Absorber |  |  |  | WP20
Level of Installation L5: Diagnostic |  |  |  | WP20
Level of Installation L5: Injector Dump Absorber Installation |  |  |  | WP17
Level of Installation L3: Water Connection |  |  |  | WP33
Level of Installation L3: Diagnosis Connection |  |  |  | WP34
Level of Installation L2: TGA |  |  |  | WP34
Level of Installation L3: Cryogenic System |  |  |  | WP17
Level of Installation L3: Water System |  |  |  | WP34
Level of Installation L4: regular (cooling) Water |  |  |  | WP34
Level of Installation L5: Water Connection (Gun) |  |  |  | WP34
Level of Installation L5: Water Connection (Magnet) |  |  |  | WP34
Level of Installation L5: Flow-Through System |  |  |  | WP34
Level of Installation L4: Process Water |  |  |  | WP34
Level of Installation L5: Water Connection (Gun) |  |  |  | WP34
WP34 | bar: Level of Installation L5
Level of Installation L3: HF System |  |  |  | WP34
Level of Installation L3: Electrical System |  |  |  | WP34
Level of Installation L4: Small Power Supply |  |  |  | WP34
Level of Installation L5: Electronic Racks |  |  |  | WP34
Level of Installation L6: FPGA Regulation |  |  |  | WP34
Level of Installation L6: SCR Bridge |  |  |  | WP34
Level of Installation L7: Magnet Connection |  |  |  | WP34
Level of Installation L6: Cooling System |  |  |  | WP34
Level of Installation L6: Fire Extinguishing Unit |  |  |  | WP34
Level of Installation L6: Cable Guiding |  |  |  | WP34
Level of Installation L5: Redundant System |  |  |  | WP34
Level of Installation L4: Medium Power Supply |  |  |  | WP34
Level of Installation L5: FPGA Regulation |  |  |  | WP34
Level of Installation L5: Quad Connections |  |  |  | WP34
Level of Installation L5: Redundant System |  |  |  | WP34
Level of Installation L4: Large Power Supply |  |  |  | WP34
Level of Installation L5: FPGA Regulation |  |  |  | WP34
Level of Installation L5: Dipole Connections |  |  |  | WP34
Level of Installation L5: Redundant System |  |  |  | WP34

## Process Data
Drop Down
Yes | Assembly | temporary
No | Component | reusable
Lot Part | Catalog | modificable
alternate