## MBOM
Level of Installation | [6 empty] | EDMS ID |  | Metadata |  |  |  | Serialization
L1 | L2 | L3 | L4 | L5 | L6 | L7 | 3D-Modell | Drawing | Amount | Responsible WP | Coordinator | Supplier | Serialized? | S/N Format | Who places S/N? | Label Type
Girder, komplett
Girder mit Vakuumaufbauten
Girder, reinraumtauglich
Girder mit Magneten
Grundgirder
Level of Installation L5: Girdergrundmontage |  |  |  |  | MEA4 | MEA4
Level of Installation L6: Anlieferung nach Halle 1 |  |  |  |  | MEA4 | BAU12
Level of Installation L6: Alu-Platten aufbringen |  |  |  |  | MEA4 | MEA4
Level of Installation L5: Girdermagnete |  |  |  |  | MEA4
Level of Installation L6: XQI, vermessen |  |  |  |  | MEA4 | WP12
Level of Installation L6: XQI, Magnetgestell |  |  |  |  | MEA4 | WP33
Level of Installation L6: XQC, vermessen |  |  |  |  | MEA4 | WP12
Level of Installation L6: XQC, Magnetgestell |  |  |  |  | MEA4 | WP33
Level of Installation L5: Magnetmontage |  |  |  |  | MEA4 | MEA4
Level of Installation L5: Magnete, Grundjustage |  |  |  |  | MEA4 | MEA2
Level of Installation L4: Teilen der Magnete |  |  |  |  | MEA4 | [5 empty] | Wo, evtl erst vor Reinraum?
Level of Installation L4: Vorbereitung auf Reinraum |  |  |  |  | MVS
Level of Installation L4: Magnetoberseiten |  |  |  |  | MEA4
Level of Installation L5: Lagerung |  |  |  |  | MEA4
Level of Installation L3: Transport zum Reinraum | [10 empty] | wo?
Level of Installation L3: Girdervakuumstring |  |  |  |  | MVS
Level of Installation L4: BAM |  |  |  |  | MDI/MSK | Vilcins
Level of Installation L4: BPMA |  |  |  |  | MDI | Noelle
Level of Installation L4: BPMB |  |  |  |  | MDI | Noelle
Level of Installation L4: BPMF |  |  |  |  | MDI | Noelle
Level of Installation L4: CRD (Platzhalter, spätere Installation) |  |  |  |  | MSK | Gerth
Level of Installation L4: DCM |  |  |  |  | MDI | Noelle
Level of Installation L4: EOD |  |  |  |  | MSK | Steffen
Level of Installation L4: OTRA |  |  |  |  | MDI | Holz
Level of Installation L4: OTRB |  |  |  |  | MDI | Holz
Level of Installation L4: OTRC |  |  |  |  | MDI | Holz
Level of Installation L4: OTRL |  |  |  |  | MDI | Holz
Level of Installation L4: PYR |  |  |  |  | MSK | Gerth
Level of Installation L4: TORA |  |  |  |  | MDI | Noelle
Level of Installation L4: TDSA |  |  |  |  | INR/MVS | Gerth
Level of Installation L4: TDSB |  |  |  |  | INR/MVS | Gerth
Level of Installation L4: KAX |  |  |  |  | MVS | Wagner
Level of Installation L4: KBX |  |  |  |  | MVS | Wagner
Level of Installation L4: KBY |  |  |  |  | MVS | Wagner
Level of Installation L4: KDX |  |  |  |  | MVS | Wagner
Level of Installation L4: KDY |  |  |  |  | MVS | Wagner
VCBSTOP
Level of Installation L4: Pumpstücke |  |  |  |  | MVS
Level of Installation L4: Ventile |  |  |  |  | MVS
Level of Installation L4: Bellows |  |  |  |  | MVS
Level of Installation L4: Rohrstücke |  |  |  |  | MVS
Level of Installation L4: Stützen |  |  |  |  | MVS
Level of Installation L3: Vakuummontage |  |  |  |  | MVS
Level of Installation L3: Girder transportfähig machen |  |  |  |  | BAU12
Level of Installation L2: Transport |  |  |  |  | MEA4 | [5 empty] | von wo nach wo?
Magnete schliessen
Wasserdruckprobe
Anzugsdrehmomente prüfen
Level of Installation L3: Berührungsschutz montieren |  |  |  |  | MEA4
Korrekturmagnete aufsetzen
Level of Installation L2: Anschlüsse | [10 empty] | komplett?
Level of Installation L3: Magnetverkabelung |  |  |  |  | MKK
Level of Installation L4: Klemmen | [10 empty] | wo?
Magnetanschlusskabel
Pilothermkabel
Level of Installation L4: Verkabelung |  |  |  |  | MDI
Signalverkabelung
Signalkabel, Satz
Level of Installation L4: Patchfeld | [10 empty] | wo?
Verkabelung
Level of Installation L4: Kalibrierung |  |  |  |  | MKK
Wasseranschlüsse
Level of Installation L4: Wasseranschlüsse | [10 empty] | wo?
Wasserverteilung
Anschlussschläuche
Schlauchverbindung
Level of Installation L4: Druckprobe |  |  |  |  | MDI
Pilothermverkabelung
Level of Installation L4: Anschlussdose | [10 empty] | wo?
Verkabelung
Level of Installation L4: Prüfung |  |  |  |  | MEA2
Abschliessende Vermessung
Abschliessende Justierung
Level of Installation L3: Transfermessung |  |  |  |  | MEA4
Level of Installation L1: Einlagerung | [10 empty] | Halle 1?
XQC Magnet,measured
Girder Magnet Assembly
BPM-F with Support
OTR with Support
EOD with Support
Toroid with Support
Beam Pipe Set for Girder 1
Vacuum Assembly
Cables to Patchpanel
Girder Magnet Alignment

## Process Data
Drop Down
Yes | Assembly | temporary
No | Component | reusable
Lot Part | Catalog | modificable
alternate