## Slide 1: Status of the 3H Module at Injector [XFEL WP46: 3.9 GHz system]
Paolo Pierini
Second Collaboration Meeting of the European XFEL
+ INFN/DESY contributors
PPT version 21/4/2013
Injector Session

## Slide 2: Design and procurement
Cavity Prototypes
  All tested vertically
  (Still) to be assembled in tanks for horizontal tests
All main system components designed
  Cavity PRR in 2011
    Tender assigned to EZ
  Module PRR in 2013
    CFT ongoing
In procurement phase for all main components
  at INFN and DESY

## Slide 3: Prototypes
Test of all 3.9 GHz cavities at INFN
Vertical Test Facility
  18 W @ 2 K / 10 W @ 1.8 K
  less than 1 W static
  VT insert 2x3.9 GHz cavities
  200 W RF
Clean room (9m2), UPW plant and HPR qualified for operation with 1DE15
VT
CR with HPR

## Slide 4: Outcome of VT on prototypes: 3HZ03
Full qualification of 3HZ03, also with HOM antennas
    Q>2 109, Max Eacc 19 MV/m

## Slide 5: 3HZ01 & 3HZ02
Show low Q at low fields and quenches at 12-15 MV/m
  No clear reason but:
    1°time EZ did step/recess equatorial weld
      Now standard on 1.3 GHz, with EBW improvements
    In general less «clean» conditions than actual state
1° test,
Trouble with VC antenna,
switched to FC

## Slide 6: 3HZ01
3HZ01 was sent to FNAL for further benchmarking
  Vertical test reproduce Milano results
  A chemistry at ANL was tried but a leak developed
    Investigating repairs
    HR X scan at avonix by FNAL
Courtesy E. Harms, FNAL

## Slide 7: The module

## Slide 8: Interfaces
Main interfaces discussed at the PRR for the Cold Mass and Vessel in March 2013
Models and specifications uploaded in EDMS
  D*3331741
    Technical specification document, draft form
  D*2128441
    3.9 GHz 3D Models (STEP & JT)
  D*2666811
    3H Module Drawings Baseline
      Third iteration, first two rounds discussed with KJ
Updated documents after PRR changes not yet updated

## Slide 9: XFEL 3.9 Cryomodule design: transverse layout
Design is “Plug compatible” with Type III+/XFEL modules
  Identical transverse X-section for all cryo piping
Module part of the same cryo line with the injector module
  Adapts at interfaces of standard cryo components
Shorter module/string lengths
All cryo piping in the same relative position with respect to beam axis

## Slide 10: Same X-Section as XM1-100...

## Slide 11: Longitudinal interfaces preserved as XM
XFEL Module @ 1.3 GHz
Shorter module length...

## Slide 12: Injector Modules Interconnection

## Slide 13: Vacuum beam components
Interfaces discussed
INFN procuring
  NW 78-40 transition flanges
  Intercavity bellows
DESY procuring
  Standard and «modified» gate valve
Pending WP8 approval

## Slide 14: Quad BPM region
Discussed with HB in several iterations
4K shield mods for assembly

## Slide 15: Vessel interfaces
Coupler vacuum supports agreed and integrated after PRR
  Full model provided by DESY (JH) and integrated
Waveguides supports agreed and integrated after PRR
  Can integrate in model if DESY provides models (JR)

## Slide 16: Interfaces: To Do
Cabling and signal inventory
  XM documentation made available (KJ)
    Will provide similar list to EDMS

## Slide 17: Schedule: Cavities
Kick-Off 17/4
  Contact with Notified Body for design approval and Module G
    INFN will likely act as Manufacturer (TBC)
      All Nb/NbTi material in-house at INFN
    N.B. asked design documentation
      Operating conditions, risk analysis, test conditions
      Will need precise info from DESY
        MAWP=4 bar, agreed
        Statement of pressure used for the tests of cavity/string (complete with tuner?)
  Crude estimate: 40+ wks for 8 cavities ready for string installation from T0 (design approval by Notified Body)
    Review in 4 weeks with vendor timeplan /documentation and further contact with Notified Body

## Slide 18: Test capacity
Cavity schedule based on
  Process at LASA Max 1 cavity/week coming after fine BCP
  2 VT needed (1 w/o HOM, 1 with HOM)
  1 cooldown with 2 cavities every 3 weeks
    Dominated by He batch operation
Horizontal testing
  FNAL is the only short term solution
  We don’t have a cavity ready for HT
    Prototype this summer
    First series in Sep/13 (w/o tank), with tank Oct/13 (T0)
  Discussing use of a modified cryostat adapter in AMTF
    Meeting next Thursday to assess timeline

## Slide 19: Schedule: Couplers & module
4 prototypes ready and conditioned at FNAL
Series of 8(+8) ordered by DESY
  First couple of couplers from CPI to FNAL Sep/2013
  Delivery of others 2/week to FNAL
  Coupler processing at FNAL
    After 4 weeks (max.) at DESY
    First couplers from series ready Oct/2013
Still compatible but with small margins
  String assembly May/2014
  Module installation August/2014
  Technical commissioning September/2014
  Start inj. beam operation October/2014