## Slide 1: Status of the System Components
Mechanics:
  Series fabrication ongoing.
  Series piezo fixture delivery finished.
Drive unit:
  Documentation reports decided.
  First units have FAT and been delivered to CEA and DESY.
  Ramp up to series rate has been achieved.
Piezo system:
  Continuing tests of permanent FLASH setup.
  Series production of fixtures ongoing.
QC testing during module installation at Saclay (INFN contribution).
  Series system completed (rack delivery).
  Software development continues.
Fabrication of all tuner parts ongoing.
Documentation in EDMS continues.
Mechanics
Drive Unit
Piezo System

## Slide 2: Comment to MSPE
Plan overview is simple
  Delivery of components is for one module per week from now on
Recent problem
  Tuner rings
    Manufacturer does not deliver required quality
      Gave up on Monday
    Cross check on how many rings have been delivered is underway
    I do not expect an effect on the cavity production at this moment in time

## Slide 3: Number of components on 31st of July2013
Tunerrings being researched, expectation ~ some 100s
Piezo fixtures ~400
Normal tuners
  Tuner mechanics ~ 300
  Motors ~80
Mirrored tuners
  Tuner mechanics ~ 50
  Motors ~12