## Sheet1
T.Higuchi (Kavli IPMU, Univ. of Tokyo)
Apr. 10th, 2013
Guntt Chart toward the DESY Telescope Test (as of Apr. 10th, 2013)
|  | Sep., 2013 |  |  |  | Oct., 2013 |  |  |  | Nov., 2013 |  |  |  | Dec.,2013 |  |  |  | Jan.,2014
|  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
General | B2GM/BGM | bar: Nov., 2013 2
PXD | Works on sensors, ASICs, and mechanics | bar: Sep., 2013 1 to Sep., 2013 3
Sensors, ASICs, and mechanics get ready | bar: Sep., 2013 4
Integration of DHH, ONSEN, and DATCON | bar: Oct., 2013 1 to Oct., 2013 4
SVD | Works on sensors and mechanics | bar: Sep., 2013 1 to Sep., 2013 3
Sensors and mechanics get ready | bar: Sep., 2013 4
Shipment of FADC and FTB to DESY | bar: Nov., 2013 3
DAQ | Occupied by CDC's beam test | bar: Sep., 2013 1 to Sep., 2013 4
Shipment of POCKET DAQ to DESY | bar: Oct., 2013 1
Integrated system test of POCKET DAQ in DESY | bar: Oct., 2013 2 to Oct., 2013 4
Itoh-san's unavailability | bar: Oct., 2013 4
Nakao-san's unavailability | bar: Nov., 2013 1
PXD+SVD | Dry box and cooling mechanincs assembly | bar: Oct., 2013 1
Cooling system study | bar: Oct., 2013 2 to Oct., 2013 4
Integration of DATCON and SVD | bar: Nov., 2013 3
PXD+DAQ | Integrarion of DHH, ONSEN, MIMOSA, and POCKET DAQ | bar: Oct., 2013 3 to Oct., 2013 4
SVD+DAQ
PXD+SVD+DAQ | Fine tuning of the integrated system | bar: Dec.,2013 1 to Dec.,2013 4
DESY telescope test | bar: Jan.,2014 1 to Jan.,2014 4