## Slide 1: Schedule
Belle 2 Telescope “Gemba” Meeting @ DESY

## Slide 2: SVD Schedule Overview
 |  | Date |  |  | 2013 |  |  |  |  |  |  |  |  |  |  |  | 2014 |  |  | 
 |  | from | to |  | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 01 | 02 | 03 | 04
L3 module | production | 2013/09 | 2013/10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
FADC | design and layout | 2013/02 | 2013/04 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | production, test | 2013/05 | 2013/06 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Altera Daughterboard | Electrical test | 2013/04 | 2013/04 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Basic FW for Data I/O | 2013/04 | 2013/05 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Connectivity test | Test with dummy data | 2013/06 | 2013/06 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
FADC Firmware |  | 2013/06 | 2013/11 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
NECO (controller) | design and layout | 2013/05 | 2013/06 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | production, test | 2013/07 | 2013/08 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Firmware NECO |  | 2013/08 | 2013/11 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Buffer | design, prod., test | 2013/08 | 2013/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Backplane P2 | design, prod., test | 2013/07 | 2013/09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Slowcontrol EPICS | design | 2013/04 | 2013/07 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Software TuxDAQ |  | 2013/07 | 2013/10 | ? |  |  |  |  |  |  | ? | ? | ? | ? |  |  |  |  |  | 
Full SVD readout available |  | 2013/11 | 2013/12 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Testbeam preparation |  | 2013/10 | 2013/12 | ? |  |  |  |  |  |  |  |  |  | ? | ? | ? |  |  |  | 
BEAMTEST @ DESY |  | 2014/01 | 2014/01 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 3: Important Milestones 2013
FADC board
  Layout until mid of April
  Production in May  available by June!
FADC Firmware
  New PhD student: Richard Thalmeier
  Very basic FW for Data I/O by end of May
  Firmware development until mid of Nov. 2013
June: FADC & FTB & DATCON connectivity test
NECO board
  Design and layout finalized by end of June
  Prototype available in July / August
  Firmware development from August to November
End of October: HW & FW test in Vienna, full system

## Slide 4: Important Milestones 2013
Sept.: delivery of L3 sensors  build module
Oct. – Dec.: Beam test preparation @ DESY
  Setup and common test of all subsystems
  November++: DAQ connectivity @ DESY beam test
November: shipping SVD system to DESY
  Second half of November
January 2014: Beam test

## Slide 5: Thank you