## Slide 1
EMCM Assembly Experience
IZM - Finetech - MPP

## Slide 2: Overview
Status at the last DEPFET meeting in June:
  Three EMCMs from test-zmi-5 found to be usable
    Two for partial and one for full assembly (all ASICs and SMDs)
  EMCM-2 production launched with some layout changes comp. to test-zmi-5 and EMCM-1
  Contacts to IZM (FC) and Finetech (SMD) established
The last four months …
  EMCM-2 finished and tested on wafer level (including copper and solder stop)
    Jelena’s talk
    Two EMCMs ready for (partial) assembly at IZM
  EMCM-3 launched
  Three EMCMs assembled
    FC at IZM
    SMD at Finetech
    Kapton attach and wire bonding at MPP
  EMCM evaluation still ongoing, see talks in testing session

## Slide 3: Assembly steps
Flip Chip of ASICs:
  Bumped ASICs have different solder balls (DHP: SnAg C4, DCD: SAC305, SWB: SAC305 on Au-stud)
    ~ reflow temperature ~240 °C
  Due to equipment restrictions CNM was not ready to do the FC on EMCMs  try with IZM
  Avoid flux, or, if flux used, make sure that there are no residues
SMD placement:
  Passive components (termination resistors, decoupling caps)
  Dispense solder paste, pick, place and reflow
    PbSn 37/63 paste  reflow at ~200 °C
  Challenge: small components and foot print! IZM did not want to do this job (no dispenser available)
  Try Finetech, an equipment manufacturer (FC, die attach, rework ..)
Kapton attachment, wire bonding:
  Solder paste printing on kapton,
    Sn42Bi58 solder, ~160 °C
  Kapton – substrate alignment by dowel pins
  Wire bond, wedge-wedge, 25 µm Al bond wires between kapton and substrate

## Slide 4: Flip Chip at IZM
  After some discussions, IZM just did it … first two partially, then one fully populated …
  No issues reported, no use of flux … details unknown!!
  Price tag for this job: 2700 EUR
P6-1
P6-2

## Slide 5: Flip Chip at IZM – first step in the right direction
Things to keep an eye on:
  No QC done!! Just quick X-ray at IZM
    Need shear tests, temp. cycling, aging tests ….
  IZM: possible issues with SAC solder and Au stud, Au is consumed  unreliable connections!
  Testing of DCDs damages bumps  better probe card??
  Missing bumps on SWB
DCD
SWB

## Slide 6: SMD placement at Finetech
0402 and 0201 caps
01005 term. res
we have ~50 0201 and 0402 decoupling caps, ~20 01005 termination resistors:
  very small footprint of components (~220µm)!!
  need for accurate dispensing of very fine solder paste
  process details (will be) disclosed to NTC/IFIC

## Slide 7: Lessons learned at Finetech
01005 misplaced
SMD (01005) is a challenging task:
  Accurate and reproducible dispensing of solder paste
    Pot life of paste, temperature control during dispense..
  Common or individual reflow??
  Little space for the dispense needle between the ASICs!!
~1mm
01005 soldered??

## Slide 8: SMD – open issues
So far the SMD at Finetech was successful, but:
  It is a dead end!! Finetech is not a production facility and has no capacity for “large scale” prod.
  Due time restrictions QC skipped completely!!!
  Possible issue:
    Soldering of ceramic passives to silicon  CTE mismatch  fatigue and cracks …
To do:
  Install SMD process within the collaboration (IFIC/NTC … Daniel’s talk)
    Learn from Finetech experience
  Make more samples!!! Get full control over the process
  Need extensive QC:
    Shear tests
    X-ray
    Cross sections
    Thermal cycling and repeat the tests above
    ….

## Slide 9: Kapton attachment and wire bonding
No real issue - all steps were perfectly prepared by Mandi, Christoph, and Tscharlie at MPP!
Some optimization/improvements:
  Homogeneous solder printing
  Bond loop with 25 µm wire
  Still not decided: do we need a protection for the bond wires??

## Slide 10: In Summary
  The time pressure in spring/summer forced us to find a fast and pragmatic solution for EMCM assembly
    Flip Chip at IZM and SMD at Finetech
  It worked “in principle”, first EMCMs assembled
  But we need to repeat that and - most importantly – qualify the processes so that they can be used for the real thing
Proposed assembly sequence for the PXD ladders:
  Flip chip of all ASICs at IZM
    Price tag: ~3000 EUR NRE costs, ~240 EUR/module  ~30 kEUR for 100 modules (need 40 for PXD..)
  SMD at IFIC/NTC
    See Daniel’s talk
  Kapton attach, wire bonding, ladder assembly at MPP
Next jobs, under the same time pressure:
  Flip chip to PXD6 ladders
    At IZM, preparing jigs now
    No SMDs … 
  Flip chip to more EMCMs – IZM again
  SMD at NTC/IFIC???