## Slide 1: Ladder Parts Production Status
Koji Hara (KEK)

## Slide 2: Ladder Parts
Sensor
Pitch adapters
Origami
H-shape/C-shape
End mount, APV guard, Kokeshi pin
Rib
Airex
Hybrid board
Sil-pad
Pins/screws
Gap pad
CO2 tube clip

## Slide 3
Need to clarify
  Supplier
  Current status
    Production, check, design, …
  Delivery date
    Must be available by prototype assembly in Apr. in the current schedule.
Need to make inventory of delivered parts at each site
    Control the parts delivery and consumption
    Keep trace in the database

## Slide 4: Pitch adapters
Supplier : KEK
Status : bonding pad problem
  Pad width too narrow
  Pull strength is not satisfactory (< 10g)
  Modify the design of patterns
  Check Ni thickness dependence (1um or 3-5um)

## Slide 5
Etching test with modified design of PF2
Pad width : 40 um
Pad length : 200um
Clearance btw pad/line : 15um
Line width : 15 um
The width seems enough.
PF2 test sample products
will be ready by Jan. 30

## Slide 6
Narrowest line width 10um
Increase the width in the design
in the 2nd test design

## Slide 7: Comparison of Pull Strength by Ni Thickness
Tomoko Iwashita 2014.01.21
Full report available on indico

## Slide 8: Pull strength at Ni=1μm and 3-5μm
Chart: Ni=1μm
| 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
P=60,F=10 | 7.8711 | 9.2281 | 11.383 | 9.2158 | 7.8962 | 10.243 | 11.933 | 10.187 | 10.206 | 11.787 | 10.164 | 10.786 | 12.036 | 10.952 | 9.8224 | 9.6512 | 11.782 | 6.0835 | 12.109 | 12.097
P=60,F=20 | 11.827 | 12.841 | 10.471 | 12.091 | 12.463 | 11.952 | 11.425 | 12.188 | 12.496 | 9.9538 | 10.919 | 12.997 | 11.625 | 12.734 | 12.39 | 12.106 | 11.36 | 13.423 | 11.944 | 13.36
P=60,F=25 | 12.052 | 12.111 | 11.506 | 12.375 | 11.303 | 12.96 | 11.947 | 13.328 | 12.037 | 11.526 | 12.312 | 12.093 | 11.933 | 12.809 | 12.674 | 11.777 | 12.542 | 12.419 | 10.478 | 12.021
P=60,F=30 | 10.339 | 12.335 | 13.05 | 11.985 | 12.356 | 10.318 | 10.897 | 10.794 | 12.337 | 11.542 | 12.712 | 11.851 | 10.988 | 12.651 | 12.087 | 11.072 | 9.3799 | 12.86 | 12.405 | 11.49
P=60,F=35 | 9.0316 | 10.999 | 13.438 | 12.038 | 11.128 | 11.351 | 11.592 | 11.532 | 12.244 | 11.264 | 11.813 | 10.495 | 11.616 | 11.633 | 11.411 | 12.151 | 9.8471 | 11.467 | 9.6485 | 12.114
P=60,F=40 | 6.8733 | 8.6401 | 9.6462 | 8.0498 | 8.2055 | 10.409 | 9.2247 | 10.369 | 10.369 | 10.663 | 8.554 | 8.4465 | 9.0365 | 10.617 | 8.9618 | 11.753 | 11.072 | 11.327 | 13.025 | 10.543
P=60,F=50 | 5.427 | 9.0824 | 6.9689 | 8.6258 | 7.493 | 9.1948 | 10.44 | 8.1022 | 7.7329 | 7.6604 | 7.0217 | 6.7366 | 6.6835 | 8.6206 | 9.2261 | 8.0834 | 9.5244 | 6.2869 | 6.9018
Chart: Ni=3-5μm
| 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
P=60,F=10 | 10.708 | 9.4812 | 8.4034 | 7.5696 | 8.2839 | 13.048 | 11.71 | 10.836 | 9.8113 | 10.785 | 13.443 | 9.5344 | 11.961 | 11.367 | 10.927 | 11.001 | 10.171 | 12.033
P=60,F=20 | 10.897 | 11.283 | 9.7396 | 11.923 | 12.052 | 11.255 | 12.39 | 11.539 | 12.754 | 12.316 | 11.887 | 11.783 | 12.228 | 11.885 | 12.162 | 12.079 | 11.493 | 12.517 | 11.688 | 13.221
P=60,F=25 | 12.446 | 12.097 | 12.763 | 11.354 | 11.043 | 10.963 | 12.191 | 11.981 | 11.915 | 12.566 | 10.884 | 11.816 | 12.281 | 11.484 | 11.544 | 11.315 | 11.247 | 12.105 | 10.978 | 12.103
P=60,F=30 | 10.898 | 10.215 | 12.537 | 11.915 | 12.396 | 11.89 | 12.699 | 11.208 | 11.925 | 10.771 | 11.824 | 12.233 | 11.98 | 12.526 | 11.49 | 12.398 | 11.945 | 12.038 | 11.822 | 12.147
P=60,F=40 | 7.5241 | 8.6803 | 10.183 | 9.9871 | 10.231 | 7.7642 | 8.2154 | 7.5985 | 11.001 | 8.9553 | 10.87 | 9.57 | 7.9309 | 7.4529 | 8.7095 | 8.4574 | 9.2149 | 9.6748 | 10.63 | 10.503
P=60,F=50 | 4.2852 | 6.4629 | 6.9813 | 7.4628 | 6.3573 | 6.9 | 7.6235 | 6.1846 | 6.4171 | 6.3186 | 6.7694 | 6.2947 | 7.567 | 7.2942 | 9.0888 | 7.1873 | 9.4147 | 6.4825 | 5.687 | 6.7372

Power (machine parameter) fixed to 60
Changing force
Bond foot at Force 25
It looks not so different.
We think we can use both.
Force parameter
Force parameter
Pull strength (g)
Pull strength (g)
Bond foot at Force 25
20 points / one parameter
Bond foot
Peel Peel/Cut
Bond foot
Peel Peel
Cut
Peel/Cut
Peel/Cut
Cut

## Slide 9: Pitch Adapter Schedule
Jan. 30
modified PF2 sample delivered to IPMU
  24 PF2 for each of Ni 1um and 3-5 um
  Bonding test @ IPMU by Feb. 3
Feb. 13
2nd PF2 test sample (line width optimized)
(Design of other PAs are being done in parallel.)
End of Mar.
  Complete of production expected
  If short circuit occured by 3-5um plating, additional design modification will be necessary to adjust the clearance between patterns
   Complete of the production will delay by ~ 1 month

## Slide 10: Origami
Supplier : KEK
Ordered assembly (Taiyo + REPIC)
  Origami +Z : 27
  Origami CE : 66
  Origami –Z : 48
  Carrying case
Status
  Origami FPC production : completed
  Mounting surface mount parts
  APV mounting (+ APV wire bonding for L4,6)

## Slide 11: Origami Issues
Disconnected lines found in (at least) 2 CE
  Cracks found at the bottom side connector pads
    Hand-soldered
    Connectors attached without H-shape for electrical test
    Reflow soldering for both sides,
    Equip H-shape when connectors are attached
  16 CE in total are suspicious
    APV not equipped. connectors, R, C are mounted.
  2 APV output lines broken in the 1st Origami +Z
    APV equipped, wire-bonded, pre-bended
  Reflow soldering are done for 16 CE, 5 –Z after the change
    Further process suspended until confirmation of the connection
Detailed check of the Origami +Z and CE/-Z after changing the assembly method in the next week.
May need additional production in Apr.

## Slide 12: End Mount
KEK is responsible for the production
L4-6 FW end mount  improved design being prepared by Florian
Production ordered except for L4-6 FW end mount
  L3 FW/BW bridges : 12
  L3 spacers : 48
  L4-6 BW end mount/APV cover/Kokeshi-pin : 75
  Material : Kokeshi-pin SUS304, others A6061
  L4-6 dummy FW end mount
  Rev. 1.0 design (simplified : no sliding mechanism)
    FW L6 APV-guard : 10
    FW end mount and Kokeshi-pin : 30
    For the practice of the ladder assembly
    Ordered using remaining money for end mount
      BW end mount cheaper than rev. 0.11. restricted usage. limit to use was Jan. 17
  Finish by end of Mar. (production takes 2 months)

## Slide 14: Ribs
Supplier : HEPHY
  Production completed
    Some damaged due to trouble in the water jet cutting
     usable for mockup
    Checking possibility to recover them
    Enough number of good quality ribs for ladder production including spares
  Expected delivery date
    Already delivered to HEPHY

## Slide 15: Hybrid board
Supplier : HEPHY
Status
  PCB produced
  Being assembled
   Need APV chips to be transported from KEK

## Slide 16: Misc. parts
Supplier : HEPHY
H-shape/C-shape
    Status : produced
    Already delivered to IPMU
Airex
    Status : produced a part of full number for mass production
      3mm Airex available at HEPHY. Need to press
    Delivery : some already delivered to IPMU enough for prototype
CO2 clip
    Status : produced a part of full number for mass production
    Delivery : 90 clips are already delivered to IPMU
Gap-pad
    Status : produced a part of full number for mass production
    Delivery : enough amount for prototype already delivered to IPMU

## Slide 17
Pins
  Supplier : HEPHY
  Already delivered to IPMU
Screws
  Supplier : HEPHY
  Updated list of screws for rev. 1.0 in hand at HEPHY
   order and deliver soon

## Slide 19: Ladder Parts Status
delivered
in production
open issues

## Slide 22: Main purpose
Check if the bondpad thickness of Ni affects the quality of bonding
In IPMU, we got two samples of metal sheet from Tokaidenshi.
  Cu 3/5μm, Ni 1μm, Au 0.05-0.1μm
  Cu 3/5μm, Ni 3-5μm, Au 0.05-0.1μm

## Slide 23: Sample and parameters
Glued samples to glass plates using Araldite
Bonding parameters (other than Power and Force) are fixed
Bonding distance is 1mm
Glass plate
Glue
Sample
1mm
Bonding point
Bonding point
Here, power and force is machine specific parameters
Power: power of super sonic
Force: pushing force on needle

## Slide 24: Pull test and check
At first, pull
Check the bond foot
  Cut or Peel
And pull strength
Pull center of bonding point and point
Cut
Peel