## Slide 1: X-ray Photon Diagnostics (WP74) Status 08 April 2014
Jan Grünert
European XFEL GmbH, Hamburg
3rd XFEL Collaboration Meeting

## Slide 2: Status WP74
In commercial production: Pop-in monitors
In-house production at European XFEL: 2D-imager-FEL, K-Monochromator, PES, Diff.Pumps
Production by DESY: XGM, transmissive imager
Production by Dubna: MCP-based detector
Design stage: 2D-imager-SR, Exit Slit Imager, Timing Diagnostics
Perspectives until fall 2014:
  Production of XTD2 (SASE1) devices
  Gearing up for first tunnel installations (XTD2)
  Finalizing designs for a few devices or subsystems like 2D-imager-SR, imager optics
  More diagnostics activities (see summary)

## Slide 3: WP74 devices in XTD2 (SASE1)
All z-distances given in the PD coordinate system
619.0m: Filter chamber
620.6m: Transmissive Imager (=OTR-C screen)
639.5m: K-monochromator system, incl. 2D-imager-SR
648.9m: X-ray gas monitor (XGM)
655.9m: Differential Pumping by WP74
659.2m: Photoelectron spectrometer (PES)
681.8m: 2D-imager-FEL
698.9m: MCP detector
700.4m: Pop-in Monitor Type II-45°

## Slide 4: Filter chamber
N:\4all\intern\User data\wp74\Devices\31-2_K-Mono\production drawings\filter chamber
Status 04/2014: all parts in house
Tunnel placement: position agreed
RFI 05/2014
T.b.d. : chamber support

## Slide 5: Transmissive Imager
N:\4all\intern\User data\wp74\Devices\31-8_Transmissive-Imager
„OTR-C“ imager = a standard WP17 device
  (only internal modification for scintillator/holder by WP74, which will be done in contact with WP17 during Q2/2014)
Tunnel placement: position agreed
Integration by WP17 as for their other screen stations

## Slide 6: K-Monochromator
N:\4all\intern\User data\wp74\Devices\31-2_K-Mono
Status 4/2014: Prototype tested. DR/PRR in review. Prototype is now being converted to SASE1 device (is in cleanroom)
RFI May 2014
Integrated in tunnel CAD model, no collisions
Control crate in production; planning of in-tunnel cabling started
2D-imager-SR as part of K-mono-system not yet designed, most likely similar to 2D-imager-FEL version concerning dimension and requirements to tunnel installation.

## Slide 7: X-ray Gas Monitor (XGM)
N:\4all\intern\User data\wp74\Devices\11-1_XGMD\Drawings\FEM steel base frame\support_pillar_pictures
Status 04/2014:
Chambers+interior available / in production (Tiedtke group @ FLASH), detailed design of girder and supports done
RFI XTD2/SASE1: 08/2014 (first complete XGM on girder)
Pillars already arrived (RFI)
Integrated in tunnel CAD model, no collisions
Installation challenge (worse if e-beamline is already in place)

## Slide 8: Differential Pumping by WP74 (between PES and XGM)
N:\4all\intern\User data\wp74\Devices\11-1_XGMD\Drawings\FEM steel base frame\support_pillar_pictures
Status 04/2014:
Design done, mostly standard parts, simlar to WP73 systems
Ordering of vacuum components started
RFI 06/2014 (but installation might be timed with PES)
Integrated in tunnel CAD model, no collisions

## Slide 9: Photoelectron spectrometer (PES)
N:\4all\intern\User data\wp74\Devices\11-1_XGMD\Drawings\FEM steel base frame\support_pillar_pictures
Status 04/2014:
Detailed design done (SASE3, modifications for SASE1 required)
Design of Fully motorized support: done, production ongoing
Most parts for SASE3 device arrived
RFI SASE3 ~10/2014
RFI SASE1 not in 2014 XTD2 installation phase  temporary pipe of 1.6m DN40CF, on dedicated holder

## Slide 10: 2D-imager (FEL)
..
Status 04/2014:
Prototype with control crate in lab
Production SASE1 device ongoing
Optics development ongoing
RFI XTD2/SASE1: 06/2014
No collisions in tunnel CAD model

## Slide 11: MCP-based detector (by JINR)
N:\4all\intern\User data\wp74\Devices\31-1_MCP-Detector\3D-sketches
Status 04/2014:
CDR/TDR/PPR done, prototype at HERA-S and tested
Final supports arrived
Transformation of prototype to SASE1 device in 06/2014
Integrated in tunnel CAD model, no collisions
Design of camera optics ongoing

## Slide 12: Pop-in Monitor Type II-45°
N:\4all\intern\User data\wp74\Devices\31-4_Pop-In-Monitors
Status 04/2014
FDR/PPR done, production ongoing at JJ X-ray
Acceptance of two initial devices done 03/2014
Delivery of all devices for all tunnels in 05/2014
Integrated in tunnel CAD model, no collisions
Detailed optics implementation ongoing

## Slide 13: WP74 summary for SASE1 / XTD2
Filter chamber
Transmissive Imager
K-mono
2D-imager (for SR)
XGM
Differential Pumping by WP74
PES
2D-imager (for FEL)
MCP detector
Pop-in Monitor II-45°
OK
OK
OK
TBD
OK
OK
temp. solution
OK
OK
OK
Device
RFI status

## Slide 14: Other current WP74 design activities (not related to XTD2 installations)
Hard X-ray Single Shot Spectrometer (HXHRSSS)
Diamond Detectors for Intensity & Position Monitoring
Temporal Diagnostics: THz Streaking and Spectral Encoding
Time
Energy
THz streaking
600 fs
Energy
Streaking principle
Setup of a THz-generation setup at XFEL.EU
Participation in a beamtime with PSI at SACLA (2/2014)
REF

## Slide 15: Open issues
Tunnel installation is approaching, need now more detail in XTD2 installation plan: sequence and dates of device vacuum installations, cabling, other infrastructure, temporary storage in tunnels/shafts,…
XTD1 (SASE2) CAD-collisions of supports and transport need to get clarified, this might lead to significant redesigns of WP74 devices compared to SASE1
Coordination needed for common orders across WPs:
  Large sets of turbo pumps
  Control racks (Beckhoff)
  Cables for connecting devices to racks/crates

## Slide 16: WP74 summary
SASE1 / XTD2 devices on track
Other current WP74 design activities (no time for details):
  Hard X-ray Single Shot Spectrometer
  Diamond Detectors
  Temporal Diagnostics
Need now more detailed, agreed XTD2 installation planning for Q2+Q3/2014 (sequence and dates)