## Slide 1: Cryo-XRTL Installations
XFEL Collaboration Meeting
April 8, 2014
K.Jensch MKS1 XFEL WP03 , B.Petersen DESY MKS XFEL WP13
Notes: How to edit the title slide
Upper area: Title of your talk, max. 2 rows of the defined size (55 pt)
Lower area (subtitle): Conference/meeting/workshop, location, date, your name and affiliation, max. 4 rows of the defined size (32 pt)
Change the partner logos or add others in the last row.

## Slide 2: Outline
List of cryo-components in XTL
Status of tunnel boxes production
General sequence of delivery&installation
Individual sequences for tunnel boxes & transfer lines
Tentative sequence of cryomodule installation
Open issues
Summary
Notes: Before you start editing the slides of your talk change to the Master Slide view:
Menu button “View” > Slide Master:
Edit the following items:
1. On the Title slide (second master slide)
a) Click to add title of your talk
b) Click to add subtitle (conference, location, name of the speaker, date)
2. On the Slide Master (first master slide)
a) The 1st row in the violet header: Delete the existent text and write the title of your talk into this text field b) The 2 rows in the footer area: Delete the text and write the information regarding your talk (same as on the Title Slide) into this text field.
If you want to use more partner logos position them left beside the DESY logo in the footer area.
Close Master View

## Slide 3: Production of Tunnel Boxes (DeMaCo NL)
EC 1 at DeMaCo
March 5, 2014
Notes: Before you start editing the slides of your talk change to the Master Slide view:
Menu button “View” > Slide Master:
Edit the following items:
1. On the Title slide (second master slide)
a) Click to add title of your talk
b) Click to add subtitle (conference, location, name of the speaker, date)
2. On the Slide Master (first master slide)
a) The 1st row in the violet header: Delete the existent text and write the title of your talk into this text field b) The 2 rows in the footer area: Delete the text and write the information regarding your talk (same as on the Title Slide) into this text field.
If you want to use more partner logos position them left beside the DESY logo in the footer area.
Close Master View

## Slide 4: List of Components (1)
List of WP03 components in XTL:
100 cryomodules
List of WP13 components in XTL
Transferline XLTL1 from XLVB to Feed-Cap1
XLTL1 = XLTL1 vertical (XSE) + XLTL1 horizontal (XTL)
FC1,EC1 in L1
Transferline XLTL2 (EC1<->FC2)
FC2,EC2 in L2
Transferline XLTL3 (EC2<->FC3)
String Connection boxes
End Cap EC3
Notes: Before you start editing the slides of your talk change to the Master Slide view:
Menu button “View” > Slide Master:
Edit the following items:
1. On the Title slide (second master slide)
a) Click to add title of your talk
b) Click to add subtitle (conference, location, name of the speaker, date)
2. On the Slide Master (first master slide)
a) The 1st row in the violet header: Delete the existent text and write the title of your talk into this text field b) The 2 rows in the footer area: Delete the text and write the information regarding your talk (same as on the Title Slide) into this text field.
If you want to use more partner logos position them left beside the DESY logo in the footer area.
Close Master View

## Slide 5: List of Components (2)
XLTL1 vertical
XLTL1 horizontal
Notes: Before you start editing the slides of your talk change to the Master Slide view:
Menu button “View” > Slide Master:
Edit the following items:
1. On the Title slide (second master slide)
a) Click to add title of your talk
b) Click to add subtitle (conference, location, name of the speaker, date)
2. On the Slide Master (first master slide)
a) The 1st row in the violet header: Delete the existent text and write the title of your talk into this text field b) The 2 rows in the footer area: Delete the text and write the information regarding your talk (same as on the Title Slide) into this text field.
If you want to use more partner logos position them left beside the DESY logo in the footer area.
Close Master View

## Slide 6: Sequence of Components
CMS
FC1
EC1
CMS
FC2
EC2
July 2014
Notes: Before you start editing the slides of your talk change to the Master Slide view:
Menu button “View” > Slide Master:
Edit the following items:
1. On the Title slide (second master slide)
a) Click to add title of your talk
b) Click to add subtitle (conference, location, name of the speaker, date)
2. On the Slide Master (first master slide)
a) The 1st row in the violet header: Delete the existent text and write the title of your talk into this text field b) The 2 rows in the footer area: Delete the text and write the information regarding your talk (same as on the Title Slide) into this text field.
If you want to use more partner logos position them left beside the DESY logo in the footer area.
Close Master View

## Slide 7: List of Components
CMS
FC1
EC1
CMS
FC2
EC2
CMS
FC3
SCB1
October 2014
Notes: Before you start editing the slides of your talk change to the Master Slide view:
Menu button “View” > Slide Master:
Edit the following items:
1. On the Title slide (second master slide)
a) Click to add title of your talk
b) Click to add subtitle (conference, location, name of the speaker, date)
2. On the Slide Master (first master slide)
a) The 1st row in the violet header: Delete the existent text and write the title of your talk into this text field b) The 2 rows in the footer area: Delete the text and write the information regarding your talk (same as on the Title Slide) into this text field.
If you want to use more partner logos position them left beside the DESY logo in the footer area.
Close Master View

## Slide 8: List of Components
XLTL1 vertical
CMS
FC1
EC1
CMS
FC2
EC2
EC3
CMS
FC3
SCB
1-2
November 2014
Notes: Before you start editing the slides of your talk change to the Master Slide view:
Menu button “View” > Slide Master:
Edit the following items:
1. On the Title slide (second master slide)
a) Click to add title of your talk
b) Click to add subtitle (conference, location, name of the speaker, date)
2. On the Slide Master (first master slide)
a) The 1st row in the violet header: Delete the existent text and write the title of your talk into this text field b) The 2 rows in the footer area: Delete the text and write the information regarding your talk (same as on the Title Slide) into this text field.
If you want to use more partner logos position them left beside the DESY logo in the footer area.
Close Master View

## Slide 9: List of Components
XLTL1 vertical
XLTL2
CMS
FC1
EC1
CMS
FC2
EC2
EC3
CMS
FC3
SCB
1-2
December 2014 – January 2015
Notes: Before you start editing the slides of your talk change to the Master Slide view:
Menu button “View” > Slide Master:
Edit the following items:
1. On the Title slide (second master slide)
a) Click to add title of your talk
b) Click to add subtitle (conference, location, name of the speaker, date)
2. On the Slide Master (first master slide)
a) The 1st row in the violet header: Delete the existent text and write the title of your talk into this text field b) The 2 rows in the footer area: Delete the text and write the information regarding your talk (same as on the Title Slide) into this text field.
If you want to use more partner logos position them left beside the DESY logo in the footer area.
Close Master View

## Slide 10: List of Components
XLTL1 vertical
XLTL3
XLTL2
CMS
FC1
EC1
CMS
FC2
EC2
EC3
CMS
FC3
SCB
1-2
Januar - March 2015
Notes: Before you start editing the slides of your talk change to the Master Slide view:
Menu button “View” > Slide Master:
Edit the following items:
1. On the Title slide (second master slide)
a) Click to add title of your talk
b) Click to add subtitle (conference, location, name of the speaker, date)
2. On the Slide Master (first master slide)
a) The 1st row in the violet header: Delete the existent text and write the title of your talk into this text field b) The 2 rows in the footer area: Delete the text and write the information regarding your talk (same as on the Title Slide) into this text field.
If you want to use more partner logos position them left beside the DESY logo in the footer area.
Close Master View

## Slide 11: List of Components
XLTL1 vertical
XLTL3
XLTL2
CMS
FC1
EC1
CMS
FC2
EC2
EC3
CMS
FC3
SCB
1-2
3-4
Februar 2015
Notes: Before you start editing the slides of your talk change to the Master Slide view:
Menu button “View” > Slide Master:
Edit the following items:
1. On the Title slide (second master slide)
a) Click to add title of your talk
b) Click to add subtitle (conference, location, name of the speaker, date)
2. On the Slide Master (first master slide)
a) The 1st row in the violet header: Delete the existent text and write the title of your talk into this text field b) The 2 rows in the footer area: Delete the text and write the information regarding your talk (same as on the Title Slide) into this text field.
If you want to use more partner logos position them left beside the DESY logo in the footer area.
Close Master View

## Slide 12: List of Components
XLTL1 vertical
XLTL3
XLTL2
CMS
FC1
EC1
CMS
FC2
EC2
EC3
CMS
FC3
SCB
1-2
3-4
XLTL1 horizontal
March - April 2015
Notes: Before you start editing the slides of your talk change to the Master Slide view:
Menu button “View” > Slide Master:
Edit the following items:
1. On the Title slide (second master slide)
a) Click to add title of your talk
b) Click to add subtitle (conference, location, name of the speaker, date)
2. On the Slide Master (first master slide)
a) The 1st row in the violet header: Delete the existent text and write the title of your talk into this text field b) The 2 rows in the footer area: Delete the text and write the information regarding your talk (same as on the Title Slide) into this text field.
If you want to use more partner logos position them left beside the DESY logo in the footer area.
Close Master View

## Slide 13: List of Components
XLTL1 vertical
XLTL3
XLTL2
CMS
FC1
EC1
CMS
FC2
EC2
CMS
SCB
5-6
EC3
CMS
FC3
SCB
1-2
3-4
XLTL1 horizontal
May 2015
Notes: Before you start editing the slides of your talk change to the Master Slide view:
Menu button “View” > Slide Master:
Edit the following items:
1. On the Title slide (second master slide)
a) Click to add title of your talk
b) Click to add subtitle (conference, location, name of the speaker, date)
2. On the Slide Master (first master slide)
a) The 1st row in the violet header: Delete the existent text and write the title of your talk into this text field b) The 2 rows in the footer area: Delete the text and write the information regarding your talk (same as on the Title Slide) into this text field.
If you want to use more partner logos position them left beside the DESY logo in the footer area.
Close Master View

## Slide 14: Sequence: Delivery & Installation of boxes & transfer lines
Sequence of WP13 components in XTL
FC1,FC2,EC1,EC2: July 2014
FC3,SCB1 : October 2014
EC3,SCB2: November 2014
XLTL1 vertical (XSE) : November 2014
XLTL2 : December 2014 – January 2015
SCB3,SCB4 : February 2015
XLTL3 : January 2015 – March 2015
XLTL1 horizontal (XTL) : March/April 2015
SCB5, SCB6: May 2015
Notes: Before you start editing the slides of your talk change to the Master Slide view:
Menu button “View” > Slide Master:
Edit the following items:
1. On the Title slide (second master slide)
a) Click to add title of your talk
b) Click to add subtitle (conference, location, name of the speaker, date)
2. On the Slide Master (first master slide)
a) The 1st row in the violet header: Delete the existent text and write the title of your talk into this text field b) The 2 rows in the footer area: Delete the text and write the information regarding your talk (same as on the Title Slide) into this text field.
If you want to use more partner logos position them left beside the DESY logo in the footer area.
Close Master View

## Slide 15: Sequence for individual tunnel boxes: Delivery & Installation
Sequence at delivery for FCs,Ecs,SCBs:
Exchange of beam tubes 2d, MVS, bldg. ???
Transportation DESY site 1d, MEA5
Survey of cap/box at MEA2 2d
Transportation,installation & survey MEA5, MEA2 2d
Installation SV header,capillaries,controls (contractor ?)
Controls/cabeling: MKS2
Required capacities (all boxes): July14 –May15
MEA2 : 48d
MEA5: 36d
MVS: 24 d
Notes: Before you start editing the slides of your talk change to the Master Slide view:
Menu button “View” > Slide Master:
Edit the following items:
1. On the Title slide (second master slide)
a) Click to add title of your talk
b) Click to add subtitle (conference, location, name of the speaker, date)
2. On the Slide Master (first master slide)
a) The 1st row in the violet header: Delete the existent text and write the title of your talk into this text field b) The 2 rows in the footer area: Delete the text and write the information regarding your talk (same as on the Title Slide) into this text field.
If you want to use more partner logos position them left beside the DESY logo in the footer area.
Close Master View

## Slide 16: Sequence for transfer lines: Delivery & Installation (Dec14-March15)
Sequence at delivery of transferlines
delivery 5 x 12m (XLTL2) 8 x 12m (XLTL3) sections
XLTL1: 18 m vertical (crane!), 5 x 12m horizontal
1 week for complete delivery of each XLTLx to DESY
Direct transportation in XTL MEA5
(equivalent of 18 cryomodules = 20d MEA5)
Complete welding on XTL floor, complete lift DEMACO
FREE SPACE at XLTLx positions in XTL !!!
Complete installation of supports DEMACO
Pressure test or 100% X-ray ?
Notes: Before you start editing the slides of your talk change to the Master Slide view:
Menu button “View” > Slide Master:
Edit the following items:
1. On the Title slide (second master slide)
a) Click to add title of your talk
b) Click to add subtitle (conference, location, name of the speaker, date)
2. On the Slide Master (first master slide)
a) The 1st row in the violet header: Delete the existent text and write the title of your talk into this text field b) The 2 rows in the footer area: Delete the text and write the information regarding your talk (same as on the Title Slide) into this text field.
If you want to use more partner logos position them left beside the DESY logo in the footer area.
Close Master View

## Slide 17: Sequence of cryomodule installation (1)
Assumption: all supports installed in XTL (MEA5)
Cryomodule transport to XTL : 1d MEA5
Survey of cryomodules in tunnel: 1d MEA2
Notes: Before you start editing the slides of your talk change to the Master Slide view:
Menu button “View” > Slide Master:
Edit the following items:
1. On the Title slide (second master slide)
a) Click to add title of your talk
b) Click to add subtitle (conference, location, name of the speaker, date)
2. On the Slide Master (first master slide)
a) The 1st row in the violet header: Delete the existent text and write the title of your talk into this text field b) The 2 rows in the footer area: Delete the text and write the information regarding your talk (same as on the Title Slide) into this text field.
If you want to use more partner logos position them left beside the DESY logo in the footer area.
Close Master View

## Slide 18: Sequence of cryomodule installation (2)
Very preliminary !
Scenario for one ‘regular’ 12 cryomodule string
Integral approach: 3d MKS1 + 3d MVS / connection
78 working days for 1 string (13 connections)
Optimized approach:
MKS1 starts with GRT/5K welds 1/d ->string
MVS follows with beam tube 3 d / connection -> string
MKS1 re-starts with process tubes 2d/ connection -> string
5d for individual helium leak checks of welds
MKS1 closing of vacuum bellows 13d ->string
String completed in about 59 d
(integral leak check in the shadow of next string)
Notes: Before you start editing the slides of your talk change to the Master Slide view:
Menu button “View” > Slide Master:
Edit the following items:
1. On the Title slide (second master slide)
a) Click to add title of your talk
b) Click to add subtitle (conference, location, name of the speaker, date)
2. On the Slide Master (first master slide)
a) The 1st row in the violet header: Delete the existent text and write the title of your talk into this text field b) The 2 rows in the footer area: Delete the text and write the information regarding your talk (same as on the Title Slide) into this text field.
If you want to use more partner logos position them left beside the DESY logo in the footer area.
Close Master View

## Slide 19: Open issues for cryo/module installations
Definition of PVI (approval before operation) procedures
Pressure tests versus 100% X-ray of welds ?
Pressure test of 2K process tubes must be avoided (piezos!)
MKS1 prefers 100% X-ray checks -> to be checked with TÜV
Procurement of X-ray checks !
Procedure of X-ray checks of welds -> at night time ?
Backing-gas procedures for welding to be defined
(Argon or Helium ? Tunnel safety issues ?)
Acceptance tests /PVI links to tunnel boxes & transfer lines
Notes: Before you start editing the slides of your talk change to the Master Slide view:
Menu button “View” > Slide Master:
Edit the following items:
1. On the Title slide (second master slide)
a) Click to add title of your talk
b) Click to add subtitle (conference, location, name of the speaker, date)
2. On the Slide Master (first master slide)
a) The 1st row in the violet header: Delete the existent text and write the title of your talk into this text field b) The 2 rows in the footer area: Delete the text and write the information regarding your talk (same as on the Title Slide) into this text field.
If you want to use more partner logos position them left beside the DESY logo in the footer area.
Close Master View

## Slide 20: Summary
Delivery of tunnel boxes in line with cryomodule schedule
Delivery of XLTLs may interfere with BCs installations
Procedures for cryomodule installation need fine tuning
There are still several open issues
Notes: Before you start editing the slides of your talk change to the Master Slide view:
Menu button “View” > Slide Master:
Edit the following items:
1. On the Title slide (second master slide)
a) Click to add title of your talk
b) Click to add subtitle (conference, location, name of the speaker, date)
2. On the Slide Master (first master slide)
a) The 1st row in the violet header: Delete the existent text and write the title of your talk into this text field b) The 2 rows in the footer area: Delete the text and write the information regarding your talk (same as on the Title Slide) into this text field.
If you want to use more partner logos position them left beside the DESY logo in the footer area.
Close Master View