## Slide 1: XFEL Meeting 8 April 2014
String and Module Assembly Status
(WP03 + WP09)
O. Napoly (CEA)

## Slide 2: Status of Assembly

## Slide 3: Status of Assembly
With the current schedule, assuming 1 module/week delivery rate,
XM100 will be delivered beginning of May 2016.

## Slide 4: Alsyom Staffing (SEIV not included)
Project Weeks
2012
2013
2014
Start of training phase
Start of production phase
Start of observation phase
01/04/2914, 24 persons
14/04/2014, 26 persons (+3—1)

## Slide 5: Alsyom Staffing (SEIV not included)
Project Weeks
2013
2012
2014
Start of training phase
Start of production phase
Start of observation phase
w1
w11
w21
w31
w41
w51
w38
XM-3
24/04
17/09
XM-2
02/04
07/08
XM1
04/09
XM2
23/09
XM-1
01/07
27/02
XM6
17/03
XM4
06/01
XM3
21/11
XM5
24/02
26/03
23/04
01/04/2914, 24 persons
14/04/2014, 26 persons (+3—1)

## Slide 6: Problems with coupler PT1000 sensors
Control of PT1000 thermal sensors after observation of two damaged sensors on XM-1 (4A), XM1 (6B)
Current solution (with XFEL Cold part + XFEL 4K shield) leads to collision with the PEEK support when coupler cold part is moved in (range = +- 10 mm). This solution is implemented on XM-1 !
Fixing the coupler thermal sensors problem started today after coupler 4K shield removal, and new routing/winding solution is approved
A
B
B
A
PEEK support

## Slide 7: Corrective action on PT1000 routing
New solution (with XFEL Cold part + XFEL 4K shield) avoids to collision with the PEEK support when coupler cold part is moved in (range = +- 10 mm)
Approval by WP05 obtained
A
B
B
A
B
N.B.: blue stycast left-over from preceding assembly

## Slide 8: Status on 2-phase line welding
XM5 welds reached level 3 (pores  0.8 mm) but 4 welds did not reach level 2 (pores  0.6 mm)
This is a huge disappointment since XM5 cavities had seamless tubes and US-cleaned bellows.
The only possible explanation would be mishandling by the SEIV welder, a certified welder working for XM5 .
The four welds have been repaired last week and will be X-rayed to-morrow (09/04/2014)
Derogation submitted to DESY for the X-Ray of the SS 42mm tube

## Slide 9: Status on X-Ray Radiography at Saclay
X-Ray Campaign follwo-up

## Slide 10: Problems with 80 shields collision
Collision between the 80 K coupler and cryostat thermal shields:
The ‘round’ shape of the cryostat shields is very sensitive.
XM-1, coupler n°8
XM3, coupler n°6

## Slide 11: Problems with 80 shields collision
CEA proposal for a wider cut-out, starting with XM2.