## Slide 1: Warm vacuum XTIN (WP19)
presented by S. Lederer
Notes: How to edit the title slide
Upper area: Title of your talk, max. 2 rows of the defined size (55 pt)
Lower area (subtitle): Conference/meeting/workshop, location, date, your name and affiliation, max. 4 rows of the defined size (32 pt)
Change the partner logos or add others in the last row.

## Slide 2: RF-Gun section
Diagnostic section between RF-Gun and ACC1
  RFI end of March 2014
  3 SIP’s
  3 TSP’s
  3 diagnostic blocks
    Vacuum chambers
    Screens and faraday cups
    collimator
  Support plate – depends on direction of laser in-coupling and space requirements for screen read out

## Slide 3: Photocathode laser beam line
Design for optics ongoing by WP14 (laser group)
  SIP’s
  vacuum pipes
    No forecast possible since design is still pending

## Slide 4: Girder components I
Bellow units
  RFI April 2014
Pipes – RFI to girders April 2014
  Cu tubes raw material
  Turning of Cu tubes - starts
  Flanges – critical path
    New brazing procedure was required to achieve permeability requirements
    Company managed to produce prototypes with correct mr
  Electron beam welding
    Contract with company settled
    Prototype welding ongoing

## Slide 5: Girder components II
SIP’s
Pump t-pieces
  Body RFI
  Cu inserts in production at BINP
Girder supports RFI
Kicker chambers RFI End of February 2014
Mounting of girders could start Mai 2014
  Scheduled to mount 2 girders per week

## Slide 6: Rest
Beam shutter
  Scheduled to be RFI Mai 2014
  Costs open – who pays
Dipole chamber
  Scheduled to be RFI Mai 2014

## Slide 7: Requirements for tunnel installation
Complete infrastructure
  Pressurized air
  Network (cable)
  Electrical power (kein Baustrom)
  All cables pulled
No concrete works, drilling any more