## Slide 1: MSK workshop summary
Julien Branlard
Notes: How to edit the title slide
Upper area: Title of your talk, max. 2 rows of the defined size (55 pt)
Lower area (subtitle): Conference/meeting/workshop, location, date, your name and affiliation, max. 4 rows of the defined size (32 pt)
Change the partner logos or add others in the last row.

## Slide 2: MONDAY AM
XFEL installation
  JB: LLRF installation: steps, team and schedule for WP02
  CG: WP18 installation: not so systematic, keep an eye for personnel overbooking
  MF: test stands: some problems but should be OK for selected devices (uDWC, uADC, TCK7) + guidelines for designers
  WW: racks: preparation stage, on-track, in time for L1
  CS: commissioning (warm) sequential, (cold) in parallel, 2 teams, open questions about FW, HW upgrade during installation
MO and Reference distribution
  LZ: MO: 1 channel ready for Dec. 2014, open points about distributing 216MHz, 10MHz and split the distribution into passive and active part
  DS: REFMs: 68 modules, 13 different types, redundancy control unclear
  CS: laser synch: 46 stabilization units (!), mostly on track, RF for July gun test, final phase noise performance MO delivered in Jan. 2015.

## Slide 3: MONDAY PM
Hardware production
  FL/MF: overview: 33 projects (WP02) 17 projects (WP18) + more! Delays due to unclear/changing requirements, lack of reviews, bad habits
  MC: TMCB2: 2.5 k€, prototypes mid June, visit to ELMA  ask for quote
  MZ: LOGM: almost finished, industrial partner chosen, 2 prototypes mid June, LOGM39 = universal LOGM with standard 450mm chassis
  JP: DCM: new design meets all requirements, 2 units for June, DCM39 unclear
WP02 special diagnostics
  SBH: DS800: project clean up + bug fixes, next production June-July
  SBH: KLM-RTM: general purpose RTM + mezzanine for KLM, write specifications + review required, establish schedule
  SBH: HOM-RTM: tuning filters require several iterations, impact of temperature ? review in DESY required with people in charge
  UM: uLOG: uRFB with MCH-RTM in time for L3, Reset scheme from x2timer-RTM works, full test in July – August
  JB: PZ16M: ITech and call for tender on hold, clarify CE certification, review design modification mid June

## Slide 4: TUESDAY AM
Server and software
  AP: server: working at FLASH, ZMQ, reorganization, CVS -> SVN, unique bin, future work : propr. clean up and automatic update
  CS: software: long list, development team ramps up for XFEL
  Discussion: properties name guildelines, work moving toward real time
MSK lab space:
  FZ: laser lab: space problems, effort toward making OCAS work
  BZ: Helgoland: safety, identified problems, good lab practice,
  Discussion: easy steps to implement, follow up on proposal

## Slide 5: TUESDAY PM
Firmware
  LB: overview: MTCA for FLASH, single cav. Controller, framework, man power is a problem
  CG: summary on parallel session: prioritize WP18 / WP02
  BY : documentation : time consuming draw understandable diagrams, effort to use Doxygen for minimal documentation for users
  Discussion: compatibility with server, deployment, good documentation would require changing working habits, only hope for us is automation (SVN, redmine, doxygen, etc…)
Beyond the XFEL
  TW: HVF: 5/9 licensing in 2013, put DESY on the map, front edge of MTCA.4
  FL: HVF future: some 80-90% done, missing 4 months, other not: EMI classification (additional $$ requested)
  HS: future projects: HVF (licensed module maintenance, EMI lab), ARD (CW RF CW optical synch, sub-fs RF controls, technology transfer DESY-> Helmholtz, FLASH forward plasma, SINBAD), future LLRF projects (Flute, Elbe, BerlinPro, Candle, ESS)  FW, SW mostly

## Slide 6: THANK YOU!